## Start Here
Clinical Roundup ¦ Option C build and scale
MODEL, NOT QUOTE. USD cash planning; US hiring benchmark; 60 months. Blue = editable, green = formula, amber = evidence/quote gap. No PHI or live PoC changes.
← Start Here
Scenario | Base | Workbook navigation ↓ (also see tabs)
Project start (first day of month) | 2026-11-01 | Source refresh and approvals required before commitments.
Enable optional AI (0/1) | 0 | No macros, external workbook links, or network calls in generator.
Enable optional CTMS (0/1) | 0
Mutually exclusive cloud candidate | Azure
Pay founder cash (0/1) | 0
Decision metrics (after Excel recalculation; see snapshot.json for offline results)
5-year total cash spend | 10907250.1099
Year 1 spend / cost-only burn | 1027452.55
Peak FTE incl. founder | 12.75
Cash low point with revenue/financing | -5465729.5339
Maximum financing gap (not sum of deficits) | 5465729.5339
Cost-only financing gap (zero revenue) | 6907250.1099
Quote/unverified vendor allowance subtotal | 428483.5562
Unresolved selected catalog line count | 9
Unpaid founder opportunity cost (outside spend) | 974938.0608
Runway: first negative month / >60 / not funded | 12
Use: 1 choose scenario/start/options; 2 review blue inputs; 3 resolve amber sources; 4 inspect monthly/annual and gates.
No guarantee of PMF, valuation, revenue, compliance or enterprise readiness. Negative cash is not funded.
Baseline = clinical rounding. CTMS requires new study/site workflows, integrations and validation; AI has separate approval gates.
Ranges: low/medium confidence estimates. Cash excludes income/sales taxes, debt interest, equity, depreciation and working-capital delays.
Scenario changes do not prove faster delivery. Gates override calendar; stop before unapproved PHI, AI or research processing.
Assumptions |  | Five-year cash by category
Sources |  | Staff cash | 8684588.2803
Staffing |  | Recruiting | 80000
Nonlabor |  | Equipment | 38250
Requirements |  | INFRA | 93355.5761
Migration WBS |  | TOOLS | 32053.0357
Architecture |  | LEGAL | 71709.6297
Roadmap |  | SECURITY | 95564.4446
Risks and Funding |  | COMPLIANCE | 79637.0372
Staff Months |  | INSURANCE | 63709.6297
Monthly Lean |  | ACCOUNTING | 38225.7778
Monthly Base |  | SUPPORT | 5570.963
Monthly Growth |  | MARKETING | 132333.1735
Monthly Model |  | ONBOARD | 31962.8807
Vendor Months |  | AI | 0
Annual Summary |  | CTMS | 0
Scenario Comparison |  | Contingency | 1417044.0643
Charts |  | Payment fees | 43245.6173
Optional staffing is in Staff cash, not in optional vendor-only categories.
WBS assumed person-days use these staffing pools; not additional project labor invoices.

## Assumptions
Editable scenario assumptions
Selected values are formulas; scenario columns are independent assumptions, not total-cost multipliers. Start and switches live on Start Here.
← Start Here
Key | Assumption | Lean | Base | Growth | Unit | Basis / caveat | Selected
initial_cash | Initial available cash | 500000 | 1000000 | 2000000 | USD | Assumption; not committed financing | 1000000
financing_month | Proposed financing month | 13 | 13 | 10 | month | One hypothetical event; no valuation implied | 13
financing_amount | Proposed financing cash | 1000000 | 3000000 | 6000000 | USD | Editable and uncommitted; set to zero for no financing | 3000000
inflation | Annual non-labor inflation | 3% | 3% | 4% | percent | Planning assumption; annual step from project start | 3%
salary_growth | Annual salary escalation | 3% | 4% | 5% | percent | Planning assumption, not wage forecast | 4%
burden | Employer burden as fraction of WAGES | 40% | 40% | 40% | percent | Selected allowance, includes payroll tax/benefits; never percent of total compensation | 40%
contingency | Contingency on labor + vendor cash | 10% | 15% | 20% | percent | Applied once; excludes founder unpaid opportunity cost and payment fees | 15%
launch | First revenue month (gated assumption) | 16 | 13 | 12 | month | Not authorization for customer PHI pilot | 13
new_customers | New customers per month at launch | 0.5 | 1 | 2 | customers/month | Expected-value cohorts, fractional customers allowed | 1
customer_growth | Annual growth in new customer cohorts | 25% | 50% | 70% | percent | Unproven acquisition assumption; not market data | 50%
churn | Monthly customer churn | 1.5% | 1% | 1% | percent | Applied to opening customers; cohorts start billing immediately | 1%
arpa | Monthly subscription per organization | 500 | 900 | 1400 | USD/customer | Pricing hypothesis, no market validation; no annual prepay | 900
users | Users per active customer | 8 | 15 | 25 | users | Workload assumption | 15
requests | API requests per user per day | 100 | 150 | 250 | requests | 30-day planning months, not performance evidence | 150
storage | GB stored per customer | 2 | 5 | 10 | GB | Stock proxy including history; revisit retention/growth | 5
logs | GB logs ingested per month per customer | 0.5 | 1 | 2 | GB | No PHI in telemetry; cap and sample | 1
tokens_in | AI input tokens per customer/month | 100000 | 300000 | 1000000 | tokens | Only when AI enabled; no PHI until provider approval | 300000
tokens_out | AI output tokens per customer/month | 20000 | 60000 | 200000 | tokens | Assistive use only, human approval and evaluation required | 60000
ai_start | Optional AI work start | 19 | 16 | 16 | month | Does not accelerate core roadmap; retain core approval dependencies if edited | 16
ctms_start | Optional CTMS work start | 31 | 25 | 25 | month | Separate discovery/integration/validation track; no added revenue assumed; retain gate dependencies | 25
founder_salary | Founder annual opportunity salary | 150000 | 180000 | 200000 | USD/year | Selected economic assumption, unpaid by default | 180000
recruiting | Recruiting cost per new role FTE | 5000 | 8000 | 12000 | USD/FTE | Planning allowance, not agency quote | 8000
equipment | Equipment/onboarding per new role FTE | 2500 | 3000 | 3500 | USD/FTE | Cash budget, no accounting capitalization opinion | 3000
payment_rate | Payment processing percent | 3% | 3% | 3% | percent | Allowance for collection fees; contract/payment mix unresolved | 3%
cadence | Iteration length | 2 | 2 | 2 | weeks | Lightweight delivery assumption, not guarantee | 2

## Sources
Cost catalog and public source register
Research access/attempt date is recorded, not inferred. Unavailable primary pages remain unverified. Selected allowances are not vendor quotes; public wage surveys are not startup hiring rates.
← Start Here
Source ID | Publisher | Product / role | Exact public URL | Access / attempt | Effective / survey | Currency | Region | Unit | Public benchmark | Selected allowance | Evidence status | Confidence | Rationale | Exclusions | Refresh by
ASSUMPTION | Planning model | Selected allowances and compensation |  | 2026-10-20 | Model dated 2026-10-20 | USD | US hiring / candidate East US infrastructure | See each cost or assumption row |  |  | Planning allowance | Low | Explicit editable judgment, not proprietary spending or vendor quote. US hiring basis is not founder location preference. | Taxes, financing costs, negotiated agreements, current hiring offers | Before budget approval
BLS-DEV | US Bureau of Labor Statistics | Software developers, national median wage | https://www.bls.gov/ooh/computer-and-information-technology/software-developers.htm | 2026-10-20 | May 2024 historical figure supplied in task; newer survey not verified | USD | US national | employee annual wage | 133080 |  | Unverified | Historical context only | Primary retrieval DNS blocked. $133,080 historical benchmark is not labeled latest or verified here. Selected engineering salaries are separate role assumptions. | Seniority, startup premium, equity, contractor rates, benefits | Before hiring; retrieve latest primary OEWS/OOH
BLS-QA | US Bureau of Labor Statistics | Software QA analysts/testers SOC 15-1253 | https://www.bls.gov/oes/current/oes151253.htm | 2026-10-20 | Survey year unavailable; retrieval blocked | USD | US national | employee annual wage |  | 110000 | Unverified | Low | No current figure verified. $110,000 is a selected salary assumption, not BLS data. | Seniority, location, benefits, contractor billing | Before hiring
BLS-BENEFITS | US Bureau of Labor Statistics | Employer Costs for Employee Compensation | https://www.bls.gov/charts/employer-costs-for-employee-compensation/costs-per-hour.htm | 2026-10-20 | Reference quarter unverified; retrieval blocked | USD | US; choose private industry consistently | benefits / wages ratio |  | 0.4 | Unverified | Low | 40% of wages is a selected all-in employer burden allowance. Correct conversion: benefits/wages, or share_of_total/(1-share_of_total). Broad-industry figures are not startup quotes. | Do not add payroll tax again if already in burden; equity and equipment separate | Before budget approval
GITHUB | GitHub | Team (Enterprise alternative not selected) | https://github.com/pricing | 2026-10-20 | Displayed on access date; effective-from date not stated | USD | Public USD display; no regional variation established | user/month | 4 | 4 | Published price | Medium | Primary HTML retrieved: Team $4/user/month; Enterprise starts $21/user/month, NOT charged. Annual-price section says first 12 months. Model holds selected rate with inflation; renewal must be confirmed. | Tax, promotions/renewal changes, Actions overages, security add-ons, Copilot; separate allowance row covers incremental CI/security | Before purchase / annually
AZURE-APP | Microsoft Azure | Linux App Service candidate | https://azure.microsoft.com/en-us/pricing/details/app-service/linux/ | 2026-10-20 | Unverified; primary retrieval DNS blocked | USD | East US modeled candidate | monthly pooled environment allowance |  | 400 | Quote required | Low | No SKU/meter verified. $400 is explicit dev/stage/prod application allowance, not public retail price. App Service Linux sizing must be quoted. | Exact instance-hours, replicas, reserved discounts and eligibility unresolved | Architecture gate
AZURE-PG | Microsoft Azure | PostgreSQL Flexible Server | https://azure.microsoft.com/en-us/pricing/details/postgresql/flexible-server/ | 2026-10-20 | URL cataloged; price not retrieved or verified | USD | East US modeled candidate | monthly pooled DB allowance |  | 600 | Quote required | Low | Primary+HA standby production and smaller nonprod modeled; no SKU or meter price verified. Compute/storage/backup and HA quote required. | No assertion that cheap tiers qualify for healthcare; BAA/service eligibility review required | Architecture gate
AZURE-RETAIL | Microsoft Azure | Official Retail Prices API research attempt | https://prices.azure.com/api/retail/prices?currencyCode=%27USD%27&$filter=armRegionName%20eq%20%27eastus%27%20and%20serviceName%20eq%20%27Azure%20App%20Service%27%20and%20priceType%20eq%20%27Consumption%27 | 2026-10-20 | No API response obtained | USD | eastus filter | SKU/meter dependent |  |  | Unverified | Unavailable | Exact attempted filter retained; DNS blocked. No meter, unitOfMeasure or effectiveStartDate retrieved. Do not infer current price. | Pagination, tiers, OS and reservation filtering require verification on successful retrieval | Before commitments
AWS | Amazon Web Services | App Runner + RDS PostgreSQL Multi-AZ alternative | https://aws.amazon.com/rds/postgresql/pricing/ | 2026-10-20 | Reference URL only; not fetched | USD | US East modeled alternative; region to select | monthly pooled app/DB allowance |  | 1100 | Quote required | Low | Mutually exclusive comparison allowance, not AWS retail price. Match HA/nonprod/storage/egress/contract terms before selection. | App Runner pricing separate; bundled number is judgment, no negotiated discounts | Architecture decision
AI-PRICE | OpenAI (candidate only) | Optional GPT-4.1-mini candidate; no provider approved | https://openai.com/api/pricing/ | 2026-10-20 | Unverified; DNS blocked | USD | Provider processing region unresolved | USD/million input or output tokens |  |  | Unverified | Low | Model selects provisional 0.40 input / 1.60 output per million tokens solely as editable allowances. NOT verified prices. AI disabled by default; confirm model availability, exact version, rates and tools before enablement. | Tools, caching, fine-tuning, storage, evaluation labor, privacy eligibility and contracts | Before AI gate
AI-PRIVACY | OpenAI (candidate only) | API data controls / provider due diligence | https://platform.openai.com/docs/guides/your-data | 2026-10-20 | Unverified; retrieval blocked | USD | Unresolved | Non-price approval gate |  |  | Unverified | Unavailable | No assurance of retention, zero-data-retention eligibility, regional processing, healthcare contractual coverage or allowed endpoints. Specialist approval before any sensitive data. | Provider policy is not application compliance | Before AI gate
BLS-MANAGER | US Bureau of Labor Statistics | Computer/information systems managers SOC 11-3021 | https://www.bls.gov/oes/current/oes113021.htm | 2026-10-20 | Survey year unavailable; DNS blocked | USD | US national | annual wage |  |  | Unverified | Low | Potential management proxy; no current amount used. | Founder opportunity cost is selected separately, not a BLS management rate | Before hiring
BLS-PROJECT | US Bureau of Labor Statistics | Project management specialists SOC 13-1082 | https://www.bls.gov/oes/current/oes131082.htm | 2026-10-20 | Survey year unavailable; DNS blocked | USD | US national | annual wage |  |  | Unverified | Low | Project management is only a potential product-management proxy; no current amount verified. | Not a startup product leader quote | Before hiring
BLS-DESIGN | US Bureau of Labor Statistics | Web/digital interface designers SOC 15-1255 | https://www.bls.gov/oes/current/oes151255.htm | 2026-10-20 | Survey year unavailable; DNS blocked | USD | US national | annual wage |  | 130000 | Unverified | Low | Selected annual designer retainer equivalent is an assumption, not BLS rate. | Contractor overhead and agency quotes unresolved | Before hiring
BLS-SUPPORT | US Bureau of Labor Statistics | Customer service representatives SOC 43-4051 | https://www.bls.gov/oes/current/oes434051.htm | 2026-10-20 | Survey year unavailable; DNS blocked | USD | US national | annual wage |  | 90000 | Unverified | Low | Weak proxy: technical implementation/customer success differs from customer service. Selected salary is independent assumption. | No customer-success market salary asserted | Before hiring

## Staffing
Phased staffing ¦ annual selected salaries and fractional capacity
FTE bands are months 1–6 / 7–15 / 16–30 / 31–60. Headcount slots ≠ FTE or hiring promise. Contractor annual rates are selected retainer equivalents; no employee burden. Founder cash defaults off.
← Start Here
Scenario | Role ID | Role / responsibility | Engagement | Scope | Start month | End month | FTE M1–6 | FTE M7–15 | FTE M16–30 | FTE M31–60 | Selected annual USD | Benchmark ID | Employer burden / wages | Recruit / added FTE | Equipment / added FTE
Lean | FOUNDER | Founder / product / clinical lead | Founder | Core | 1 | 60 | 0.75 | 0.75 | 0.75 | 0.75 | 150000 | ASSUMPTION | 0% | 0 | 2500
Lean | LEAD | Tech lead / full stack | Employee | Core | 1 | 60 | 1 | 1 | 1 | 1 | 165000 | BLS-DEV | 40% | 5000 | 2500
Lean | BACKEND | Backend / tenant API / data migration | Employee | Core | 4 | 60 | 0.5 | 0.75 | 1 | 1 | 145000 | BLS-DEV | 40% | 5000 | 2500
Lean | FRONTEND | Frontend / mobile workflows | Employee | Core | 7 | 60 | 0 | 0.5 | 0.75 | 1 | 140000 | BLS-DEV | 40% | 5000 | 2500
Lean | QA | QA automation / migration reconciliation | Employee | Core | 5 | 60 | 0.25 | 0.5 | 0.75 | 1 | 110000 | BLS-QA | 40% | 5000 | 2500
Lean | OPS | DevOps / security engineering | Fractional contractor | Core | 2 | 60 | 0.15 | 0.2 | 0.25 | 0.5 | 190000 | BLS-DEV | 0% | 0 | 2500
Lean | DESIGN | Product design / accessibility | Fractional contractor | Core | 2 | 24 | 0.15 | 0.15 | 0.1 | 0 | 130000 | ASSUMPTION | 0% | 0 | 2500
Lean | VALIDATION | Compliance / legal / validation owner | Fractional contractor | Core | 2 | 60 | 0.1 | 0.15 | 0.15 | 0.2 | 200000 | ASSUMPTION | 0% | 0 | 2500
Lean | SUCCESS | Implementation / customer success / support | Employee | Core | 12 | 60 | 0 | 0.25 | 0.5 | 1 | 90000 | ASSUMPTION | 40% | 5000 | 2500
Lean | SALES | Sales / partnerships (no commission forecast) | Employee | Core | 25 | 60 | 0 | 0 | 0.25 | 0.5 | 120000 | ASSUMPTION | 40% | 5000 | 2500
Lean | AI-ENG | Optional AI / data evaluation engineer | Employee | AI | 19 | 60 | 0 | 0 | 0.5 | 0.5 | 170000 | BLS-DEV | 40% | 5000 | 2500
Lean | CTMS-PM | Optional research operations / CTMS domain lead | Fractional contractor | CTMS | 31 | 60 | 0 | 0 | 0 | 0.5 | 180000 | ASSUMPTION | 0% | 0 | 2500
Lean | CTMS-ENG | Optional CTMS integrations / research validation | Employee | CTMS | 31 | 60 | 0 | 0 | 0 | 0.5 | 155000 | BLS-DEV | 40% | 5000 | 2500
Base | FOUNDER | Founder / product / clinical lead | Founder | Core | 1 | 60 | 1 | 1 | 1 | 1 | 180000 | ASSUMPTION | 0% | 0 | 3000
Base | LEAD | Tech lead / full stack | Employee | Core | 1 | 60 | 1 | 1 | 1 | 1 | 165000 | BLS-DEV | 40% | 8000 | 3000
Base | BACKEND | Backend / tenant API / data migration | Employee | Core | 3 | 60 | 1 | 1 | 2 | 2 | 145000 | BLS-DEV | 40% | 8000 | 3000
Base | FRONTEND | Frontend / mobile workflows | Employee | Core | 4 | 60 | 0.5 | 1 | 1 | 2 | 140000 | BLS-DEV | 40% | 8000 | 3000
Base | QA | QA automation / migration reconciliation | Employee | Core | 4 | 60 | 0.5 | 0.75 | 1 | 2 | 110000 | BLS-QA | 40% | 8000 | 3000
Base | OPS | DevOps / security engineering | Fractional contractor | Core | 2 | 60 | 0.25 | 0.5 | 0.75 | 1 | 190000 | BLS-DEV | 0% | 0 | 3000
Base | DESIGN | Product design / accessibility | Fractional contractor | Core | 2 | 36 | 0.25 | 0.25 | 0.25 | 0.25 | 130000 | ASSUMPTION | 0% | 0 | 3000
Base | VALIDATION | Compliance / legal / validation owner | Fractional contractor | Core | 2 | 60 | 0.15 | 0.25 | 0.25 | 0.5 | 200000 | ASSUMPTION | 0% | 0 | 3000
Base | SUCCESS | Implementation / customer success / support | Employee | Core | 10 | 60 | 0 | 0.5 | 1 | 2 | 90000 | ASSUMPTION | 40% | 8000 | 3000
Base | SALES | Sales / partnerships (no commission forecast) | Employee | Core | 19 | 60 | 0 | 0 | 0.5 | 1 | 120000 | ASSUMPTION | 40% | 8000 | 3000
Base | AI-ENG | Optional AI / data evaluation engineer | Employee | AI | 16 | 60 | 0 | 0 | 0.75 | 1 | 170000 | BLS-DEV | 40% | 8000 | 3000
Base | CTMS-PM | Optional research operations / CTMS domain lead | Fractional contractor | CTMS | 25 | 60 | 0 | 0 | 0.5 | 1 | 180000 | ASSUMPTION | 0% | 0 | 3000
Base | CTMS-ENG | Optional CTMS integrations / research validation | Employee | CTMS | 25 | 60 | 0 | 0 | 0.5 | 1 | 155000 | BLS-DEV | 40% | 8000 | 3000
Growth | FOUNDER | Founder / product / clinical lead | Founder | Core | 1 | 60 | 1 | 1 | 1 | 1 | 200000 | ASSUMPTION | 0% | 0 | 3500
Growth | LEAD | Tech lead / full stack | Employee | Core | 1 | 60 | 1 | 1 | 1 | 1 | 165000 | BLS-DEV | 40% | 12000 | 3500
Growth | BACKEND | Backend / tenant API / data migration | Employee | Core | 2 | 60 | 1 | 2 | 3 | 4 | 145000 | BLS-DEV | 40% | 12000 | 3500
Growth | FRONTEND | Frontend / mobile workflows | Employee | Core | 3 | 60 | 1 | 1 | 2 | 3 | 140000 | BLS-DEV | 40% | 12000 | 3500
Growth | QA | QA automation / migration reconciliation | Employee | Core | 3 | 60 | 0.5 | 1 | 2 | 3 | 110000 | BLS-QA | 40% | 12000 | 3500
Growth | OPS | DevOps / security engineering | Fractional contractor | Core | 2 | 60 | 0.5 | 0.75 | 1 | 2 | 190000 | BLS-DEV | 0% | 0 | 3500
Growth | DESIGN | Product design / accessibility | Fractional contractor | Core | 2 | 60 | 0.5 | 0.5 | 0.75 | 1 | 130000 | ASSUMPTION | 0% | 0 | 3500
Growth | VALIDATION | Compliance / legal / validation owner | Fractional contractor | Core | 2 | 60 | 0.25 | 0.5 | 0.75 | 1 | 200000 | ASSUMPTION | 0% | 0 | 3500
Growth | SUCCESS | Implementation / customer success / support | Employee | Core | 9 | 60 | 0 | 1 | 2 | 4 | 90000 | ASSUMPTION | 40% | 12000 | 3500
Growth | SALES | Sales / partnerships (no commission forecast) | Employee | Core | 16 | 60 | 0 | 0 | 1 | 3 | 120000 | ASSUMPTION | 40% | 12000 | 3500
Growth | AI-ENG | Optional AI / data evaluation engineer | Employee | AI | 16 | 60 | 0 | 1 | 1 | 2 | 170000 | BLS-DEV | 40% | 12000 | 3500
Growth | CTMS-PM | Optional research operations / CTMS domain lead | Fractional contractor | CTMS | 25 | 60 | 0 | 0 | 1 | 1 | 180000 | ASSUMPTION | 0% | 0 | 3500
Growth | CTMS-ENG | Optional CTMS integrations / research validation | Employee | CTMS | 25 | 60 | 0 | 0 | 1 | 2 | 155000 | BLS-DEV | 40% | 12000 | 3500

## Nonlabor
Non-labor cash catalog ¦ stable cost IDs
Only one cloud stack charged. Annual items recur start+12n; Once items occur once. Optional items start at MAX(catalog start, scenario expansion start). Salary is only in Staffing; WBS labor is informational.
← Start Here
Cost ID | Category | Line item | Stack | Scope | Start | End | Frequency | Quantity driver | Selected rate USD | Source ID | Evidence status | Caveat / exclusions | Active unresolved line
INFRA-APP | INFRA | API / worker / frontend managed app allowance | Azure | Core | 1 | 60 | Monthly | Fixed | 400 | AZURE-APP | Quote required | App Service candidate; dev/stage/prod pooled allowance, not an SKU quote | 1
INFRA-DB | INFRA | Managed PostgreSQL HA + nonprod allowance | Azure | Core | 1 | 60 | Monthly | Fixed | 600 | AZURE-PG | Quote required | Flexible Server candidate; production primary + HA standby, nonprod smaller; backups separate | 1
INFRA-AWS | INFRA | Alternative AWS app + PostgreSQL HA bundle | AWS | Core | 1 | 60 | Monthly | Fixed | 1100 | AWS | Quote required | Mutually exclusive Azure app/DB; App Runner + RDS Multi-AZ candidate, not quote | 0
INFRA-EDGE | INFRA | WAF/CDN, identity, DNS and transactional email | Both | Core | 1 | 60 | Monthly | Fixed | 250 | ASSUMPTION | Quote required | Includes minimum identity/email allowance; eligibility and MAU tiers to quote | 1
INFRA-STORE | INFRA | Object storage / backups / egress | Both | Core | 1 | 60 | Monthly | StorageGB | 0.15 | ASSUMPTION | Planning allowance | Blended selected rate, no claim of Azure/AWS retail storage price | 0
INFRA-LOG | INFRA | Logs / queues / secrets / metrics | Both | Core | 1 | 60 | Monthly | LogGB | 5 | ASSUMPTION | Planning allowance | Blended usage rate; privacy filters, retention and ingestion caps required | 0
INFRA-REQ | INFRA | Capacity growth reserve per million API requests | Both | Core | 1 | 60 | Monthly | RequestsM | 30 | ASSUMPTION | Planning allowance | Capacity reserve not serverless quote; load test before resize | 0
TOOLS-GH | TOOLS | GitHub Team seats (only selected plan) | Both | Core | 1 | 60 | Monthly | Seats | 4 | GITHUB | Published price | Public starting price; promotions/taxes/CI allowances not assumed perpetual | 0
TOOLS-CI | TOOLS | Incremental CI, dependency scan, secrets and security tools | Both | Core | 1 | 60 | Monthly | Seats | 45 | ASSUMPTION | Planning allowance | Above included plan limits; no Copilot or enterprise plan implicitly charged | 0
LEGAL-SETUP | LEGAL | Privacy, DPA, BAA, terms, company and IP contracts | Both | Core | 2 | 2 | Once | Fixed | 20000 | ASSUMPTION | Quote required | External counsel deliverables, not duplicate embedded validation staff | 1
LEGAL-RENEW | LEGAL | External legal contract review retainer | Both | Core | 14 | 60 | Annual | Fixed | 12000 | ASSUMPTION | Quote required | Annual renewal at start+12n; legal applicability not guaranteed | 1
SECURITY-TEST | SECURITY | Independent penetration test + retest | Both | Core | 10 | 60 | Annual | Fixed | 18000 | ASSUMPTION | Quote required | Independent assessment, not engineering labor | 1
COMPLIANCE-EXT | COMPLIANCE | Independent readiness / validation assessment | Both | Core | 11 | 60 | Annual | Fixed | 15000 | ASSUMPTION | Quote required | No certification or regulatory clearance promised | 1
INSURANCE | INSURANCE | Cyber / E&O insurance | Both | Core | 9 | 60 | Annual | Fixed | 12000 | ASSUMPTION | Quote required | Coverage and exclusions require broker quote | 1
ACCOUNTING | ACCOUNTING | Bookkeeping / tax and payroll services | Both | Core | 1 | 60 | Monthly | Fixed | 600 | ASSUMPTION | Quote required | Service cash only; income/sales tax itself excluded | 1
SUPPORT | SUPPORT | Support tooling / knowledge base | Both | Core | 9 | 60 | Monthly | Fixed | 100 | ASSUMPTION | Planning allowance | Customer success labor separately in Staffing | 0
MARKETING | MARKETING | Demand discovery then measured marketing experiments | Both | Core | 10 | 60 | Monthly | Customers | 75 | ASSUMPTION | Planning allowance | No implied CAC or automatic product-market fit | 0
ONBOARD | ONBOARD | Customer travel / training materials / migration expenses | Both | Core | 10 | 60 | Monthly | NewCustomers | 300 | ASSUMPTION | Planning allowance | External expenses only; implementation staff already costed | 0
AI-IN | AI | Optional model input tokens / million | Both | AI | 1 | 60 | Monthly | InputM | 0.4 | AI-PRICE | Unverified | Conservative placeholder until source verification; provider/privacy gate | 0
AI-OUT | AI | Optional model output tokens / million | Both | AI | 1 | 60 | Monthly | OutputM | 1.6 | AI-PRICE | Unverified | Placeholder until source verification; human review not automated clinical advice | 0
AI-EVAL | AI | Optional independent AI evaluation / provider review | Both | AI | 1 | 60 | Annual | Fixed | 15000 | ASSUMPTION | Quote required | First occurs at scenario AI start then annually | 0
CTMS-EXT | CTMS | Optional research systems validation and integration contracts | Both | CTMS | 1 | 60 | Annual | Fixed | 40000 | ASSUMPTION | Quote required | First at CTMS start; study/site/EDC/eTMF scope, not patient relabeling | 0

## Requirements
Requirements and evidence register
Repository presence = Implemented, not Verified or In customer use. Successful M365 PoC is user-reported; no deployment verification performed.
← Start Here
Id | Heading | Item | Evidence | Status | Caveat | Requirement | Acceptance | Priority | Phase | Owner | Dependency | Scope | Wbs | Cost
R1.1 | 1. Product / current baseline | 1.1 Census, encounters, findings, procedures, STAT, handoff and history | clinical-rounding-adaptive.html: openModal, savePatient, renderMainTable, generateHandoff; USP.md | Implemented | Code/documentation present; no running deployment or customer-use verification here. | Preserve core rounding behavior through characterization and clinical acceptance. | Synthetic golden journeys; visit history/backfeed excludes fresh findings; clinician sign-off. | P0 | Assess | Founder / QA | None | Core | W1.1 | STAFF
R1.2 | 1. Product / source of truth | 1.2 Canonical source and release inventory | README.md; AGENTS.md; .github/copilot-instructions.md; release/; azure-integration.js; clinical-rounding-adaptive.html.orig/.rej | Implemented | Firebase-era instructions conflict with newer browser-MSAL-Graph-M365 description. Root/release duplicates and Azure alternative are not interchangeable. | Record canonical product/version, alternatives and supported artifact manifest. | Approved inventory and diff; no changes to PoC during planning; one future release source of truth. | P0 | Assess | Tech lead | R1.1 | Core | W1.2 | STAFF
R1.3 | 1. Product / customers | 1.3 Intended use, buyer and commercial scope | USP.md; README.md; documents/exec-brief/Clinical-Roundup-CTMS-Exec-Brief.md | Idea | User reports successful M365 PoC; this is not evidence of paid demand or CTMS readiness. | Choose specialty-practice rounding wedge; define exclusions, pilot agreement and success criteria. | Buyer interviews, named decision-maker, clinical safety review, pilot acceptance contract; no valuation target. | P0 | Assess | Founder / clinical lead | R1.1 | Core | W1.3 | STAFF
R2.1 | 2. Refactor / frontend | 2.1 Extract UI and domain modules | clinical-rounding-adaptive.html: savePatient, renderUI, setTab, Device; import-engine.js | Idea | Large single-file app is reusable behavior, not an established modular SaaS codebase. | Extract forms/domain services, typed API boundary and mobile components incrementally; framework decision after spike. | Characterization regressions pass; accessible phone/tablet flows, no PHI in fixtures. | P0 | Foundation | Tech lead / frontend | R1.1 | Core | W2.1 | STAFF
R2.2 | 2. Refactor / services | 2.2 Server API, contracts and authorization | api/patients/index.js; api/backfeed/index.js; api/settings/index.js; api/onCallSchedule/index.js; api/export/index.js; api/shared/dataService.js; staticwebapp.config.json | Implemented | API alternative has role checks and Graph access; runtime trust boundary and deployment not verified. Not a proven SaaS backend. | Validate requests, trusted identity and tenant-scoped access server-side; contract/version tests, idempotency and optimistic concurrency. | Cross-tenant negative tests on every method including export; malformed requests denied; replay/concurrency tests; no header trust without gateway validation. | P0 | Foundation | Backend / security | R3.1 | Core | W2.2 | STAFF
R3.1 | 3. Identity / tenant data | 3.1 Organizations, membership, roles and boundaries | m365-integration.js: M365_CONFIG, login, getAccessToken; api/patients/index.js | Idea | Single configured site/list and UI controls are not proof of commercial tenant isolation. | Tenant lifecycle, verified organization membership, per-resource authorization, invitation/revocation and admin separation. | Two synthetic tenants cannot enumerate/read/write/export each other; offboarding revokes access. | P0 | Foundation | Backend / tech lead | R1.3 | Core | W3.1 | STAFF
R3.2 | 3. Identity / tenant data | 3.2 Patient and encounter identity, schema and indexes | m365-integration.js: api_savePatient computeVisitKey, resolvePatientItemIdByVisitKey; api/shared/dataService.js | Implemented | Current MRN/date-style VisitKey is not globally unique across organizations; hospital/source scope must be decided. | Design tenant+source/facility-scoped patient IDs and encounter IDs; constraints, migrations, indexes and retention. | Same MRN/date in two organizations remains isolated; multiple encounters/day policy; reversible migration and query plans. | P0 | Foundation | Backend / data lead | R3.1 | Core | W3.2 | STAFF
R3.3 | 3. Identity / tenant data | 3.3 Cache, offline, conflict and session policy | m365-integration.js: startPolling, fetchAllData, localStorage cache, triggerServerSessionInvalidation; clinical-rounding-adaptive.html | Implemented | Polling/cache/session code presence does not prove isolation, revocation or privacy behavior. | Explicit offline/PHI policy, tenant-aware cache purge, session timeout, conflict detection and safe retries. | Shared-browser tenant switch, lost-device/logout/cache purge, expired session and stale write tests. | P0 | Foundation | Frontend / security | R3.1 | Core | W3.3 | STAFF
R4.1 | 4. Migration / interoperability | 4.1 SharePoint extraction and field mapping | m365-integration.js: api_fetchPatients, api_savePatient, api_fetchOnCallSchedule, api_fetchSettings; api/shared/dataService.js | Idea | Graph/SharePoint field names, choices, dates, JSON findings and attachments must be mapped, not copied blindly. | Version source schema manifest and export mapping; map internal field names/types/nulls/timezones/VisitKey to SaaS IDs. | Synthetic sample export with findings/codes/values, archive, on-call, settings, document links; signed mapping and exceptions. | P0 | Foundation | Backend / implementation | R3.2 | Core | W4.1 | STAFF
R4.2 | 4. Migration / interoperability | 4.2 Import/export data integrity and documents | import-engine.js; clinical-rounding-adaptive.html: previewBulkImport, proceedBulkImport; m365-integration.js: exportToOneDrive, api_uploadPatientFile, api_fetchPatientFiles | Implemented | Preview, bulk/resume and document paths require production-oriented validation, limits and authorization. | Retain preview/dedup/resume semantics with server validation; tenant object storage, signed downloads, safe CSV/XLSX exports and malware policy. | Synthetic duplicate/corrupt/large-file/retry tests; formula-injection controls; no cross-tenant document access or public PHI links. | P0 | Foundation | Backend / QA | R4.1 | Core | W4.2 | STAFF
R4.3 | 4. Migration / interoperability | 4.3 Rehearsal, reconciliation, cutover and rollback | m365-integration.js; import-engine.js; docs/testing/E2E_TEST_RECORDS_MANUAL.txt | Idea | No evidence here of a verified migration runbook or lossless live cutover. | Synthetic rehearsals; counts, canonical hashes and per-field reconciliation; staged tenant cutover with source write pause and rollback. | 100% explained record/field exceptions; restore rehearsal; signed go/no-go, rollback trigger and elapsed window; no uncontrolled dual-write. | P0 | Synthetic pilot | Implementation / backend / QA | R4.2 | Core | W4.3 | STAFF
R4.4 | 4. Migration / interoperability | 4.4 PoC coexistence, retirement and exit portability | README.md; AGENTS.md; release/; .github/workflows/deploy-to-pages.yml | Idea | Existing Pages pipeline deploys a static subset, not the future SaaS stack. | Keep PoC read-only or separately owned per cutover plan; customer export/exit, retention and deletion policy. | Accountable source-of-record per tenant; reconcile final export; no deletion until rollback/retention approvals; customer exit tested. | P1 | Approved pilot | Founder / implementation | R4.3 | Core | W4.4 | STAFF
R5.1 | 5. Trust / compliance | 5.1 Audit, privacy and specialist applicability | .kiro/specs/healthcare-compliance/requirements.md; design.md; tasks.md; api/patients/index.js: logAudit; m365-integration.js: api_logAuditEvent | Implemented | Spec/task completion checkboxes and audit calls are not independent control evidence; cloud encryption cannot be inferred absent/present from client code. | Threat model, privacy minimization, attributable tamper-resistant audit, access review, retention and qualified regulatory/BAA assessment. | Audit read/write/export/admin coverage and protected retention tests; counsel-approved agreements and service eligibility; no automatic SOX mandate. | P0 | Foundation | Security / validation / legal | R3.1 | Core | W5.1 | COMPLIANCE
R5.2 | 5. Trust / compliance | 5.2 Independent review and approved customer pilot | .kiro/specs/healthcare-compliance/*; docs/testing/New E2E.md | Idea | No security attestation, clinical validation, customer use or compliance certification asserted. | Clinical safety acceptance, independent penetration test/retest, contracts, data-handling approval and incident response before customer PHI. | No unaccepted critical findings; documented residual risk; clinical/technical/legal sign-offs; customer pilot stop rules. | P0 | Approved pilot | Founder / security / validation | R5.1 | Core | W5.2 | SECURITY
R6.1 | 6. Delivery / operations | 6.1 Automated characterization, contracts and release gates | api/package.json: test echoes No tests yet; docs/testing/E2E_UI_TEST_SEQUENCE_TEEN.md; docs/testing/New E2E.md; tools/diagnostics/ | Implemented | Manual guides/diagnostics exist; placeholder API test command is not automated assurance. This workbook does not add SaaS application tests. | Practical CI unit/integration/e2e, tenant isolation, import round-trip, mobile and restore tests; reviewed PRs and staged deployment. | Repeatable synthetic pipeline, meaningful failures, evidence retained per release, dependency/secrets scans and rollback drill. | P0 | Assess | QA / tech lead | R1.1 | Core | W6.1 | STAFF
R6.2 | 6. Delivery / operations | 6.2 Managed infrastructure and environment isolation | staticwebapp.config.json; api/host.json; .github/workflows/deploy-to-pages.yml; azure-integration.js | Idea | Existing Azure config/API alternative does not establish deployed SaaS environments. | Managed modular monolith; dev/stage/prod, relational DB, object storage, worker/queue, secrets, identity, edge/WAF and IaC review. | Documented SKU/region/replicas, isolation and budgets; mutually exclusive Azure/AWS choice; no production PHI in nonprod. | P0 | Foundation | DevOps / tech lead | R3.2 | Core | W6.2 | INFRA
R6.3 | 6. Delivery / operations | 6.3 Backup, recovery, telemetry and incident operations | api/host.json; m365-integration.js: error/retry paths; .kiro/specs/healthcare-compliance/requirements.md | Idea | Config presence is not restore evidence or SLA. | Proposed pilot RPO 24h/RTO 8h, growth RPO 1h/RTO 4h subject to quote/test; PHI-free logging, alerting and incident runbooks. | Timed restore test, deletion-retention review, on-call coverage, incident tabletop and cost/ingestion alert drill. | P0 | Synthetic pilot | DevOps / security | R6.2 | Core | W6.3 | INFRA
R6.4 | 6. Delivery / operations | 6.4 Onboarding, subscriptions, admin and support | clinical-rounding-adaptive.html: settings; m365-integration.js: settings APIs; USP.md | Idea | Settings/billing code entry are not SaaS subscription billing or tenant provisioning. | Tenant onboarding/admin, subscription lifecycle, entitlement checks, invoicing, support/escalation and account offboarding. | Synthetic invoice/failed payment/cancel/refund, role invitation/revocation and onboarding playbook; support ownership staffed. | P0 | Approved pilot | Implementation / backend / founder | R3.1 | Core | W6.4 | STAFF
R6.5 | 6. Delivery / operations | 6.5 Load, scaling and repeatability | m365-integration.js: polling; import-engine.js: queue/throttle; README.md | Idea | No measured SaaS throughput or customer acquisition evidence; polling need not be replaced without measurement. | Measure concurrent rounding/imports and cost per tenant; resize from observed SLO, optimize queries/jobs before distribution. | Representative load and noisy-neighbor tests, p95/queue/DB alarms; repeat deployment and pilot feedback gate before growth hires. | P1 | Repeatable | Tech lead / DevOps / success | R6.3 | Core | W6.5 | STAFF
R7.1 | 7. Optional expansions | 7.1 Assistive AI with human approval | AI_USP.md; documents/AI_AUGMENTATION_OPTIONS.md | Idea | Backlog ideas are not implemented/evaluated models. Provider price/privacy pages unavailable; default off. | Narrow assistive use case, synthetic eval, sources/provenance, human review, privacy/contract/endpoint approval, cost limits and fallback. | Approved evaluation thresholds, no unapproved PHI, provider review, prompt-injection and safety tests; no automatic clinical decision. | Optional | Expansion | AI engineer / clinical / security | R5.2 | AI | W7.1 | AI
R7.2 | 7. Optional expansions | 7.2 Trial operations intelligence / CTMS discovery | documents/exec-brief/Clinical-Roundup-CTMS-Exec-Brief.md; AI_USP.md | Idea | CTMS is not patient relabeling. No trial-management capability or revenue assumed. | Separate study/site/subject model, protocol and milestone workflows, permissions, sponsor/CRO buyer research, EDC/eTMF integrations and scope-specific validation/e-signatures. | Research stakeholder validation, data/licensing agreements, intended-use and regulatory assessment, separate synthetic pilot and go/no-go investment case. | Optional | Expansion | Research domain lead / integration / validation | R6.5 | CTMS | W7.2 | CTMS

## Migration WBS
Migration and refactoring WBS
Effort is an assumed person-day range, not a separate engineering charge. STAFF references the staffing pool; no WBS labor added to financial totals. Freeze/write-pause cutover; no unqualified dual-write.
← Start Here
Id | Requirement | Work | Decision | Evidence | Effort Days | Start | End | Owner | Dependency | Scope | Cost | Acceptance | Low assumed days (−30%) | High assumed days (+50%)
W1.1 | R1.1 | Characterize rounding journeys and historical/backfeed semantics with synthetic fixtures | Reuse behavior; verify before extraction | clinical-rounding-adaptive.html; USP.md | 25 | 1 | 3 | Founder / QA | None | Core | STAFF | Golden workflow baseline signed | 17.5 | 37.5
W1.2 | R1.2 | Inventory root/release and Azure/M365 alternatives; choose canonical app and release manifest | Assess now; defer code cleanup until authorized migration | README.md; AGENTS.md; release/; .github/copilot-instructions.md | 8 | 1 | 2 | Tech lead | W1.1 | Core | STAFF | Canonical-source decision record | 5.6 | 12
W1.3 | R1.3 | Buyer discovery, intended-use scope and pilot acceptance criteria | Reuse clinical wedge; defer CTMS and EHR connectors | USP.md; documents/exec-brief/Clinical-Roundup-CTMS-Exec-Brief.md | 20 | 1 | 3 | Founder | W1.1 | Core | STAFF | Scope and pilot go/no-go | 14 | 30
W2.1 | R2.1 | Extract domain/form/render services, establish API adapters, mobile accessibility regression | Refactor incrementally, not a big-bang framework rewrite | clinical-rounding-adaptive.html; import-engine.js | 90 | 4 | 8 | Frontend / tech lead | W1.1 | Core | STAFF | Core synthetic journeys preserved | 63 | 135
W2.2 | R2.2 | API validation, trusted identity integration, server authorization, concurrency and contract tests | Refactor API ideas; replace browser-direct data trust boundary | api/*; api/shared/dataService.js; staticwebapp.config.json | 75 | 4 | 8 | Backend / security | W3.1 | Core | STAFF | Negative tenant tests and contract suite | 52.5 | 112.5
W3.1 | R3.1 | Organization membership, invitations, role matrix and enforceable tenant query context | Replace single-site tenancy assumptions | m365-integration.js; api/patients/index.js | 45 | 3 | 6 | Backend / tech lead | W1.3 | Core | STAFF | Isolation design and two-tenant tests | 31.5 | 67.5
W3.2 | R3.2 | Relational tenant/patient/encounter schema, constraints, migrations/indexes, archive policy | Replace MRN/date global identity; retain source keys as mapped provenance | m365-integration.js: api_savePatient; api/shared/dataService.js | 45 | 4 | 7 | Backend | W3.1 | Core | STAFF | Migration up/down, duplicate MRN tenant tests | 31.5 | 67.5
W3.3 | R3.3 | Cache/session/offline policy, revocation, stale-write UX and safe retry semantics | Refactor; offline PHI may be restricted rather than retained | m365-integration.js: cache, polling, session invalidation | 30 | 5 | 8 | Frontend / security | W3.1 | Core | STAFF | Tenant switch/logout/offline tests | 21 | 45
W4.1 | R4.1 | Extract SharePoint schema and snapshots; typed field mapping and source-to-target key map | Reuse field knowledge; replace direct persistence mapping | m365-integration.js; api/shared/dataService.js | 25 | 6 | 8 | Backend / implementation | W3.2 | Core | STAFF | Versioned mapping with exceptions | 17.5 | 37.5
W4.2 | R4.2 | Import preview/dedup/resume and export parity; document store and scoped download access | Reuse parser semantics; refactor job/storage execution | import-engine.js; m365-integration.js: patient file APIs; clinical-rounding-adaptive.html | 45 | 6 | 9 | Backend / QA | W4.1 | Core | STAFF | Synthetic round-trip including attachments | 31.5 | 67.5
W4.3 | R4.3 | Synthetic rehearsal, count/canonical-hash/field reconciliation, write-pause cutover and rollback drills | New migration tooling; avoid uncontrolled dual-write | m365-integration.js; docs/testing/* | 35 | 9 | 11 | QA / backend / implementation | W4.2 | Core | STAFF | Explained differences and timed rollback | 24.5 | 52.5
W4.4 | R4.4 | Per-tenant source-of-record, PoC read-only coexistence/retirement and customer exit workflow | Defer PoC deletion until retention/rollback sign-off | README.md; release/; .github/workflows/deploy-to-pages.yml | 15 | 12 | 15 | Founder / success | W4.3 | Core | STAFF | Signed tenant handover and exit export | 10.5 | 22.5
W5.1 | R5.1 | Threat model, audit design/retention/access, privacy minimization and legal applicability assessment | Reuse specs as requirements; verify implementation and operation | .kiro/specs/healthcare-compliance/*; api/patients/index.js | 40 | 3 | 10 | Security / validation | W3.1 | Core | STAFF | Evidence matrix; counsel identifies applicable obligations | 28 | 60
W5.2 | R5.2 | Independent pen-test/retest, clinical safety and legal/data-handling customer-pilot approval | External independent assessment; remediation labor already staffed | docs/testing/*; .kiro/specs/healthcare-compliance/* | 25 | 10 | 15 | Founder / security / validation | W5.1 | Core | SECURITY | No unaccepted critical issues; written pilot approval | 17.5 | 37.5
W6.1 | R6.1 | Characterization automation, CI contracts/e2e/tenant tests, review/release evidence gates | Refactor manual tests into automated assurance; placeholder not evidence | api/package.json; docs/testing/*; tools/diagnostics/ | 45 | 1 | 8 | QA / tech lead | W1.1 | Core | STAFF | Failing-regression demo and green staged release | 31.5 | 67.5
W6.2 | R6.2 | Managed environments, IaC, identity/secrets, DB/object/queue, WAF and cost budgets | Choose Azure OR AWS; modular monolith before microservices | staticwebapp.config.json; api/host.json; azure-integration.js | 35 | 4 | 8 | DevOps | W3.2 | Core | STAFF | Reproducible environment and boundary tests | 24.5 | 52.5
W6.3 | R6.3 | Restore/recovery rehearsal, PHI-free observability, incident tabletop and service targets | New operational evidence; vendor SLA is insufficient | api/host.json; .kiro/specs/healthcare-compliance/requirements.md | 25 | 8 | 11 | DevOps / security | W6.2 | Core | STAFF | Measured RPO/RTO and incident drill | 17.5 | 37.5
W6.4 | R6.4 | Tenant provisioning, entitlements/subscriptions, billing admin, onboarding and support playbooks | New SaaS capability; billing codes are not subscription billing | clinical-rounding-adaptive.html; m365-integration.js: settings APIs | 45 | 10 | 15 | Backend / success / founder | W3.1 | Core | STAFF | Provision/invoice/cancel/offboard synthetic cycle | 31.5 | 67.5
W6.5 | R6.5 | Pilot feedback, load/noisy-neighbor tests, query/job tuning and repeatable deploys before growth | Measure before scaling; defer Kubernetes and EHR integrations | import-engine.js; m365-integration.js: startPolling | 60 | 16 | 24 | Tech lead / success / DevOps | W6.3 | Core | STAFF | SLO/cost evidence, repeat onboarding and release | 42 | 90
W7.1 | R7.1 | Optional assistive AI discovery/eval, provider approval, human review UX and monitored synthetic pilot | Defer by default; separately staffed and token-metered | AI_USP.md; documents/AI_AUGMENTATION_OPTIONS.md | 90 | 16 | 24 | AI engineer / clinical / security | W5.2 | AI | AI | Evaluation, privacy, cost and clinical sign-offs | 63 | 135
W7.2 | R7.2 | Optional CTMS discovery, study/site model, research integrations and scope-dependent validation/e-signatures | Defer by default; separate product case, not relabeling rounding | documents/exec-brief/Clinical-Roundup-CTMS-Exec-Brief.md | 180 | 25 | 42 | Research domain / integration / validation | W6.5 | CTMS | CTMS | Research buyer evidence and independent go/no-go | 126 | 270

## Architecture
Architecture candidates ¦ managed modular monolith
Azure East US is a modeled candidate, not mandated. AWS US East managed alternative is mutually exclusive. All HA/retention/SKUs require sizing, eligibility review and quotes; no Kubernetes prerequisite.
← Start Here
Id | Component | Azure | Alternative | Decision | Driver | Sku | Region | Allowance | Ha | Retention | Trigger | Effort Days | Cost
A1 | Frontend / API / worker | Static frontend + Linux App Service modular monolith; queue worker | Static S3/CloudFront frontend + App Runner service/worker | Mutually exclusive candidate stacks; framework chosen by spike, no Kubernetes prerequisite | Environments, instances, measured request concurrency; RequestsM reserve | App Service Linux SKU TBD / App Runner size TBD; quote required | East US baseline; AWS US East alternate TBD | INFRA-APP $400/month or INFRA-AWS pooled $1100; not SKU rates | Proposed prod 2 app instances; smaller dev/stage; quote/review required | No PHI in app logs; signed release artifacts | Sustained p95/CPU/queue saturation against approved SLO | 15 | INFRA
A2 | Managed relational database | PostgreSQL Flexible Server | RDS PostgreSQL Multi-AZ | Tenant IDs, constraints and query authorization; RLS defense-in-depth evaluated | Compute, primary+standby, nonprod, provisioned GB and backup retention | General Purpose candidate; vCPU/storage TBD, not Burstable assumed healthcare-ready | East US / AWS US East TBD | INFRA-DB $600/month or AWS bundle; actual quote unresolved | Proposed production primary + HA standby; nonprod 1 smaller each | Proposed 35-day point-in-time backup; long-term retention per approved policy | DB saturation, storage growth, restore time or tenant isolation tier | 15 | INFRA
A3 | Organization identity and authorization | Entra External ID/federation candidate; server membership enforcement | Cognito/federation candidate; same server enforcement | Do not equate IdP tenant with app organization; verify B2B/MAU terms | MAUs, federation/SSO/MFA and support tier | Plan and MAU allowances TBD, quote required | Tenant/processing residency reviewed | INFRA-EDGE pooled allowance; not unlimited free identity | Managed provider plus recovery/break-glass policy | Invitation/access review/audit per legal policy | Enterprise SSO requirements or MAU tier | 20 | INFRA
A4 | Object storage / exports / customer documents | Blob Storage with tenant-scoped signed access | S3 with tenant-scoped presigned access | No public patient objects; per-request tenant authorization, scanning and lifecycle | StorageGB blended $0.15/GB-month covers backup/egress allowance, not retail rate | Standard hot/cool candidate; operations/egress quote TBD | East US / AWS US East TBD | INFRA-STORE includes selected blended costs; minimum fixed services elsewhere | Replication policy and restore independence TBD | Clinical and export lifecycle per contract; proposed export expiry 7 days | GB, egress and object count growth; retention changes | 10 | INFRA
A5 | Queues / secrets / observability | Storage Queue/Service Bus candidate; Key Vault; Azure Monitor | SQS; Secrets Manager; CloudWatch | Managed jobs, retries/idempotency, least privilege, no PHI in telemetry | LogsGB $5 blended plus RequestsM $30 capacity reserve; actual per-meter quotes needed | Service tiers TBD; included allowance/minimum unverified, not treated as zero price | East US / AWS US East TBD | INFRA-LOG and INFRA-REQ; engineer implementation cost is STAFF | Dead-letter queue, alert owner and credential rotation | Proposed 30-day searchable logs / 90-day security summary; audit separate legal policy | Ingestion cap, queue age, error budget and request volume | 15 | INFRA
A6 | Edge/WAF/DNS/email and environments | Azure Front Door/WAF, DNS, approved email provider | CloudFront/WAF, Route53, SES candidate | Separate dev/stage/prod; staging synthetic only; eligibility and outbound data review | Base minima, requests, egress, emails; quoted bundle allowance | WAF/CDN/transactional email plan TBD | Edge global; origin/data East US candidate | INFRA-EDGE $250/month shared candidate bundle; provider prices unresolved | Proposed redundant edge and deployment rollback | DNS/email audit and delivery logs without PHI | Traffic/abuse, geography, transactional email volume | 10 | INFRA
A7 | Backup / disaster recovery / operations | DB PITR + Blob recovery + separately protected backups | RDS PITR + S3 recovery + separately protected backups | Vendor HA is not DR; timed restore evidence required before customer pilot | Backup GB and retention, restore environments, independent copies | Backup/replication SKU TBD; no cross-region guarantee in allowance | Second region is decision/quote, not silently included | INFRA-DB / INFRA-STORE allowances, revisit at DR gate | Pilot RPO 24h/RTO 8h; growth candidate 1h/4h, not guaranteed | 35-day PITR proposal; legal hold/deletion reconciliation specialist-reviewed | Customer recovery target, material data volume or legal retention change | 10 | INFRA
A8 | Optional AI / CTMS services | Provider-neutral AI adapter; separate research bounded context | Same modular boundary on alternate managed stack | Default off; no competing stack sum, no data sharing until approval | AI InputM/OutputM + evaluation; CTMS integration/validation annual allowance | GPT-4.1-mini candidate unverified; EDC/eTMF partner licenses TBD | Provider residency and endpoints unresolved | AI and CTMS line items plus optional STAFF; no revenue uplift | Non-AI fallback, human approval, independent research gates | Provider/clinical/research policy review; no PHI in prompts by default | Separate investment case, buyer evidence and specialist approvals | 30 | AI / CTMS

## Roadmap
Methodology, roadmap and decision gates
Assume 2-week iterations, small vertical slices, acceptance criteria, PR review + tests, threat model, staged release, feedback. Gates can delay dates; added headcount does not halve timelines.
← Start Here
Id | Phase | Start | End | Dependency | Owner | Acceptance | Confidence | Scope | Risk | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
G1 | Assess: characterize and choose scope | 1 | 3 | None | Founder / tech lead | Product wedge, intended use, canonical inventory and test baseline; reject/stop if no viable pilot need. | Medium; ±1 month | Core | Buyer and inherited behavior uncertainty | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G2 | SaaS foundation | 4 | 8 | G1; W3.1 identity design begins M3 | Tech lead | Tenant model, auth/API, schema/mapping, modular UI and CI; review threat model and infrastructure quote. | Low–medium; −1/+3 months | Core | Identity and schema discoveries; hiring lead time | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G3 | Synthetic-data pilot only | 9 | 11 | G2 | QA / implementation | Synthetic migration reconciliation, restore/rollback, load and negative isolation tests; no customer PHI. | Medium; −1/+2 months | Core | Mapping loss, concurrency and recovery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G4 | Approved customer pilot | 12 | 15 | G3 plus legal/security/clinical approval | Founder / validation | Contracts, service eligibility/BAA where needed, security/clinical sign-off; staged tenant cutover and customer feedback. Stop for safety/control failure. | Low; −1/+4 months | Core | Procurement, remediation, training and clinical risk | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G5 | Repeatable deployment and sales learning | 16 | 24 | G4 | Success / tech lead | Repeat onboarding, release/incident/restore evidence, retention and unit-cost evidence before hiring growth capacity. | Low; ±4 months | Core | Unproven retention, acquisition and operating model | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G6 | Conditional growth / scale | 25 | 60 | G5; capital and demand evidence | Founder / sales / tech lead | Quarterly funding, clinical safety and unit-economics review; hire to measured demand, not valuation; resize from SLOs. | Low; reforecast quarterly | Core | Revenue/hiring forecasts are not commitments | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1
G-AI | Optional AI discovery → evaluated assistive pilot | 16 | 24 | G4; separate privacy/provider gate | AI engineer / clinical | Start follows scenario AI month, nine-month discovery/evaluation window; no assumed revenue uplift or clinical automation. | Low; −2/+6 months | AI | Provider, safety, evaluation data and contractual limitations | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
G-CTMS | Optional CTMS discovery → research synthetic pilot | 25 | 42 | G5 plus new product investment case | Research domain / validation | Start follows scenario CTMS month, 18-month planning window; study/site schema, partner integrations and validation decision. | Low; −3/+12 months | CTMS | Separate buyers, integration rights and regulatory applicability | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0

## Risks and Funding
Risks, decisions and funding gates
Qualified specialists must assess HIPAA/BAA eligibility, clinical safety, intended use and research validation/e-signature rules. SOX is not assumed. No cloud product makes the application compliant.
← Start Here
Id | Risk | Owner | Mitigation | Gate | Cost | Likelihood
K1 | Wrong first buyer or scope; rounding/CTMS conflation | Founder | Paid-pilot problem discovery; separate CTMS investment case; no valuation reverse engineering | G1 and quarterly | STAFF; contingency already included once | High
K2 | Cross-tenant access or identity boundary failure | Security / backend | Trusted auth, per-resource checks, negative isolation tests, independent review and incident drills | G2/G3/G4 | STAFF / SECURITY | High impact; likelihood unmeasured
K3 | Migration data loss or hidden field incompatibility | Implementation / QA | Schema manifest, synthetic rehearsal, count/hash/field reconciliation, write pause, staged cutover and rollback | G3/G4 per tenant | STAFF / ONBOARD | Medium assumption
K4 | Clinical safety or validation evidence insufficient | Clinical / validation | Intended-use scope, synthetic edge cases, clinician acceptance, customer approval and stop rules | G4; every material release | STAFF / COMPLIANCE | High impact; unmeasured
K5 | Incorrect regulatory applicability / contracts / cloud eligibility | Qualified legal / validation specialist | Review HIPAA/BAA/service eligibility and state privacy rules; SOX not assumed; research e-signature/validation scope-specific | Before PHI or optional research/AI | LEGAL / COMPLIANCE | Unresolved
K6 | Hiring timing, blended roles and key-person dependence | Founder / tech lead | Confirm actual availability, contractor agreements and onboarding; capacity-level WBS before commitment; dates do not automatically compress | Each hire / G2 | STAFF / EQUIPMENT; recruiting modeled per incremental FTE | Medium assumption
K7 | Sales procurement/onboarding lead time and churn exceed forecasts | Founder / success / sales | Track cohorts and buying process; zero-revenue cash sensitivity; quarterly reforecast before growth hires | G4/G5/G6 | MARKETING / ONBOARD / STAFF | High
K8 | Unpriced infrastructure/security/legal/insurance services | DevOps / founder | Resolve amber catalog sources; exact SKUs/region/meters/renewal and independent quotes; do not treat allowances as vendor commitments | G2 architecture / before contracts | INFRA / LEGAL / SECURITY / INSURANCE | Known gap
K9 | Vendor dependency, outage, backup failure and unexpected data egress | DevOps | Portable API/schema, export and restore drills, alert caps; choose one stack; review second-region recovery pricing | G3 and quarterly | INFRA / STAFF | Medium assumption
K10 | Optional AI hallucination, privacy exposure, evaluation or provider changes | AI / clinical / security | Default off, synthetic evaluation, human approval, privacy/contract and model-version gates, token budgets and fallback | G-AI | AI / STAFF | Unresolved optional
K11 | CTMS scope, partner rights and research validation underestimate | Research domain / validation | Separate study/site model, EDC/eTMF permissions, stakeholder evidence and scope-specific specialist review | G-CTMS | CTMS / STAFF | High optional
K12 | Funding unavailable despite forecast receipts | Founder | Financing events are uncommitted; fund before first negative month, review stage cash needs and contingency; no valuation promise | Every stage; monthly cash review | Contingency is expense reserve, financing excluded from spend | Unresolved
Funding by core stage (selected scenario; spend includes contingency)
Stage | From | Through | Stage gross spend | Cumulative gross spend | Cumulative net need before cash/financing | Maximum gap to date
Assessment | 1 | 3 | 167832.15 | 167832.15 | 167832.15 | 0
Foundation | 4 | 8 | 419124.7833 | 586956.9333 | 586956.9333 | 0
Synthetic pilot | 9 | 11 | 343367 | 930323.9333 | 930323.9333 | 0
Approved pilot | 12 | 15 | 416116.1347 | 1346440.0681 | 1341075.9781 | 27452.55
Repeatable delivery | 16 | 24 | 1370392.4256 | 2716832.4937 | 2649143.2867 | 27452.55
Growth | 25 | 60 | 8190417.6162 | 10907250.1099 | 9465729.5339 | 5465729.5339

## Staff Months
Staffing monthly calculation detail
Formula audit trail: date-bounded capacity; positive incremental FTE triggers recruiting/equipment. Only employees receive wage-based burden. Fractional headcount slots are ceiling(FTE), not confirmed people.
← Start Here
Scenario | Role ID | Month | Date | FTE | Salary cash | Employer burden cash | Loaded cash | Unpaid founder economic | Recruiting | Equipment | Headcount slots
Lean | FOUNDER | 1 | 2026-11-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 1875 | 1
Lean | FOUNDER | 2 | 2026-12-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 3 | 2027-01-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 4 | 2027-02-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 5 | 2027-03-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 6 | 2027-04-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 7 | 2027-05-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 8 | 2027-06-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 9 | 2027-07-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 10 | 2027-08-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 11 | 2027-09-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 12 | 2027-10-01 | 0.75 | 0 | 0 | 0 | 9375 | 0 | 0 | 1
Lean | FOUNDER | 13 | 2027-11-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 14 | 2027-12-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 15 | 2028-01-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 16 | 2028-02-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 17 | 2028-03-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 18 | 2028-04-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 19 | 2028-05-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 20 | 2028-06-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 21 | 2028-07-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 22 | 2028-08-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 23 | 2028-09-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 24 | 2028-10-01 | 0.75 | 0 | 0 | 0 | 9656.25 | 0 | 0 | 1
Lean | FOUNDER | 25 | 2028-11-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 26 | 2028-12-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 27 | 2029-01-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 28 | 2029-02-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 29 | 2029-03-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 30 | 2029-04-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 31 | 2029-05-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 32 | 2029-06-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 33 | 2029-07-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 34 | 2029-08-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 35 | 2029-09-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 36 | 2029-10-01 | 0.75 | 0 | 0 | 0 | 9945.9375 | 0 | 0 | 1
Lean | FOUNDER | 37 | 2029-11-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 38 | 2029-12-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 39 | 2030-01-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 40 | 2030-02-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 41 | 2030-03-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 42 | 2030-04-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 43 | 2030-05-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 44 | 2030-06-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 45 | 2030-07-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 46 | 2030-08-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 47 | 2030-09-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 48 | 2030-10-01 | 0.75 | 0 | 0 | 0 | 10244.3156 | 0 | 0 | 1
Lean | FOUNDER | 49 | 2030-11-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 50 | 2030-12-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 51 | 2031-01-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 52 | 2031-02-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 53 | 2031-03-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 54 | 2031-04-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 55 | 2031-05-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 56 | 2031-06-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 57 | 2031-07-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 58 | 2031-08-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 59 | 2031-09-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | FOUNDER | 60 | 2031-10-01 | 0.75 | 0 | 0 | 0 | 10551.6451 | 0 | 0 | 1
Lean | LEAD | 1 | 2026-11-01 | 1 | 13750 | 5500 | 19250 | 0 | 5000 | 2500 | 1
Lean | LEAD | 2 | 2026-12-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 3 | 2027-01-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 4 | 2027-02-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 5 | 2027-03-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 6 | 2027-04-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 7 | 2027-05-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 8 | 2027-06-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 9 | 2027-07-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 10 | 2027-08-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 11 | 2027-09-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 12 | 2027-10-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Lean | LEAD | 13 | 2027-11-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 14 | 2027-12-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 15 | 2028-01-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 16 | 2028-02-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 17 | 2028-03-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 18 | 2028-04-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 19 | 2028-05-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 20 | 2028-06-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 21 | 2028-07-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 22 | 2028-08-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 23 | 2028-09-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 24 | 2028-10-01 | 1 | 14162.5 | 5665 | 19827.5 | 0 | 0 | 0 | 1
Lean | LEAD | 25 | 2028-11-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 26 | 2028-12-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 27 | 2029-01-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 28 | 2029-02-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 29 | 2029-03-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 30 | 2029-04-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 31 | 2029-05-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 32 | 2029-06-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 33 | 2029-07-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 34 | 2029-08-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 35 | 2029-09-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 36 | 2029-10-01 | 1 | 14587.375 | 5834.95 | 20422.325 | 0 | 0 | 0 | 1
Lean | LEAD | 37 | 2029-11-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 38 | 2029-12-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 39 | 2030-01-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 40 | 2030-02-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 41 | 2030-03-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 42 | 2030-04-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 43 | 2030-05-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 44 | 2030-06-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 45 | 2030-07-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 46 | 2030-08-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 47 | 2030-09-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 48 | 2030-10-01 | 1 | 15024.9963 | 6009.9985 | 21034.9948 | 0 | 0 | 0 | 1
Lean | LEAD | 49 | 2030-11-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 50 | 2030-12-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 51 | 2031-01-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 52 | 2031-02-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 53 | 2031-03-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 54 | 2031-04-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 55 | 2031-05-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 56 | 2031-06-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 57 | 2031-07-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 58 | 2031-08-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 59 | 2031-09-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | LEAD | 60 | 2031-10-01 | 1 | 15475.7461 | 6190.2985 | 21666.0446 | 0 | 0 | 0 | 1
Lean | BACKEND | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | BACKEND | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | BACKEND | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | BACKEND | 4 | 2027-02-01 | 0.5 | 6041.6667 | 2416.6667 | 8458.3333 | 0 | 2500 | 1250 | 1
Lean | BACKEND | 5 | 2027-03-01 | 0.5 | 6041.6667 | 2416.6667 | 8458.3333 | 0 | 0 | 0 | 1
Lean | BACKEND | 6 | 2027-04-01 | 0.5 | 6041.6667 | 2416.6667 | 8458.3333 | 0 | 0 | 0 | 1
Lean | BACKEND | 7 | 2027-05-01 | 0.75 | 9062.5 | 3625 | 12687.5 | 0 | 1250 | 625 | 1
Lean | BACKEND | 8 | 2027-06-01 | 0.75 | 9062.5 | 3625 | 12687.5 | 0 | 0 | 0 | 1
Lean | BACKEND | 9 | 2027-07-01 | 0.75 | 9062.5 | 3625 | 12687.5 | 0 | 0 | 0 | 1
Lean | BACKEND | 10 | 2027-08-01 | 0.75 | 9062.5 | 3625 | 12687.5 | 0 | 0 | 0 | 1
Lean | BACKEND | 11 | 2027-09-01 | 0.75 | 9062.5 | 3625 | 12687.5 | 0 | 0 | 0 | 1
Lean | BACKEND | 12 | 2027-10-01 | 0.75 | 9062.5 | 3625 | 12687.5 | 0 | 0 | 0 | 1
Lean | BACKEND | 13 | 2027-11-01 | 0.75 | 9334.375 | 3733.75 | 13068.125 | 0 | 0 | 0 | 1
Lean | BACKEND | 14 | 2027-12-01 | 0.75 | 9334.375 | 3733.75 | 13068.125 | 0 | 0 | 0 | 1
Lean | BACKEND | 15 | 2028-01-01 | 0.75 | 9334.375 | 3733.75 | 13068.125 | 0 | 0 | 0 | 1
Lean | BACKEND | 16 | 2028-02-01 | 1 | 12445.8333 | 4978.3333 | 17424.1667 | 0 | 1250 | 625 | 1
Lean | BACKEND | 17 | 2028-03-01 | 1 | 12445.8333 | 4978.3333 | 17424.1667 | 0 | 0 | 0 | 1
Lean | BACKEND | 18 | 2028-04-01 | 1 | 12445.8333 | 4978.3333 | 17424.1667 | 0 | 0 | 0 | 1
Lean | BACKEND | 19 | 2028-05-01 | 1 | 12445.8333 | 4978.3333 | 17424.1667 | 0 | 0 | 0 | 1
Lean | BACKEND | 20 | 2028-06-01 | 1 | 12445.8333 | 4978.3333 | 17424.1667 | 0 | 0 | 0 | 1
Lean | BACKEND | 21 | 2028-07-01 | 1 | 12445.8333 | 4978.3333 | 17424.1667 | 0 | 0 | 0 | 1
Lean | BACKEND | 22 | 2028-08-01 | 1 | 12445.8333 | 4978.3333 | 17424.1667 | 0 | 0 | 0 | 1
Lean | BACKEND | 23 | 2028-09-01 | 1 | 12445.8333 | 4978.3333 | 17424.1667 | 0 | 0 | 0 | 1
Lean | BACKEND | 24 | 2028-10-01 | 1 | 12445.8333 | 4978.3333 | 17424.1667 | 0 | 0 | 0 | 1
Lean | BACKEND | 25 | 2028-11-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 26 | 2028-12-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 27 | 2029-01-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 28 | 2029-02-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 29 | 2029-03-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 30 | 2029-04-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 31 | 2029-05-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 32 | 2029-06-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 33 | 2029-07-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 34 | 2029-08-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 35 | 2029-09-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 36 | 2029-10-01 | 1 | 12819.2083 | 5127.6833 | 17946.8917 | 0 | 0 | 0 | 1
Lean | BACKEND | 37 | 2029-11-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 38 | 2029-12-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 39 | 2030-01-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 40 | 2030-02-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 41 | 2030-03-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 42 | 2030-04-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 43 | 2030-05-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 44 | 2030-06-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 45 | 2030-07-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 46 | 2030-08-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 47 | 2030-09-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 48 | 2030-10-01 | 1 | 13203.7846 | 5281.5138 | 18485.2984 | 0 | 0 | 0 | 1
Lean | BACKEND | 49 | 2030-11-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 50 | 2030-12-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 51 | 2031-01-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 52 | 2031-02-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 53 | 2031-03-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 54 | 2031-04-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 55 | 2031-05-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 56 | 2031-06-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 57 | 2031-07-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 58 | 2031-08-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 59 | 2031-09-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | BACKEND | 60 | 2031-10-01 | 1 | 13599.8981 | 5439.9592 | 19039.8574 | 0 | 0 | 0 | 1
Lean | FRONTEND | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | FRONTEND | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | FRONTEND | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | FRONTEND | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | FRONTEND | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | FRONTEND | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | FRONTEND | 7 | 2027-05-01 | 0.5 | 5833.3333 | 2333.3333 | 8166.6667 | 0 | 2500 | 1250 | 1
Lean | FRONTEND | 8 | 2027-06-01 | 0.5 | 5833.3333 | 2333.3333 | 8166.6667 | 0 | 0 | 0 | 1
Lean | FRONTEND | 9 | 2027-07-01 | 0.5 | 5833.3333 | 2333.3333 | 8166.6667 | 0 | 0 | 0 | 1
Lean | FRONTEND | 10 | 2027-08-01 | 0.5 | 5833.3333 | 2333.3333 | 8166.6667 | 0 | 0 | 0 | 1
Lean | FRONTEND | 11 | 2027-09-01 | 0.5 | 5833.3333 | 2333.3333 | 8166.6667 | 0 | 0 | 0 | 1
Lean | FRONTEND | 12 | 2027-10-01 | 0.5 | 5833.3333 | 2333.3333 | 8166.6667 | 0 | 0 | 0 | 1
Lean | FRONTEND | 13 | 2027-11-01 | 0.5 | 6008.3333 | 2403.3333 | 8411.6667 | 0 | 0 | 0 | 1
Lean | FRONTEND | 14 | 2027-12-01 | 0.5 | 6008.3333 | 2403.3333 | 8411.6667 | 0 | 0 | 0 | 1
Lean | FRONTEND | 15 | 2028-01-01 | 0.5 | 6008.3333 | 2403.3333 | 8411.6667 | 0 | 0 | 0 | 1
Lean | FRONTEND | 16 | 2028-02-01 | 0.75 | 9012.5 | 3605 | 12617.5 | 0 | 1250 | 625 | 1
Lean | FRONTEND | 17 | 2028-03-01 | 0.75 | 9012.5 | 3605 | 12617.5 | 0 | 0 | 0 | 1
Lean | FRONTEND | 18 | 2028-04-01 | 0.75 | 9012.5 | 3605 | 12617.5 | 0 | 0 | 0 | 1
Lean | FRONTEND | 19 | 2028-05-01 | 0.75 | 9012.5 | 3605 | 12617.5 | 0 | 0 | 0 | 1
Lean | FRONTEND | 20 | 2028-06-01 | 0.75 | 9012.5 | 3605 | 12617.5 | 0 | 0 | 0 | 1
Lean | FRONTEND | 21 | 2028-07-01 | 0.75 | 9012.5 | 3605 | 12617.5 | 0 | 0 | 0 | 1
Lean | FRONTEND | 22 | 2028-08-01 | 0.75 | 9012.5 | 3605 | 12617.5 | 0 | 0 | 0 | 1
Lean | FRONTEND | 23 | 2028-09-01 | 0.75 | 9012.5 | 3605 | 12617.5 | 0 | 0 | 0 | 1
Lean | FRONTEND | 24 | 2028-10-01 | 0.75 | 9012.5 | 3605 | 12617.5 | 0 | 0 | 0 | 1
Lean | FRONTEND | 25 | 2028-11-01 | 0.75 | 9282.875 | 3713.15 | 12996.025 | 0 | 0 | 0 | 1
Lean | FRONTEND | 26 | 2028-12-01 | 0.75 | 9282.875 | 3713.15 | 12996.025 | 0 | 0 | 0 | 1
Lean | FRONTEND | 27 | 2029-01-01 | 0.75 | 9282.875 | 3713.15 | 12996.025 | 0 | 0 | 0 | 1
Lean | FRONTEND | 28 | 2029-02-01 | 0.75 | 9282.875 | 3713.15 | 12996.025 | 0 | 0 | 0 | 1
Lean | FRONTEND | 29 | 2029-03-01 | 0.75 | 9282.875 | 3713.15 | 12996.025 | 0 | 0 | 0 | 1
Lean | FRONTEND | 30 | 2029-04-01 | 0.75 | 9282.875 | 3713.15 | 12996.025 | 0 | 0 | 0 | 1
Lean | FRONTEND | 31 | 2029-05-01 | 1 | 12377.1667 | 4950.8667 | 17328.0333 | 0 | 1250 | 625 | 1
Lean | FRONTEND | 32 | 2029-06-01 | 1 | 12377.1667 | 4950.8667 | 17328.0333 | 0 | 0 | 0 | 1
Lean | FRONTEND | 33 | 2029-07-01 | 1 | 12377.1667 | 4950.8667 | 17328.0333 | 0 | 0 | 0 | 1
Lean | FRONTEND | 34 | 2029-08-01 | 1 | 12377.1667 | 4950.8667 | 17328.0333 | 0 | 0 | 0 | 1
Lean | FRONTEND | 35 | 2029-09-01 | 1 | 12377.1667 | 4950.8667 | 17328.0333 | 0 | 0 | 0 | 1
Lean | FRONTEND | 36 | 2029-10-01 | 1 | 12377.1667 | 4950.8667 | 17328.0333 | 0 | 0 | 0 | 1
Lean | FRONTEND | 37 | 2029-11-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 38 | 2029-12-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 39 | 2030-01-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 40 | 2030-02-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 41 | 2030-03-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 42 | 2030-04-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 43 | 2030-05-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 44 | 2030-06-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 45 | 2030-07-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 46 | 2030-08-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 47 | 2030-09-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 48 | 2030-10-01 | 1 | 12748.4817 | 5099.3927 | 17847.8743 | 0 | 0 | 0 | 1
Lean | FRONTEND | 49 | 2030-11-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 50 | 2030-12-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 51 | 2031-01-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 52 | 2031-02-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 53 | 2031-03-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 54 | 2031-04-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 55 | 2031-05-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 56 | 2031-06-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 57 | 2031-07-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 58 | 2031-08-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 59 | 2031-09-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | FRONTEND | 60 | 2031-10-01 | 1 | 13130.9361 | 5252.3744 | 18383.3106 | 0 | 0 | 0 | 1
Lean | QA | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | QA | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | QA | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | QA | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | QA | 5 | 2027-03-01 | 0.25 | 2291.6667 | 916.6667 | 3208.3333 | 0 | 1250 | 625 | 1
Lean | QA | 6 | 2027-04-01 | 0.25 | 2291.6667 | 916.6667 | 3208.3333 | 0 | 0 | 0 | 1
Lean | QA | 7 | 2027-05-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 1250 | 625 | 1
Lean | QA | 8 | 2027-06-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Lean | QA | 9 | 2027-07-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Lean | QA | 10 | 2027-08-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Lean | QA | 11 | 2027-09-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Lean | QA | 12 | 2027-10-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Lean | QA | 13 | 2027-11-01 | 0.5 | 4720.8333 | 1888.3333 | 6609.1667 | 0 | 0 | 0 | 1
Lean | QA | 14 | 2027-12-01 | 0.5 | 4720.8333 | 1888.3333 | 6609.1667 | 0 | 0 | 0 | 1
Lean | QA | 15 | 2028-01-01 | 0.5 | 4720.8333 | 1888.3333 | 6609.1667 | 0 | 0 | 0 | 1
Lean | QA | 16 | 2028-02-01 | 0.75 | 7081.25 | 2832.5 | 9913.75 | 0 | 1250 | 625 | 1
Lean | QA | 17 | 2028-03-01 | 0.75 | 7081.25 | 2832.5 | 9913.75 | 0 | 0 | 0 | 1
Lean | QA | 18 | 2028-04-01 | 0.75 | 7081.25 | 2832.5 | 9913.75 | 0 | 0 | 0 | 1
Lean | QA | 19 | 2028-05-01 | 0.75 | 7081.25 | 2832.5 | 9913.75 | 0 | 0 | 0 | 1
Lean | QA | 20 | 2028-06-01 | 0.75 | 7081.25 | 2832.5 | 9913.75 | 0 | 0 | 0 | 1
Lean | QA | 21 | 2028-07-01 | 0.75 | 7081.25 | 2832.5 | 9913.75 | 0 | 0 | 0 | 1
Lean | QA | 22 | 2028-08-01 | 0.75 | 7081.25 | 2832.5 | 9913.75 | 0 | 0 | 0 | 1
Lean | QA | 23 | 2028-09-01 | 0.75 | 7081.25 | 2832.5 | 9913.75 | 0 | 0 | 0 | 1
Lean | QA | 24 | 2028-10-01 | 0.75 | 7081.25 | 2832.5 | 9913.75 | 0 | 0 | 0 | 1
Lean | QA | 25 | 2028-11-01 | 0.75 | 7293.6875 | 2917.475 | 10211.1625 | 0 | 0 | 0 | 1
Lean | QA | 26 | 2028-12-01 | 0.75 | 7293.6875 | 2917.475 | 10211.1625 | 0 | 0 | 0 | 1
Lean | QA | 27 | 2029-01-01 | 0.75 | 7293.6875 | 2917.475 | 10211.1625 | 0 | 0 | 0 | 1
Lean | QA | 28 | 2029-02-01 | 0.75 | 7293.6875 | 2917.475 | 10211.1625 | 0 | 0 | 0 | 1
Lean | QA | 29 | 2029-03-01 | 0.75 | 7293.6875 | 2917.475 | 10211.1625 | 0 | 0 | 0 | 1
Lean | QA | 30 | 2029-04-01 | 0.75 | 7293.6875 | 2917.475 | 10211.1625 | 0 | 0 | 0 | 1
Lean | QA | 31 | 2029-05-01 | 1 | 9724.9167 | 3889.9667 | 13614.8833 | 0 | 1250 | 625 | 1
Lean | QA | 32 | 2029-06-01 | 1 | 9724.9167 | 3889.9667 | 13614.8833 | 0 | 0 | 0 | 1
Lean | QA | 33 | 2029-07-01 | 1 | 9724.9167 | 3889.9667 | 13614.8833 | 0 | 0 | 0 | 1
Lean | QA | 34 | 2029-08-01 | 1 | 9724.9167 | 3889.9667 | 13614.8833 | 0 | 0 | 0 | 1
Lean | QA | 35 | 2029-09-01 | 1 | 9724.9167 | 3889.9667 | 13614.8833 | 0 | 0 | 0 | 1
Lean | QA | 36 | 2029-10-01 | 1 | 9724.9167 | 3889.9667 | 13614.8833 | 0 | 0 | 0 | 1
Lean | QA | 37 | 2029-11-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 38 | 2029-12-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 39 | 2030-01-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 40 | 2030-02-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 41 | 2030-03-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 42 | 2030-04-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 43 | 2030-05-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 44 | 2030-06-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 45 | 2030-07-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 46 | 2030-08-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 47 | 2030-09-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 48 | 2030-10-01 | 1 | 10016.6642 | 4006.6657 | 14023.3298 | 0 | 0 | 0 | 1
Lean | QA | 49 | 2030-11-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 50 | 2030-12-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 51 | 2031-01-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 52 | 2031-02-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 53 | 2031-03-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 54 | 2031-04-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 55 | 2031-05-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 56 | 2031-06-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 57 | 2031-07-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 58 | 2031-08-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 59 | 2031-09-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | QA | 60 | 2031-10-01 | 1 | 10317.1641 | 4126.8656 | 14444.0297 | 0 | 0 | 0 | 1
Lean | OPS | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | OPS | 2 | 2026-12-01 | 0.15 | 2375 | 0 | 2375 | 0 | 0 | 375 | 1
Lean | OPS | 3 | 2027-01-01 | 0.15 | 2375 | 0 | 2375 | 0 | 0 | 0 | 1
Lean | OPS | 4 | 2027-02-01 | 0.15 | 2375 | 0 | 2375 | 0 | 0 | 0 | 1
Lean | OPS | 5 | 2027-03-01 | 0.15 | 2375 | 0 | 2375 | 0 | 0 | 0 | 1
Lean | OPS | 6 | 2027-04-01 | 0.15 | 2375 | 0 | 2375 | 0 | 0 | 0 | 1
Lean | OPS | 7 | 2027-05-01 | 0.2 | 3166.6667 | 0 | 3166.6667 | 0 | 0 | 125 | 1
Lean | OPS | 8 | 2027-06-01 | 0.2 | 3166.6667 | 0 | 3166.6667 | 0 | 0 | 0 | 1
Lean | OPS | 9 | 2027-07-01 | 0.2 | 3166.6667 | 0 | 3166.6667 | 0 | 0 | 0 | 1
Lean | OPS | 10 | 2027-08-01 | 0.2 | 3166.6667 | 0 | 3166.6667 | 0 | 0 | 0 | 1
Lean | OPS | 11 | 2027-09-01 | 0.2 | 3166.6667 | 0 | 3166.6667 | 0 | 0 | 0 | 1
Lean | OPS | 12 | 2027-10-01 | 0.2 | 3166.6667 | 0 | 3166.6667 | 0 | 0 | 0 | 1
Lean | OPS | 13 | 2027-11-01 | 0.2 | 3261.6667 | 0 | 3261.6667 | 0 | 0 | 0 | 1
Lean | OPS | 14 | 2027-12-01 | 0.2 | 3261.6667 | 0 | 3261.6667 | 0 | 0 | 0 | 1
Lean | OPS | 15 | 2028-01-01 | 0.2 | 3261.6667 | 0 | 3261.6667 | 0 | 0 | 0 | 1
Lean | OPS | 16 | 2028-02-01 | 0.25 | 4077.0833 | 0 | 4077.0833 | 0 | 0 | 125 | 1
Lean | OPS | 17 | 2028-03-01 | 0.25 | 4077.0833 | 0 | 4077.0833 | 0 | 0 | 0 | 1
Lean | OPS | 18 | 2028-04-01 | 0.25 | 4077.0833 | 0 | 4077.0833 | 0 | 0 | 0 | 1
Lean | OPS | 19 | 2028-05-01 | 0.25 | 4077.0833 | 0 | 4077.0833 | 0 | 0 | 0 | 1
Lean | OPS | 20 | 2028-06-01 | 0.25 | 4077.0833 | 0 | 4077.0833 | 0 | 0 | 0 | 1
Lean | OPS | 21 | 2028-07-01 | 0.25 | 4077.0833 | 0 | 4077.0833 | 0 | 0 | 0 | 1
Lean | OPS | 22 | 2028-08-01 | 0.25 | 4077.0833 | 0 | 4077.0833 | 0 | 0 | 0 | 1
Lean | OPS | 23 | 2028-09-01 | 0.25 | 4077.0833 | 0 | 4077.0833 | 0 | 0 | 0 | 1
Lean | OPS | 24 | 2028-10-01 | 0.25 | 4077.0833 | 0 | 4077.0833 | 0 | 0 | 0 | 1
Lean | OPS | 25 | 2028-11-01 | 0.25 | 4199.3958 | 0 | 4199.3958 | 0 | 0 | 0 | 1
Lean | OPS | 26 | 2028-12-01 | 0.25 | 4199.3958 | 0 | 4199.3958 | 0 | 0 | 0 | 1
Lean | OPS | 27 | 2029-01-01 | 0.25 | 4199.3958 | 0 | 4199.3958 | 0 | 0 | 0 | 1
Lean | OPS | 28 | 2029-02-01 | 0.25 | 4199.3958 | 0 | 4199.3958 | 0 | 0 | 0 | 1
Lean | OPS | 29 | 2029-03-01 | 0.25 | 4199.3958 | 0 | 4199.3958 | 0 | 0 | 0 | 1
Lean | OPS | 30 | 2029-04-01 | 0.25 | 4199.3958 | 0 | 4199.3958 | 0 | 0 | 0 | 1
Lean | OPS | 31 | 2029-05-01 | 0.5 | 8398.7917 | 0 | 8398.7917 | 0 | 0 | 625 | 1
Lean | OPS | 32 | 2029-06-01 | 0.5 | 8398.7917 | 0 | 8398.7917 | 0 | 0 | 0 | 1
Lean | OPS | 33 | 2029-07-01 | 0.5 | 8398.7917 | 0 | 8398.7917 | 0 | 0 | 0 | 1
Lean | OPS | 34 | 2029-08-01 | 0.5 | 8398.7917 | 0 | 8398.7917 | 0 | 0 | 0 | 1
Lean | OPS | 35 | 2029-09-01 | 0.5 | 8398.7917 | 0 | 8398.7917 | 0 | 0 | 0 | 1
Lean | OPS | 36 | 2029-10-01 | 0.5 | 8398.7917 | 0 | 8398.7917 | 0 | 0 | 0 | 1
Lean | OPS | 37 | 2029-11-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 38 | 2029-12-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 39 | 2030-01-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 40 | 2030-02-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 41 | 2030-03-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 42 | 2030-04-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 43 | 2030-05-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 44 | 2030-06-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 45 | 2030-07-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 46 | 2030-08-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 47 | 2030-09-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 48 | 2030-10-01 | 0.5 | 8650.7554 | 0 | 8650.7554 | 0 | 0 | 0 | 1
Lean | OPS | 49 | 2030-11-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 50 | 2030-12-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 51 | 2031-01-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 52 | 2031-02-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 53 | 2031-03-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 54 | 2031-04-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 55 | 2031-05-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 56 | 2031-06-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 57 | 2031-07-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 58 | 2031-08-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 59 | 2031-09-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | OPS | 60 | 2031-10-01 | 0.5 | 8910.2781 | 0 | 8910.2781 | 0 | 0 | 0 | 1
Lean | DESIGN | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 2 | 2026-12-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 375 | 1
Lean | DESIGN | 3 | 2027-01-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 4 | 2027-02-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 5 | 2027-03-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 6 | 2027-04-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 7 | 2027-05-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 8 | 2027-06-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 9 | 2027-07-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 10 | 2027-08-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 11 | 2027-09-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 12 | 2027-10-01 | 0.15 | 1625 | 0 | 1625 | 0 | 0 | 0 | 1
Lean | DESIGN | 13 | 2027-11-01 | 0.15 | 1673.75 | 0 | 1673.75 | 0 | 0 | 0 | 1
Lean | DESIGN | 14 | 2027-12-01 | 0.15 | 1673.75 | 0 | 1673.75 | 0 | 0 | 0 | 1
Lean | DESIGN | 15 | 2028-01-01 | 0.15 | 1673.75 | 0 | 1673.75 | 0 | 0 | 0 | 1
Lean | DESIGN | 16 | 2028-02-01 | 0.1 | 1115.8333 | 0 | 1115.8333 | 0 | 0 | 0 | 1
Lean | DESIGN | 17 | 2028-03-01 | 0.1 | 1115.8333 | 0 | 1115.8333 | 0 | 0 | 0 | 1
Lean | DESIGN | 18 | 2028-04-01 | 0.1 | 1115.8333 | 0 | 1115.8333 | 0 | 0 | 0 | 1
Lean | DESIGN | 19 | 2028-05-01 | 0.1 | 1115.8333 | 0 | 1115.8333 | 0 | 0 | 0 | 1
Lean | DESIGN | 20 | 2028-06-01 | 0.1 | 1115.8333 | 0 | 1115.8333 | 0 | 0 | 0 | 1
Lean | DESIGN | 21 | 2028-07-01 | 0.1 | 1115.8333 | 0 | 1115.8333 | 0 | 0 | 0 | 1
Lean | DESIGN | 22 | 2028-08-01 | 0.1 | 1115.8333 | 0 | 1115.8333 | 0 | 0 | 0 | 1
Lean | DESIGN | 23 | 2028-09-01 | 0.1 | 1115.8333 | 0 | 1115.8333 | 0 | 0 | 0 | 1
Lean | DESIGN | 24 | 2028-10-01 | 0.1 | 1115.8333 | 0 | 1115.8333 | 0 | 0 | 0 | 1
Lean | DESIGN | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | DESIGN | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | VALIDATION | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | VALIDATION | 2 | 2026-12-01 | 0.1 | 1666.6667 | 0 | 1666.6667 | 0 | 0 | 250 | 1
Lean | VALIDATION | 3 | 2027-01-01 | 0.1 | 1666.6667 | 0 | 1666.6667 | 0 | 0 | 0 | 1
Lean | VALIDATION | 4 | 2027-02-01 | 0.1 | 1666.6667 | 0 | 1666.6667 | 0 | 0 | 0 | 1
Lean | VALIDATION | 5 | 2027-03-01 | 0.1 | 1666.6667 | 0 | 1666.6667 | 0 | 0 | 0 | 1
Lean | VALIDATION | 6 | 2027-04-01 | 0.1 | 1666.6667 | 0 | 1666.6667 | 0 | 0 | 0 | 1
Lean | VALIDATION | 7 | 2027-05-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 125 | 1
Lean | VALIDATION | 8 | 2027-06-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 0 | 1
Lean | VALIDATION | 9 | 2027-07-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 0 | 1
Lean | VALIDATION | 10 | 2027-08-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 0 | 1
Lean | VALIDATION | 11 | 2027-09-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 0 | 1
Lean | VALIDATION | 12 | 2027-10-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 0 | 1
Lean | VALIDATION | 13 | 2027-11-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 14 | 2027-12-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 15 | 2028-01-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 16 | 2028-02-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 17 | 2028-03-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 18 | 2028-04-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 19 | 2028-05-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 20 | 2028-06-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 21 | 2028-07-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 22 | 2028-08-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 23 | 2028-09-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 24 | 2028-10-01 | 0.15 | 2575 | 0 | 2575 | 0 | 0 | 0 | 1
Lean | VALIDATION | 25 | 2028-11-01 | 0.15 | 2652.25 | 0 | 2652.25 | 0 | 0 | 0 | 1
Lean | VALIDATION | 26 | 2028-12-01 | 0.15 | 2652.25 | 0 | 2652.25 | 0 | 0 | 0 | 1
Lean | VALIDATION | 27 | 2029-01-01 | 0.15 | 2652.25 | 0 | 2652.25 | 0 | 0 | 0 | 1
Lean | VALIDATION | 28 | 2029-02-01 | 0.15 | 2652.25 | 0 | 2652.25 | 0 | 0 | 0 | 1
Lean | VALIDATION | 29 | 2029-03-01 | 0.15 | 2652.25 | 0 | 2652.25 | 0 | 0 | 0 | 1
Lean | VALIDATION | 30 | 2029-04-01 | 0.15 | 2652.25 | 0 | 2652.25 | 0 | 0 | 0 | 1
Lean | VALIDATION | 31 | 2029-05-01 | 0.2 | 3536.3333 | 0 | 3536.3333 | 0 | 0 | 125 | 1
Lean | VALIDATION | 32 | 2029-06-01 | 0.2 | 3536.3333 | 0 | 3536.3333 | 0 | 0 | 0 | 1
Lean | VALIDATION | 33 | 2029-07-01 | 0.2 | 3536.3333 | 0 | 3536.3333 | 0 | 0 | 0 | 1
Lean | VALIDATION | 34 | 2029-08-01 | 0.2 | 3536.3333 | 0 | 3536.3333 | 0 | 0 | 0 | 1
Lean | VALIDATION | 35 | 2029-09-01 | 0.2 | 3536.3333 | 0 | 3536.3333 | 0 | 0 | 0 | 1
Lean | VALIDATION | 36 | 2029-10-01 | 0.2 | 3536.3333 | 0 | 3536.3333 | 0 | 0 | 0 | 1
Lean | VALIDATION | 37 | 2029-11-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 38 | 2029-12-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 39 | 2030-01-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 40 | 2030-02-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 41 | 2030-03-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 42 | 2030-04-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 43 | 2030-05-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 44 | 2030-06-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 45 | 2030-07-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 46 | 2030-08-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 47 | 2030-09-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 48 | 2030-10-01 | 0.2 | 3642.4233 | 0 | 3642.4233 | 0 | 0 | 0 | 1
Lean | VALIDATION | 49 | 2030-11-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 50 | 2030-12-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 51 | 2031-01-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 52 | 2031-02-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 53 | 2031-03-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 54 | 2031-04-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 55 | 2031-05-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 56 | 2031-06-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 57 | 2031-07-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 58 | 2031-08-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 59 | 2031-09-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | VALIDATION | 60 | 2031-10-01 | 0.2 | 3751.696 | 0 | 3751.696 | 0 | 0 | 0 | 1
Lean | SUCCESS | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SUCCESS | 12 | 2027-10-01 | 0.25 | 1875 | 750 | 2625 | 0 | 1250 | 625 | 1
Lean | SUCCESS | 13 | 2027-11-01 | 0.25 | 1931.25 | 772.5 | 2703.75 | 0 | 0 | 0 | 1
Lean | SUCCESS | 14 | 2027-12-01 | 0.25 | 1931.25 | 772.5 | 2703.75 | 0 | 0 | 0 | 1
Lean | SUCCESS | 15 | 2028-01-01 | 0.25 | 1931.25 | 772.5 | 2703.75 | 0 | 0 | 0 | 1
Lean | SUCCESS | 16 | 2028-02-01 | 0.5 | 3862.5 | 1545 | 5407.5 | 0 | 1250 | 625 | 1
Lean | SUCCESS | 17 | 2028-03-01 | 0.5 | 3862.5 | 1545 | 5407.5 | 0 | 0 | 0 | 1
Lean | SUCCESS | 18 | 2028-04-01 | 0.5 | 3862.5 | 1545 | 5407.5 | 0 | 0 | 0 | 1
Lean | SUCCESS | 19 | 2028-05-01 | 0.5 | 3862.5 | 1545 | 5407.5 | 0 | 0 | 0 | 1
Lean | SUCCESS | 20 | 2028-06-01 | 0.5 | 3862.5 | 1545 | 5407.5 | 0 | 0 | 0 | 1
Lean | SUCCESS | 21 | 2028-07-01 | 0.5 | 3862.5 | 1545 | 5407.5 | 0 | 0 | 0 | 1
Lean | SUCCESS | 22 | 2028-08-01 | 0.5 | 3862.5 | 1545 | 5407.5 | 0 | 0 | 0 | 1
Lean | SUCCESS | 23 | 2028-09-01 | 0.5 | 3862.5 | 1545 | 5407.5 | 0 | 0 | 0 | 1
Lean | SUCCESS | 24 | 2028-10-01 | 0.5 | 3862.5 | 1545 | 5407.5 | 0 | 0 | 0 | 1
Lean | SUCCESS | 25 | 2028-11-01 | 0.5 | 3978.375 | 1591.35 | 5569.725 | 0 | 0 | 0 | 1
Lean | SUCCESS | 26 | 2028-12-01 | 0.5 | 3978.375 | 1591.35 | 5569.725 | 0 | 0 | 0 | 1
Lean | SUCCESS | 27 | 2029-01-01 | 0.5 | 3978.375 | 1591.35 | 5569.725 | 0 | 0 | 0 | 1
Lean | SUCCESS | 28 | 2029-02-01 | 0.5 | 3978.375 | 1591.35 | 5569.725 | 0 | 0 | 0 | 1
Lean | SUCCESS | 29 | 2029-03-01 | 0.5 | 3978.375 | 1591.35 | 5569.725 | 0 | 0 | 0 | 1
Lean | SUCCESS | 30 | 2029-04-01 | 0.5 | 3978.375 | 1591.35 | 5569.725 | 0 | 0 | 0 | 1
Lean | SUCCESS | 31 | 2029-05-01 | 1 | 7956.75 | 3182.7 | 11139.45 | 0 | 2500 | 1250 | 1
Lean | SUCCESS | 32 | 2029-06-01 | 1 | 7956.75 | 3182.7 | 11139.45 | 0 | 0 | 0 | 1
Lean | SUCCESS | 33 | 2029-07-01 | 1 | 7956.75 | 3182.7 | 11139.45 | 0 | 0 | 0 | 1
Lean | SUCCESS | 34 | 2029-08-01 | 1 | 7956.75 | 3182.7 | 11139.45 | 0 | 0 | 0 | 1
Lean | SUCCESS | 35 | 2029-09-01 | 1 | 7956.75 | 3182.7 | 11139.45 | 0 | 0 | 0 | 1
Lean | SUCCESS | 36 | 2029-10-01 | 1 | 7956.75 | 3182.7 | 11139.45 | 0 | 0 | 0 | 1
Lean | SUCCESS | 37 | 2029-11-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 38 | 2029-12-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 39 | 2030-01-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 40 | 2030-02-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 41 | 2030-03-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 42 | 2030-04-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 43 | 2030-05-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 44 | 2030-06-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 45 | 2030-07-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 46 | 2030-08-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 47 | 2030-09-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 48 | 2030-10-01 | 1 | 8195.4525 | 3278.181 | 11473.6335 | 0 | 0 | 0 | 1
Lean | SUCCESS | 49 | 2030-11-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 50 | 2030-12-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 51 | 2031-01-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 52 | 2031-02-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 53 | 2031-03-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 54 | 2031-04-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 55 | 2031-05-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 56 | 2031-06-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 57 | 2031-07-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 58 | 2031-08-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 59 | 2031-09-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SUCCESS | 60 | 2031-10-01 | 1 | 8441.3161 | 3376.5264 | 11817.8425 | 0 | 0 | 0 | 1
Lean | SALES | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | SALES | 25 | 2028-11-01 | 0.25 | 2652.25 | 1060.9 | 3713.15 | 0 | 1250 | 625 | 1
Lean | SALES | 26 | 2028-12-01 | 0.25 | 2652.25 | 1060.9 | 3713.15 | 0 | 0 | 0 | 1
Lean | SALES | 27 | 2029-01-01 | 0.25 | 2652.25 | 1060.9 | 3713.15 | 0 | 0 | 0 | 1
Lean | SALES | 28 | 2029-02-01 | 0.25 | 2652.25 | 1060.9 | 3713.15 | 0 | 0 | 0 | 1
Lean | SALES | 29 | 2029-03-01 | 0.25 | 2652.25 | 1060.9 | 3713.15 | 0 | 0 | 0 | 1
Lean | SALES | 30 | 2029-04-01 | 0.25 | 2652.25 | 1060.9 | 3713.15 | 0 | 0 | 0 | 1
Lean | SALES | 31 | 2029-05-01 | 0.5 | 5304.5 | 2121.8 | 7426.3 | 0 | 1250 | 625 | 1
Lean | SALES | 32 | 2029-06-01 | 0.5 | 5304.5 | 2121.8 | 7426.3 | 0 | 0 | 0 | 1
Lean | SALES | 33 | 2029-07-01 | 0.5 | 5304.5 | 2121.8 | 7426.3 | 0 | 0 | 0 | 1
Lean | SALES | 34 | 2029-08-01 | 0.5 | 5304.5 | 2121.8 | 7426.3 | 0 | 0 | 0 | 1
Lean | SALES | 35 | 2029-09-01 | 0.5 | 5304.5 | 2121.8 | 7426.3 | 0 | 0 | 0 | 1
Lean | SALES | 36 | 2029-10-01 | 0.5 | 5304.5 | 2121.8 | 7426.3 | 0 | 0 | 0 | 1
Lean | SALES | 37 | 2029-11-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 38 | 2029-12-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 39 | 2030-01-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 40 | 2030-02-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 41 | 2030-03-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 42 | 2030-04-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 43 | 2030-05-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 44 | 2030-06-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 45 | 2030-07-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 46 | 2030-08-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 47 | 2030-09-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 48 | 2030-10-01 | 0.5 | 5463.635 | 2185.454 | 7649.089 | 0 | 0 | 0 | 1
Lean | SALES | 49 | 2030-11-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 50 | 2030-12-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 51 | 2031-01-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 52 | 2031-02-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 53 | 2031-03-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 54 | 2031-04-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 55 | 2031-05-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 56 | 2031-06-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 57 | 2031-07-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 58 | 2031-08-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 59 | 2031-09-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | SALES | 60 | 2031-10-01 | 0.5 | 5627.5441 | 2251.0176 | 7878.5617 | 0 | 0 | 0 | 1
Lean | AI-ENG | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | AI-ENG | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-PM | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Lean | CTMS-ENG | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | FOUNDER | 1 | 2026-11-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 3000 | 1
Base | FOUNDER | 2 | 2026-12-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 3 | 2027-01-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 4 | 2027-02-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 5 | 2027-03-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 6 | 2027-04-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 7 | 2027-05-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 8 | 2027-06-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 9 | 2027-07-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 10 | 2027-08-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 11 | 2027-09-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 12 | 2027-10-01 | 1 | 0 | 0 | 0 | 15000 | 0 | 0 | 1
Base | FOUNDER | 13 | 2027-11-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 14 | 2027-12-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 15 | 2028-01-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 16 | 2028-02-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 17 | 2028-03-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 18 | 2028-04-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 19 | 2028-05-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 20 | 2028-06-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 21 | 2028-07-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 22 | 2028-08-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 23 | 2028-09-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 24 | 2028-10-01 | 1 | 0 | 0 | 0 | 15600 | 0 | 0 | 1
Base | FOUNDER | 25 | 2028-11-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 26 | 2028-12-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 27 | 2029-01-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 28 | 2029-02-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 29 | 2029-03-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 30 | 2029-04-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 31 | 2029-05-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 32 | 2029-06-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 33 | 2029-07-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 34 | 2029-08-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 35 | 2029-09-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 36 | 2029-10-01 | 1 | 0 | 0 | 0 | 16224 | 0 | 0 | 1
Base | FOUNDER | 37 | 2029-11-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 38 | 2029-12-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 39 | 2030-01-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 40 | 2030-02-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 41 | 2030-03-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 42 | 2030-04-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 43 | 2030-05-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 44 | 2030-06-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 45 | 2030-07-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 46 | 2030-08-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 47 | 2030-09-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 48 | 2030-10-01 | 1 | 0 | 0 | 0 | 16872.96 | 0 | 0 | 1
Base | FOUNDER | 49 | 2030-11-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 50 | 2030-12-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 51 | 2031-01-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 52 | 2031-02-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 53 | 2031-03-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 54 | 2031-04-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 55 | 2031-05-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 56 | 2031-06-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 57 | 2031-07-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 58 | 2031-08-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 59 | 2031-09-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | FOUNDER | 60 | 2031-10-01 | 1 | 0 | 0 | 0 | 17547.8784 | 0 | 0 | 1
Base | LEAD | 1 | 2026-11-01 | 1 | 13750 | 5500 | 19250 | 0 | 8000 | 3000 | 1
Base | LEAD | 2 | 2026-12-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 3 | 2027-01-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 4 | 2027-02-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 5 | 2027-03-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 6 | 2027-04-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 7 | 2027-05-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 8 | 2027-06-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 9 | 2027-07-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 10 | 2027-08-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 11 | 2027-09-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 12 | 2027-10-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Base | LEAD | 13 | 2027-11-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 14 | 2027-12-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 15 | 2028-01-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 16 | 2028-02-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 17 | 2028-03-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 18 | 2028-04-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 19 | 2028-05-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 20 | 2028-06-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 21 | 2028-07-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 22 | 2028-08-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 23 | 2028-09-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 24 | 2028-10-01 | 1 | 14300 | 5720 | 20020 | 0 | 0 | 0 | 1
Base | LEAD | 25 | 2028-11-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 26 | 2028-12-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 27 | 2029-01-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 28 | 2029-02-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 29 | 2029-03-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 30 | 2029-04-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 31 | 2029-05-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 32 | 2029-06-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 33 | 2029-07-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 34 | 2029-08-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 35 | 2029-09-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 36 | 2029-10-01 | 1 | 14872 | 5948.8 | 20820.8 | 0 | 0 | 0 | 1
Base | LEAD | 37 | 2029-11-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 38 | 2029-12-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 39 | 2030-01-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 40 | 2030-02-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 41 | 2030-03-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 42 | 2030-04-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 43 | 2030-05-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 44 | 2030-06-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 45 | 2030-07-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 46 | 2030-08-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 47 | 2030-09-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 48 | 2030-10-01 | 1 | 15466.88 | 6186.752 | 21653.632 | 0 | 0 | 0 | 1
Base | LEAD | 49 | 2030-11-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 50 | 2030-12-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 51 | 2031-01-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 52 | 2031-02-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 53 | 2031-03-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 54 | 2031-04-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 55 | 2031-05-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 56 | 2031-06-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 57 | 2031-07-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 58 | 2031-08-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 59 | 2031-09-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | LEAD | 60 | 2031-10-01 | 1 | 16085.5552 | 6434.2221 | 22519.7773 | 0 | 0 | 0 | 1
Base | BACKEND | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | BACKEND | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | BACKEND | 3 | 2027-01-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 8000 | 3000 | 1
Base | BACKEND | 4 | 2027-02-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Base | BACKEND | 5 | 2027-03-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Base | BACKEND | 6 | 2027-04-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Base | BACKEND | 7 | 2027-05-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Base | BACKEND | 8 | 2027-06-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Base | BACKEND | 9 | 2027-07-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Base | BACKEND | 10 | 2027-08-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Base | BACKEND | 11 | 2027-09-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Base | BACKEND | 12 | 2027-10-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Base | BACKEND | 13 | 2027-11-01 | 1 | 12566.6667 | 5026.6667 | 17593.3333 | 0 | 0 | 0 | 1
Base | BACKEND | 14 | 2027-12-01 | 1 | 12566.6667 | 5026.6667 | 17593.3333 | 0 | 0 | 0 | 1
Base | BACKEND | 15 | 2028-01-01 | 1 | 12566.6667 | 5026.6667 | 17593.3333 | 0 | 0 | 0 | 1
Base | BACKEND | 16 | 2028-02-01 | 2 | 25133.3333 | 10053.3333 | 35186.6667 | 0 | 8000 | 3000 | 2
Base | BACKEND | 17 | 2028-03-01 | 2 | 25133.3333 | 10053.3333 | 35186.6667 | 0 | 0 | 0 | 2
Base | BACKEND | 18 | 2028-04-01 | 2 | 25133.3333 | 10053.3333 | 35186.6667 | 0 | 0 | 0 | 2
Base | BACKEND | 19 | 2028-05-01 | 2 | 25133.3333 | 10053.3333 | 35186.6667 | 0 | 0 | 0 | 2
Base | BACKEND | 20 | 2028-06-01 | 2 | 25133.3333 | 10053.3333 | 35186.6667 | 0 | 0 | 0 | 2
Base | BACKEND | 21 | 2028-07-01 | 2 | 25133.3333 | 10053.3333 | 35186.6667 | 0 | 0 | 0 | 2
Base | BACKEND | 22 | 2028-08-01 | 2 | 25133.3333 | 10053.3333 | 35186.6667 | 0 | 0 | 0 | 2
Base | BACKEND | 23 | 2028-09-01 | 2 | 25133.3333 | 10053.3333 | 35186.6667 | 0 | 0 | 0 | 2
Base | BACKEND | 24 | 2028-10-01 | 2 | 25133.3333 | 10053.3333 | 35186.6667 | 0 | 0 | 0 | 2
Base | BACKEND | 25 | 2028-11-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 26 | 2028-12-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 27 | 2029-01-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 28 | 2029-02-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 29 | 2029-03-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 30 | 2029-04-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 31 | 2029-05-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 32 | 2029-06-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 33 | 2029-07-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 34 | 2029-08-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 35 | 2029-09-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 36 | 2029-10-01 | 2 | 26138.6667 | 10455.4667 | 36594.1333 | 0 | 0 | 0 | 2
Base | BACKEND | 37 | 2029-11-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 38 | 2029-12-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 39 | 2030-01-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 40 | 2030-02-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 41 | 2030-03-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 42 | 2030-04-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 43 | 2030-05-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 44 | 2030-06-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 45 | 2030-07-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 46 | 2030-08-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 47 | 2030-09-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 48 | 2030-10-01 | 2 | 27184.2133 | 10873.6853 | 38057.8987 | 0 | 0 | 0 | 2
Base | BACKEND | 49 | 2030-11-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 50 | 2030-12-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 51 | 2031-01-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 52 | 2031-02-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 53 | 2031-03-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 54 | 2031-04-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 55 | 2031-05-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 56 | 2031-06-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 57 | 2031-07-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 58 | 2031-08-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 59 | 2031-09-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | BACKEND | 60 | 2031-10-01 | 2 | 28271.5819 | 11308.6327 | 39580.2146 | 0 | 0 | 0 | 2
Base | FRONTEND | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | FRONTEND | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | FRONTEND | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | FRONTEND | 4 | 2027-02-01 | 0.5 | 5833.3333 | 2333.3333 | 8166.6667 | 0 | 4000 | 1500 | 1
Base | FRONTEND | 5 | 2027-03-01 | 0.5 | 5833.3333 | 2333.3333 | 8166.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 6 | 2027-04-01 | 0.5 | 5833.3333 | 2333.3333 | 8166.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 7 | 2027-05-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 4000 | 1500 | 1
Base | FRONTEND | 8 | 2027-06-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Base | FRONTEND | 9 | 2027-07-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Base | FRONTEND | 10 | 2027-08-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Base | FRONTEND | 11 | 2027-09-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Base | FRONTEND | 12 | 2027-10-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Base | FRONTEND | 13 | 2027-11-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 14 | 2027-12-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 15 | 2028-01-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 16 | 2028-02-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 17 | 2028-03-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 18 | 2028-04-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 19 | 2028-05-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 20 | 2028-06-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 21 | 2028-07-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 22 | 2028-08-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 23 | 2028-09-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 24 | 2028-10-01 | 1 | 12133.3333 | 4853.3333 | 16986.6667 | 0 | 0 | 0 | 1
Base | FRONTEND | 25 | 2028-11-01 | 1 | 12618.6667 | 5047.4667 | 17666.1333 | 0 | 0 | 0 | 1
Base | FRONTEND | 26 | 2028-12-01 | 1 | 12618.6667 | 5047.4667 | 17666.1333 | 0 | 0 | 0 | 1
Base | FRONTEND | 27 | 2029-01-01 | 1 | 12618.6667 | 5047.4667 | 17666.1333 | 0 | 0 | 0 | 1
Base | FRONTEND | 28 | 2029-02-01 | 1 | 12618.6667 | 5047.4667 | 17666.1333 | 0 | 0 | 0 | 1
Base | FRONTEND | 29 | 2029-03-01 | 1 | 12618.6667 | 5047.4667 | 17666.1333 | 0 | 0 | 0 | 1
Base | FRONTEND | 30 | 2029-04-01 | 1 | 12618.6667 | 5047.4667 | 17666.1333 | 0 | 0 | 0 | 1
Base | FRONTEND | 31 | 2029-05-01 | 2 | 25237.3333 | 10094.9333 | 35332.2667 | 0 | 8000 | 3000 | 2
Base | FRONTEND | 32 | 2029-06-01 | 2 | 25237.3333 | 10094.9333 | 35332.2667 | 0 | 0 | 0 | 2
Base | FRONTEND | 33 | 2029-07-01 | 2 | 25237.3333 | 10094.9333 | 35332.2667 | 0 | 0 | 0 | 2
Base | FRONTEND | 34 | 2029-08-01 | 2 | 25237.3333 | 10094.9333 | 35332.2667 | 0 | 0 | 0 | 2
Base | FRONTEND | 35 | 2029-09-01 | 2 | 25237.3333 | 10094.9333 | 35332.2667 | 0 | 0 | 0 | 2
Base | FRONTEND | 36 | 2029-10-01 | 2 | 25237.3333 | 10094.9333 | 35332.2667 | 0 | 0 | 0 | 2
Base | FRONTEND | 37 | 2029-11-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 38 | 2029-12-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 39 | 2030-01-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 40 | 2030-02-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 41 | 2030-03-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 42 | 2030-04-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 43 | 2030-05-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 44 | 2030-06-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 45 | 2030-07-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 46 | 2030-08-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 47 | 2030-09-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 48 | 2030-10-01 | 2 | 26246.8267 | 10498.7307 | 36745.5573 | 0 | 0 | 0 | 2
Base | FRONTEND | 49 | 2030-11-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 50 | 2030-12-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 51 | 2031-01-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 52 | 2031-02-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 53 | 2031-03-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 54 | 2031-04-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 55 | 2031-05-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 56 | 2031-06-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 57 | 2031-07-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 58 | 2031-08-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 59 | 2031-09-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | FRONTEND | 60 | 2031-10-01 | 2 | 27296.6997 | 10918.6799 | 38215.3796 | 0 | 0 | 0 | 2
Base | QA | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | QA | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | QA | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | QA | 4 | 2027-02-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 4000 | 1500 | 1
Base | QA | 5 | 2027-03-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Base | QA | 6 | 2027-04-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Base | QA | 7 | 2027-05-01 | 0.75 | 6875 | 2750 | 9625 | 0 | 2000 | 750 | 1
Base | QA | 8 | 2027-06-01 | 0.75 | 6875 | 2750 | 9625 | 0 | 0 | 0 | 1
Base | QA | 9 | 2027-07-01 | 0.75 | 6875 | 2750 | 9625 | 0 | 0 | 0 | 1
Base | QA | 10 | 2027-08-01 | 0.75 | 6875 | 2750 | 9625 | 0 | 0 | 0 | 1
Base | QA | 11 | 2027-09-01 | 0.75 | 6875 | 2750 | 9625 | 0 | 0 | 0 | 1
Base | QA | 12 | 2027-10-01 | 0.75 | 6875 | 2750 | 9625 | 0 | 0 | 0 | 1
Base | QA | 13 | 2027-11-01 | 0.75 | 7150 | 2860 | 10010 | 0 | 0 | 0 | 1
Base | QA | 14 | 2027-12-01 | 0.75 | 7150 | 2860 | 10010 | 0 | 0 | 0 | 1
Base | QA | 15 | 2028-01-01 | 0.75 | 7150 | 2860 | 10010 | 0 | 0 | 0 | 1
Base | QA | 16 | 2028-02-01 | 1 | 9533.3333 | 3813.3333 | 13346.6667 | 0 | 2000 | 750 | 1
Base | QA | 17 | 2028-03-01 | 1 | 9533.3333 | 3813.3333 | 13346.6667 | 0 | 0 | 0 | 1
Base | QA | 18 | 2028-04-01 | 1 | 9533.3333 | 3813.3333 | 13346.6667 | 0 | 0 | 0 | 1
Base | QA | 19 | 2028-05-01 | 1 | 9533.3333 | 3813.3333 | 13346.6667 | 0 | 0 | 0 | 1
Base | QA | 20 | 2028-06-01 | 1 | 9533.3333 | 3813.3333 | 13346.6667 | 0 | 0 | 0 | 1
Base | QA | 21 | 2028-07-01 | 1 | 9533.3333 | 3813.3333 | 13346.6667 | 0 | 0 | 0 | 1
Base | QA | 22 | 2028-08-01 | 1 | 9533.3333 | 3813.3333 | 13346.6667 | 0 | 0 | 0 | 1
Base | QA | 23 | 2028-09-01 | 1 | 9533.3333 | 3813.3333 | 13346.6667 | 0 | 0 | 0 | 1
Base | QA | 24 | 2028-10-01 | 1 | 9533.3333 | 3813.3333 | 13346.6667 | 0 | 0 | 0 | 1
Base | QA | 25 | 2028-11-01 | 1 | 9914.6667 | 3965.8667 | 13880.5333 | 0 | 0 | 0 | 1
Base | QA | 26 | 2028-12-01 | 1 | 9914.6667 | 3965.8667 | 13880.5333 | 0 | 0 | 0 | 1
Base | QA | 27 | 2029-01-01 | 1 | 9914.6667 | 3965.8667 | 13880.5333 | 0 | 0 | 0 | 1
Base | QA | 28 | 2029-02-01 | 1 | 9914.6667 | 3965.8667 | 13880.5333 | 0 | 0 | 0 | 1
Base | QA | 29 | 2029-03-01 | 1 | 9914.6667 | 3965.8667 | 13880.5333 | 0 | 0 | 0 | 1
Base | QA | 30 | 2029-04-01 | 1 | 9914.6667 | 3965.8667 | 13880.5333 | 0 | 0 | 0 | 1
Base | QA | 31 | 2029-05-01 | 2 | 19829.3333 | 7931.7333 | 27761.0667 | 0 | 8000 | 3000 | 2
Base | QA | 32 | 2029-06-01 | 2 | 19829.3333 | 7931.7333 | 27761.0667 | 0 | 0 | 0 | 2
Base | QA | 33 | 2029-07-01 | 2 | 19829.3333 | 7931.7333 | 27761.0667 | 0 | 0 | 0 | 2
Base | QA | 34 | 2029-08-01 | 2 | 19829.3333 | 7931.7333 | 27761.0667 | 0 | 0 | 0 | 2
Base | QA | 35 | 2029-09-01 | 2 | 19829.3333 | 7931.7333 | 27761.0667 | 0 | 0 | 0 | 2
Base | QA | 36 | 2029-10-01 | 2 | 19829.3333 | 7931.7333 | 27761.0667 | 0 | 0 | 0 | 2
Base | QA | 37 | 2029-11-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 38 | 2029-12-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 39 | 2030-01-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 40 | 2030-02-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 41 | 2030-03-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 42 | 2030-04-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 43 | 2030-05-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 44 | 2030-06-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 45 | 2030-07-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 46 | 2030-08-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 47 | 2030-09-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 48 | 2030-10-01 | 2 | 20622.5067 | 8249.0027 | 28871.5093 | 0 | 0 | 0 | 2
Base | QA | 49 | 2030-11-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 50 | 2030-12-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 51 | 2031-01-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 52 | 2031-02-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 53 | 2031-03-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 54 | 2031-04-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 55 | 2031-05-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 56 | 2031-06-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 57 | 2031-07-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 58 | 2031-08-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 59 | 2031-09-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | QA | 60 | 2031-10-01 | 2 | 21447.4069 | 8578.9628 | 30026.3697 | 0 | 0 | 0 | 2
Base | OPS | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | OPS | 2 | 2026-12-01 | 0.25 | 3958.3333 | 0 | 3958.3333 | 0 | 0 | 750 | 1
Base | OPS | 3 | 2027-01-01 | 0.25 | 3958.3333 | 0 | 3958.3333 | 0 | 0 | 0 | 1
Base | OPS | 4 | 2027-02-01 | 0.25 | 3958.3333 | 0 | 3958.3333 | 0 | 0 | 0 | 1
Base | OPS | 5 | 2027-03-01 | 0.25 | 3958.3333 | 0 | 3958.3333 | 0 | 0 | 0 | 1
Base | OPS | 6 | 2027-04-01 | 0.25 | 3958.3333 | 0 | 3958.3333 | 0 | 0 | 0 | 1
Base | OPS | 7 | 2027-05-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 750 | 1
Base | OPS | 8 | 2027-06-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 0 | 1
Base | OPS | 9 | 2027-07-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 0 | 1
Base | OPS | 10 | 2027-08-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 0 | 1
Base | OPS | 11 | 2027-09-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 0 | 1
Base | OPS | 12 | 2027-10-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 0 | 1
Base | OPS | 13 | 2027-11-01 | 0.5 | 8233.3333 | 0 | 8233.3333 | 0 | 0 | 0 | 1
Base | OPS | 14 | 2027-12-01 | 0.5 | 8233.3333 | 0 | 8233.3333 | 0 | 0 | 0 | 1
Base | OPS | 15 | 2028-01-01 | 0.5 | 8233.3333 | 0 | 8233.3333 | 0 | 0 | 0 | 1
Base | OPS | 16 | 2028-02-01 | 0.75 | 12350 | 0 | 12350 | 0 | 0 | 750 | 1
Base | OPS | 17 | 2028-03-01 | 0.75 | 12350 | 0 | 12350 | 0 | 0 | 0 | 1
Base | OPS | 18 | 2028-04-01 | 0.75 | 12350 | 0 | 12350 | 0 | 0 | 0 | 1
Base | OPS | 19 | 2028-05-01 | 0.75 | 12350 | 0 | 12350 | 0 | 0 | 0 | 1
Base | OPS | 20 | 2028-06-01 | 0.75 | 12350 | 0 | 12350 | 0 | 0 | 0 | 1
Base | OPS | 21 | 2028-07-01 | 0.75 | 12350 | 0 | 12350 | 0 | 0 | 0 | 1
Base | OPS | 22 | 2028-08-01 | 0.75 | 12350 | 0 | 12350 | 0 | 0 | 0 | 1
Base | OPS | 23 | 2028-09-01 | 0.75 | 12350 | 0 | 12350 | 0 | 0 | 0 | 1
Base | OPS | 24 | 2028-10-01 | 0.75 | 12350 | 0 | 12350 | 0 | 0 | 0 | 1
Base | OPS | 25 | 2028-11-01 | 0.75 | 12844 | 0 | 12844 | 0 | 0 | 0 | 1
Base | OPS | 26 | 2028-12-01 | 0.75 | 12844 | 0 | 12844 | 0 | 0 | 0 | 1
Base | OPS | 27 | 2029-01-01 | 0.75 | 12844 | 0 | 12844 | 0 | 0 | 0 | 1
Base | OPS | 28 | 2029-02-01 | 0.75 | 12844 | 0 | 12844 | 0 | 0 | 0 | 1
Base | OPS | 29 | 2029-03-01 | 0.75 | 12844 | 0 | 12844 | 0 | 0 | 0 | 1
Base | OPS | 30 | 2029-04-01 | 0.75 | 12844 | 0 | 12844 | 0 | 0 | 0 | 1
Base | OPS | 31 | 2029-05-01 | 1 | 17125.3333 | 0 | 17125.3333 | 0 | 0 | 750 | 1
Base | OPS | 32 | 2029-06-01 | 1 | 17125.3333 | 0 | 17125.3333 | 0 | 0 | 0 | 1
Base | OPS | 33 | 2029-07-01 | 1 | 17125.3333 | 0 | 17125.3333 | 0 | 0 | 0 | 1
Base | OPS | 34 | 2029-08-01 | 1 | 17125.3333 | 0 | 17125.3333 | 0 | 0 | 0 | 1
Base | OPS | 35 | 2029-09-01 | 1 | 17125.3333 | 0 | 17125.3333 | 0 | 0 | 0 | 1
Base | OPS | 36 | 2029-10-01 | 1 | 17125.3333 | 0 | 17125.3333 | 0 | 0 | 0 | 1
Base | OPS | 37 | 2029-11-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 38 | 2029-12-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 39 | 2030-01-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 40 | 2030-02-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 41 | 2030-03-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 42 | 2030-04-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 43 | 2030-05-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 44 | 2030-06-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 45 | 2030-07-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 46 | 2030-08-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 47 | 2030-09-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 48 | 2030-10-01 | 1 | 17810.3467 | 0 | 17810.3467 | 0 | 0 | 0 | 1
Base | OPS | 49 | 2030-11-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 50 | 2030-12-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 51 | 2031-01-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 52 | 2031-02-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 53 | 2031-03-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 54 | 2031-04-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 55 | 2031-05-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 56 | 2031-06-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 57 | 2031-07-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 58 | 2031-08-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 59 | 2031-09-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | OPS | 60 | 2031-10-01 | 1 | 18522.7605 | 0 | 18522.7605 | 0 | 0 | 0 | 1
Base | DESIGN | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 2 | 2026-12-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 750 | 1
Base | DESIGN | 3 | 2027-01-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 4 | 2027-02-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 5 | 2027-03-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 6 | 2027-04-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 7 | 2027-05-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 8 | 2027-06-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 9 | 2027-07-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 10 | 2027-08-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 11 | 2027-09-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 12 | 2027-10-01 | 0.25 | 2708.3333 | 0 | 2708.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 13 | 2027-11-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 14 | 2027-12-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 15 | 2028-01-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 16 | 2028-02-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 17 | 2028-03-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 18 | 2028-04-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 19 | 2028-05-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 20 | 2028-06-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 21 | 2028-07-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 22 | 2028-08-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 23 | 2028-09-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 24 | 2028-10-01 | 0.25 | 2816.6667 | 0 | 2816.6667 | 0 | 0 | 0 | 1
Base | DESIGN | 25 | 2028-11-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 26 | 2028-12-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 27 | 2029-01-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 28 | 2029-02-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 29 | 2029-03-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 30 | 2029-04-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 31 | 2029-05-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 32 | 2029-06-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 33 | 2029-07-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 34 | 2029-08-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 35 | 2029-09-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 36 | 2029-10-01 | 0.25 | 2929.3333 | 0 | 2929.3333 | 0 | 0 | 0 | 1
Base | DESIGN | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | DESIGN | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | VALIDATION | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | VALIDATION | 2 | 2026-12-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 450 | 1
Base | VALIDATION | 3 | 2027-01-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 0 | 1
Base | VALIDATION | 4 | 2027-02-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 0 | 1
Base | VALIDATION | 5 | 2027-03-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 0 | 1
Base | VALIDATION | 6 | 2027-04-01 | 0.15 | 2500 | 0 | 2500 | 0 | 0 | 0 | 1
Base | VALIDATION | 7 | 2027-05-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 300 | 1
Base | VALIDATION | 8 | 2027-06-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 9 | 2027-07-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 10 | 2027-08-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 11 | 2027-09-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 12 | 2027-10-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 13 | 2027-11-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 14 | 2027-12-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 15 | 2028-01-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 16 | 2028-02-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 17 | 2028-03-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 18 | 2028-04-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 19 | 2028-05-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 20 | 2028-06-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 21 | 2028-07-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 22 | 2028-08-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 23 | 2028-09-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 24 | 2028-10-01 | 0.25 | 4333.3333 | 0 | 4333.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 25 | 2028-11-01 | 0.25 | 4506.6667 | 0 | 4506.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 26 | 2028-12-01 | 0.25 | 4506.6667 | 0 | 4506.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 27 | 2029-01-01 | 0.25 | 4506.6667 | 0 | 4506.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 28 | 2029-02-01 | 0.25 | 4506.6667 | 0 | 4506.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 29 | 2029-03-01 | 0.25 | 4506.6667 | 0 | 4506.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 30 | 2029-04-01 | 0.25 | 4506.6667 | 0 | 4506.6667 | 0 | 0 | 0 | 1
Base | VALIDATION | 31 | 2029-05-01 | 0.5 | 9013.3333 | 0 | 9013.3333 | 0 | 0 | 750 | 1
Base | VALIDATION | 32 | 2029-06-01 | 0.5 | 9013.3333 | 0 | 9013.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 33 | 2029-07-01 | 0.5 | 9013.3333 | 0 | 9013.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 34 | 2029-08-01 | 0.5 | 9013.3333 | 0 | 9013.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 35 | 2029-09-01 | 0.5 | 9013.3333 | 0 | 9013.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 36 | 2029-10-01 | 0.5 | 9013.3333 | 0 | 9013.3333 | 0 | 0 | 0 | 1
Base | VALIDATION | 37 | 2029-11-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 38 | 2029-12-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 39 | 2030-01-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 40 | 2030-02-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 41 | 2030-03-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 42 | 2030-04-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 43 | 2030-05-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 44 | 2030-06-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 45 | 2030-07-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 46 | 2030-08-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 47 | 2030-09-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 48 | 2030-10-01 | 0.5 | 9373.8667 | 0 | 9373.8667 | 0 | 0 | 0 | 1
Base | VALIDATION | 49 | 2030-11-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 50 | 2030-12-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 51 | 2031-01-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 52 | 2031-02-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 53 | 2031-03-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 54 | 2031-04-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 55 | 2031-05-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 56 | 2031-06-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 57 | 2031-07-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 58 | 2031-08-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 59 | 2031-09-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | VALIDATION | 60 | 2031-10-01 | 0.5 | 9748.8213 | 0 | 9748.8213 | 0 | 0 | 0 | 1
Base | SUCCESS | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SUCCESS | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SUCCESS | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SUCCESS | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SUCCESS | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SUCCESS | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SUCCESS | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SUCCESS | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SUCCESS | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SUCCESS | 10 | 2027-08-01 | 0.5 | 3750 | 1500 | 5250 | 0 | 4000 | 1500 | 1
Base | SUCCESS | 11 | 2027-09-01 | 0.5 | 3750 | 1500 | 5250 | 0 | 0 | 0 | 1
Base | SUCCESS | 12 | 2027-10-01 | 0.5 | 3750 | 1500 | 5250 | 0 | 0 | 0 | 1
Base | SUCCESS | 13 | 2027-11-01 | 0.5 | 3900 | 1560 | 5460 | 0 | 0 | 0 | 1
Base | SUCCESS | 14 | 2027-12-01 | 0.5 | 3900 | 1560 | 5460 | 0 | 0 | 0 | 1
Base | SUCCESS | 15 | 2028-01-01 | 0.5 | 3900 | 1560 | 5460 | 0 | 0 | 0 | 1
Base | SUCCESS | 16 | 2028-02-01 | 1 | 7800 | 3120 | 10920 | 0 | 4000 | 1500 | 1
Base | SUCCESS | 17 | 2028-03-01 | 1 | 7800 | 3120 | 10920 | 0 | 0 | 0 | 1
Base | SUCCESS | 18 | 2028-04-01 | 1 | 7800 | 3120 | 10920 | 0 | 0 | 0 | 1
Base | SUCCESS | 19 | 2028-05-01 | 1 | 7800 | 3120 | 10920 | 0 | 0 | 0 | 1
Base | SUCCESS | 20 | 2028-06-01 | 1 | 7800 | 3120 | 10920 | 0 | 0 | 0 | 1
Base | SUCCESS | 21 | 2028-07-01 | 1 | 7800 | 3120 | 10920 | 0 | 0 | 0 | 1
Base | SUCCESS | 22 | 2028-08-01 | 1 | 7800 | 3120 | 10920 | 0 | 0 | 0 | 1
Base | SUCCESS | 23 | 2028-09-01 | 1 | 7800 | 3120 | 10920 | 0 | 0 | 0 | 1
Base | SUCCESS | 24 | 2028-10-01 | 1 | 7800 | 3120 | 10920 | 0 | 0 | 0 | 1
Base | SUCCESS | 25 | 2028-11-01 | 1 | 8112 | 3244.8 | 11356.8 | 0 | 0 | 0 | 1
Base | SUCCESS | 26 | 2028-12-01 | 1 | 8112 | 3244.8 | 11356.8 | 0 | 0 | 0 | 1
Base | SUCCESS | 27 | 2029-01-01 | 1 | 8112 | 3244.8 | 11356.8 | 0 | 0 | 0 | 1
Base | SUCCESS | 28 | 2029-02-01 | 1 | 8112 | 3244.8 | 11356.8 | 0 | 0 | 0 | 1
Base | SUCCESS | 29 | 2029-03-01 | 1 | 8112 | 3244.8 | 11356.8 | 0 | 0 | 0 | 1
Base | SUCCESS | 30 | 2029-04-01 | 1 | 8112 | 3244.8 | 11356.8 | 0 | 0 | 0 | 1
Base | SUCCESS | 31 | 2029-05-01 | 2 | 16224 | 6489.6 | 22713.6 | 0 | 8000 | 3000 | 2
Base | SUCCESS | 32 | 2029-06-01 | 2 | 16224 | 6489.6 | 22713.6 | 0 | 0 | 0 | 2
Base | SUCCESS | 33 | 2029-07-01 | 2 | 16224 | 6489.6 | 22713.6 | 0 | 0 | 0 | 2
Base | SUCCESS | 34 | 2029-08-01 | 2 | 16224 | 6489.6 | 22713.6 | 0 | 0 | 0 | 2
Base | SUCCESS | 35 | 2029-09-01 | 2 | 16224 | 6489.6 | 22713.6 | 0 | 0 | 0 | 2
Base | SUCCESS | 36 | 2029-10-01 | 2 | 16224 | 6489.6 | 22713.6 | 0 | 0 | 0 | 2
Base | SUCCESS | 37 | 2029-11-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 38 | 2029-12-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 39 | 2030-01-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 40 | 2030-02-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 41 | 2030-03-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 42 | 2030-04-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 43 | 2030-05-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 44 | 2030-06-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 45 | 2030-07-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 46 | 2030-08-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 47 | 2030-09-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 48 | 2030-10-01 | 2 | 16872.96 | 6749.184 | 23622.144 | 0 | 0 | 0 | 2
Base | SUCCESS | 49 | 2030-11-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 50 | 2030-12-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 51 | 2031-01-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 52 | 2031-02-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 53 | 2031-03-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 54 | 2031-04-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 55 | 2031-05-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 56 | 2031-06-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 57 | 2031-07-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 58 | 2031-08-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 59 | 2031-09-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SUCCESS | 60 | 2031-10-01 | 2 | 17547.8784 | 7019.1514 | 24567.0298 | 0 | 0 | 0 | 2
Base | SALES | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | SALES | 19 | 2028-05-01 | 0.5 | 5200 | 2080 | 7280 | 0 | 4000 | 1500 | 1
Base | SALES | 20 | 2028-06-01 | 0.5 | 5200 | 2080 | 7280 | 0 | 0 | 0 | 1
Base | SALES | 21 | 2028-07-01 | 0.5 | 5200 | 2080 | 7280 | 0 | 0 | 0 | 1
Base | SALES | 22 | 2028-08-01 | 0.5 | 5200 | 2080 | 7280 | 0 | 0 | 0 | 1
Base | SALES | 23 | 2028-09-01 | 0.5 | 5200 | 2080 | 7280 | 0 | 0 | 0 | 1
Base | SALES | 24 | 2028-10-01 | 0.5 | 5200 | 2080 | 7280 | 0 | 0 | 0 | 1
Base | SALES | 25 | 2028-11-01 | 0.5 | 5408 | 2163.2 | 7571.2 | 0 | 0 | 0 | 1
Base | SALES | 26 | 2028-12-01 | 0.5 | 5408 | 2163.2 | 7571.2 | 0 | 0 | 0 | 1
Base | SALES | 27 | 2029-01-01 | 0.5 | 5408 | 2163.2 | 7571.2 | 0 | 0 | 0 | 1
Base | SALES | 28 | 2029-02-01 | 0.5 | 5408 | 2163.2 | 7571.2 | 0 | 0 | 0 | 1
Base | SALES | 29 | 2029-03-01 | 0.5 | 5408 | 2163.2 | 7571.2 | 0 | 0 | 0 | 1
Base | SALES | 30 | 2029-04-01 | 0.5 | 5408 | 2163.2 | 7571.2 | 0 | 0 | 0 | 1
Base | SALES | 31 | 2029-05-01 | 1 | 10816 | 4326.4 | 15142.4 | 0 | 4000 | 1500 | 1
Base | SALES | 32 | 2029-06-01 | 1 | 10816 | 4326.4 | 15142.4 | 0 | 0 | 0 | 1
Base | SALES | 33 | 2029-07-01 | 1 | 10816 | 4326.4 | 15142.4 | 0 | 0 | 0 | 1
Base | SALES | 34 | 2029-08-01 | 1 | 10816 | 4326.4 | 15142.4 | 0 | 0 | 0 | 1
Base | SALES | 35 | 2029-09-01 | 1 | 10816 | 4326.4 | 15142.4 | 0 | 0 | 0 | 1
Base | SALES | 36 | 2029-10-01 | 1 | 10816 | 4326.4 | 15142.4 | 0 | 0 | 0 | 1
Base | SALES | 37 | 2029-11-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 38 | 2029-12-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 39 | 2030-01-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 40 | 2030-02-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 41 | 2030-03-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 42 | 2030-04-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 43 | 2030-05-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 44 | 2030-06-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 45 | 2030-07-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 46 | 2030-08-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 47 | 2030-09-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 48 | 2030-10-01 | 1 | 11248.64 | 4499.456 | 15748.096 | 0 | 0 | 0 | 1
Base | SALES | 49 | 2030-11-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 50 | 2030-12-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 51 | 2031-01-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 52 | 2031-02-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 53 | 2031-03-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 54 | 2031-04-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 55 | 2031-05-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 56 | 2031-06-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 57 | 2031-07-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 58 | 2031-08-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 59 | 2031-09-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | SALES | 60 | 2031-10-01 | 1 | 11698.5856 | 4679.4342 | 16378.0198 | 0 | 0 | 0 | 1
Base | AI-ENG | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | AI-ENG | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-PM | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Base | CTMS-ENG | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | FOUNDER | 1 | 2026-11-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 3500 | 1
Growth | FOUNDER | 2 | 2026-12-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 3 | 2027-01-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 4 | 2027-02-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 5 | 2027-03-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 6 | 2027-04-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 7 | 2027-05-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 8 | 2027-06-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 9 | 2027-07-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 10 | 2027-08-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 11 | 2027-09-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 12 | 2027-10-01 | 1 | 0 | 0 | 0 | 16666.6667 | 0 | 0 | 1
Growth | FOUNDER | 13 | 2027-11-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 14 | 2027-12-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 15 | 2028-01-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 16 | 2028-02-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 17 | 2028-03-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 18 | 2028-04-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 19 | 2028-05-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 20 | 2028-06-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 21 | 2028-07-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 22 | 2028-08-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 23 | 2028-09-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 24 | 2028-10-01 | 1 | 0 | 0 | 0 | 17500 | 0 | 0 | 1
Growth | FOUNDER | 25 | 2028-11-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 26 | 2028-12-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 27 | 2029-01-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 28 | 2029-02-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 29 | 2029-03-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 30 | 2029-04-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 31 | 2029-05-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 32 | 2029-06-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 33 | 2029-07-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 34 | 2029-08-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 35 | 2029-09-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 36 | 2029-10-01 | 1 | 0 | 0 | 0 | 18375 | 0 | 0 | 1
Growth | FOUNDER | 37 | 2029-11-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 38 | 2029-12-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 39 | 2030-01-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 40 | 2030-02-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 41 | 2030-03-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 42 | 2030-04-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 43 | 2030-05-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 44 | 2030-06-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 45 | 2030-07-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 46 | 2030-08-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 47 | 2030-09-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 48 | 2030-10-01 | 1 | 0 | 0 | 0 | 19293.75 | 0 | 0 | 1
Growth | FOUNDER | 49 | 2030-11-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 50 | 2030-12-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 51 | 2031-01-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 52 | 2031-02-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 53 | 2031-03-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 54 | 2031-04-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 55 | 2031-05-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 56 | 2031-06-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 57 | 2031-07-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 58 | 2031-08-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 59 | 2031-09-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | FOUNDER | 60 | 2031-10-01 | 1 | 0 | 0 | 0 | 20258.4375 | 0 | 0 | 1
Growth | LEAD | 1 | 2026-11-01 | 1 | 13750 | 5500 | 19250 | 0 | 12000 | 3500 | 1
Growth | LEAD | 2 | 2026-12-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 3 | 2027-01-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 4 | 2027-02-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 5 | 2027-03-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 6 | 2027-04-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 7 | 2027-05-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 8 | 2027-06-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 9 | 2027-07-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 10 | 2027-08-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 11 | 2027-09-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 12 | 2027-10-01 | 1 | 13750 | 5500 | 19250 | 0 | 0 | 0 | 1
Growth | LEAD | 13 | 2027-11-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 14 | 2027-12-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 15 | 2028-01-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 16 | 2028-02-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 17 | 2028-03-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 18 | 2028-04-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 19 | 2028-05-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 20 | 2028-06-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 21 | 2028-07-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 22 | 2028-08-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 23 | 2028-09-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 24 | 2028-10-01 | 1 | 14437.5 | 5775 | 20212.5 | 0 | 0 | 0 | 1
Growth | LEAD | 25 | 2028-11-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 26 | 2028-12-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 27 | 2029-01-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 28 | 2029-02-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 29 | 2029-03-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 30 | 2029-04-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 31 | 2029-05-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 32 | 2029-06-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 33 | 2029-07-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 34 | 2029-08-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 35 | 2029-09-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 36 | 2029-10-01 | 1 | 15159.375 | 6063.75 | 21223.125 | 0 | 0 | 0 | 1
Growth | LEAD | 37 | 2029-11-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 38 | 2029-12-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 39 | 2030-01-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 40 | 2030-02-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 41 | 2030-03-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 42 | 2030-04-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 43 | 2030-05-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 44 | 2030-06-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 45 | 2030-07-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 46 | 2030-08-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 47 | 2030-09-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 48 | 2030-10-01 | 1 | 15917.3438 | 6366.9375 | 22284.2812 | 0 | 0 | 0 | 1
Growth | LEAD | 49 | 2030-11-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 50 | 2030-12-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 51 | 2031-01-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 52 | 2031-02-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 53 | 2031-03-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 54 | 2031-04-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 55 | 2031-05-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 56 | 2031-06-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 57 | 2031-07-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 58 | 2031-08-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 59 | 2031-09-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | LEAD | 60 | 2031-10-01 | 1 | 16713.2109 | 6685.2844 | 23398.4953 | 0 | 0 | 0 | 1
Growth | BACKEND | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | BACKEND | 2 | 2026-12-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 12000 | 3500 | 1
Growth | BACKEND | 3 | 2027-01-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Growth | BACKEND | 4 | 2027-02-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Growth | BACKEND | 5 | 2027-03-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Growth | BACKEND | 6 | 2027-04-01 | 1 | 12083.3333 | 4833.3333 | 16916.6667 | 0 | 0 | 0 | 1
Growth | BACKEND | 7 | 2027-05-01 | 2 | 24166.6667 | 9666.6667 | 33833.3333 | 0 | 12000 | 3500 | 2
Growth | BACKEND | 8 | 2027-06-01 | 2 | 24166.6667 | 9666.6667 | 33833.3333 | 0 | 0 | 0 | 2
Growth | BACKEND | 9 | 2027-07-01 | 2 | 24166.6667 | 9666.6667 | 33833.3333 | 0 | 0 | 0 | 2
Growth | BACKEND | 10 | 2027-08-01 | 2 | 24166.6667 | 9666.6667 | 33833.3333 | 0 | 0 | 0 | 2
Growth | BACKEND | 11 | 2027-09-01 | 2 | 24166.6667 | 9666.6667 | 33833.3333 | 0 | 0 | 0 | 2
Growth | BACKEND | 12 | 2027-10-01 | 2 | 24166.6667 | 9666.6667 | 33833.3333 | 0 | 0 | 0 | 2
Growth | BACKEND | 13 | 2027-11-01 | 2 | 25375 | 10150 | 35525 | 0 | 0 | 0 | 2
Growth | BACKEND | 14 | 2027-12-01 | 2 | 25375 | 10150 | 35525 | 0 | 0 | 0 | 2
Growth | BACKEND | 15 | 2028-01-01 | 2 | 25375 | 10150 | 35525 | 0 | 0 | 0 | 2
Growth | BACKEND | 16 | 2028-02-01 | 3 | 38062.5 | 15225 | 53287.5 | 0 | 12000 | 3500 | 3
Growth | BACKEND | 17 | 2028-03-01 | 3 | 38062.5 | 15225 | 53287.5 | 0 | 0 | 0 | 3
Growth | BACKEND | 18 | 2028-04-01 | 3 | 38062.5 | 15225 | 53287.5 | 0 | 0 | 0 | 3
Growth | BACKEND | 19 | 2028-05-01 | 3 | 38062.5 | 15225 | 53287.5 | 0 | 0 | 0 | 3
Growth | BACKEND | 20 | 2028-06-01 | 3 | 38062.5 | 15225 | 53287.5 | 0 | 0 | 0 | 3
Growth | BACKEND | 21 | 2028-07-01 | 3 | 38062.5 | 15225 | 53287.5 | 0 | 0 | 0 | 3
Growth | BACKEND | 22 | 2028-08-01 | 3 | 38062.5 | 15225 | 53287.5 | 0 | 0 | 0 | 3
Growth | BACKEND | 23 | 2028-09-01 | 3 | 38062.5 | 15225 | 53287.5 | 0 | 0 | 0 | 3
Growth | BACKEND | 24 | 2028-10-01 | 3 | 38062.5 | 15225 | 53287.5 | 0 | 0 | 0 | 3
Growth | BACKEND | 25 | 2028-11-01 | 3 | 39965.625 | 15986.25 | 55951.875 | 0 | 0 | 0 | 3
Growth | BACKEND | 26 | 2028-12-01 | 3 | 39965.625 | 15986.25 | 55951.875 | 0 | 0 | 0 | 3
Growth | BACKEND | 27 | 2029-01-01 | 3 | 39965.625 | 15986.25 | 55951.875 | 0 | 0 | 0 | 3
Growth | BACKEND | 28 | 2029-02-01 | 3 | 39965.625 | 15986.25 | 55951.875 | 0 | 0 | 0 | 3
Growth | BACKEND | 29 | 2029-03-01 | 3 | 39965.625 | 15986.25 | 55951.875 | 0 | 0 | 0 | 3
Growth | BACKEND | 30 | 2029-04-01 | 3 | 39965.625 | 15986.25 | 55951.875 | 0 | 0 | 0 | 3
Growth | BACKEND | 31 | 2029-05-01 | 4 | 53287.5 | 21315 | 74602.5 | 0 | 12000 | 3500 | 4
Growth | BACKEND | 32 | 2029-06-01 | 4 | 53287.5 | 21315 | 74602.5 | 0 | 0 | 0 | 4
Growth | BACKEND | 33 | 2029-07-01 | 4 | 53287.5 | 21315 | 74602.5 | 0 | 0 | 0 | 4
Growth | BACKEND | 34 | 2029-08-01 | 4 | 53287.5 | 21315 | 74602.5 | 0 | 0 | 0 | 4
Growth | BACKEND | 35 | 2029-09-01 | 4 | 53287.5 | 21315 | 74602.5 | 0 | 0 | 0 | 4
Growth | BACKEND | 36 | 2029-10-01 | 4 | 53287.5 | 21315 | 74602.5 | 0 | 0 | 0 | 4
Growth | BACKEND | 37 | 2029-11-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 38 | 2029-12-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 39 | 2030-01-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 40 | 2030-02-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 41 | 2030-03-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 42 | 2030-04-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 43 | 2030-05-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 44 | 2030-06-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 45 | 2030-07-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 46 | 2030-08-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 47 | 2030-09-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 48 | 2030-10-01 | 4 | 55951.875 | 22380.75 | 78332.625 | 0 | 0 | 0 | 4
Growth | BACKEND | 49 | 2030-11-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 50 | 2030-12-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 51 | 2031-01-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 52 | 2031-02-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 53 | 2031-03-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 54 | 2031-04-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 55 | 2031-05-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 56 | 2031-06-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 57 | 2031-07-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 58 | 2031-08-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 59 | 2031-09-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | BACKEND | 60 | 2031-10-01 | 4 | 58749.4688 | 23499.7875 | 82249.2563 | 0 | 0 | 0 | 4
Growth | FRONTEND | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | FRONTEND | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | FRONTEND | 3 | 2027-01-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 12000 | 3500 | 1
Growth | FRONTEND | 4 | 2027-02-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Growth | FRONTEND | 5 | 2027-03-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Growth | FRONTEND | 6 | 2027-04-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Growth | FRONTEND | 7 | 2027-05-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Growth | FRONTEND | 8 | 2027-06-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Growth | FRONTEND | 9 | 2027-07-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Growth | FRONTEND | 10 | 2027-08-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Growth | FRONTEND | 11 | 2027-09-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Growth | FRONTEND | 12 | 2027-10-01 | 1 | 11666.6667 | 4666.6667 | 16333.3333 | 0 | 0 | 0 | 1
Growth | FRONTEND | 13 | 2027-11-01 | 1 | 12250 | 4900 | 17150 | 0 | 0 | 0 | 1
Growth | FRONTEND | 14 | 2027-12-01 | 1 | 12250 | 4900 | 17150 | 0 | 0 | 0 | 1
Growth | FRONTEND | 15 | 2028-01-01 | 1 | 12250 | 4900 | 17150 | 0 | 0 | 0 | 1
Growth | FRONTEND | 16 | 2028-02-01 | 2 | 24500 | 9800 | 34300 | 0 | 12000 | 3500 | 2
Growth | FRONTEND | 17 | 2028-03-01 | 2 | 24500 | 9800 | 34300 | 0 | 0 | 0 | 2
Growth | FRONTEND | 18 | 2028-04-01 | 2 | 24500 | 9800 | 34300 | 0 | 0 | 0 | 2
Growth | FRONTEND | 19 | 2028-05-01 | 2 | 24500 | 9800 | 34300 | 0 | 0 | 0 | 2
Growth | FRONTEND | 20 | 2028-06-01 | 2 | 24500 | 9800 | 34300 | 0 | 0 | 0 | 2
Growth | FRONTEND | 21 | 2028-07-01 | 2 | 24500 | 9800 | 34300 | 0 | 0 | 0 | 2
Growth | FRONTEND | 22 | 2028-08-01 | 2 | 24500 | 9800 | 34300 | 0 | 0 | 0 | 2
Growth | FRONTEND | 23 | 2028-09-01 | 2 | 24500 | 9800 | 34300 | 0 | 0 | 0 | 2
Growth | FRONTEND | 24 | 2028-10-01 | 2 | 24500 | 9800 | 34300 | 0 | 0 | 0 | 2
Growth | FRONTEND | 25 | 2028-11-01 | 2 | 25725 | 10290 | 36015 | 0 | 0 | 0 | 2
Growth | FRONTEND | 26 | 2028-12-01 | 2 | 25725 | 10290 | 36015 | 0 | 0 | 0 | 2
Growth | FRONTEND | 27 | 2029-01-01 | 2 | 25725 | 10290 | 36015 | 0 | 0 | 0 | 2
Growth | FRONTEND | 28 | 2029-02-01 | 2 | 25725 | 10290 | 36015 | 0 | 0 | 0 | 2
Growth | FRONTEND | 29 | 2029-03-01 | 2 | 25725 | 10290 | 36015 | 0 | 0 | 0 | 2
Growth | FRONTEND | 30 | 2029-04-01 | 2 | 25725 | 10290 | 36015 | 0 | 0 | 0 | 2
Growth | FRONTEND | 31 | 2029-05-01 | 3 | 38587.5 | 15435 | 54022.5 | 0 | 12000 | 3500 | 3
Growth | FRONTEND | 32 | 2029-06-01 | 3 | 38587.5 | 15435 | 54022.5 | 0 | 0 | 0 | 3
Growth | FRONTEND | 33 | 2029-07-01 | 3 | 38587.5 | 15435 | 54022.5 | 0 | 0 | 0 | 3
Growth | FRONTEND | 34 | 2029-08-01 | 3 | 38587.5 | 15435 | 54022.5 | 0 | 0 | 0 | 3
Growth | FRONTEND | 35 | 2029-09-01 | 3 | 38587.5 | 15435 | 54022.5 | 0 | 0 | 0 | 3
Growth | FRONTEND | 36 | 2029-10-01 | 3 | 38587.5 | 15435 | 54022.5 | 0 | 0 | 0 | 3
Growth | FRONTEND | 37 | 2029-11-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 38 | 2029-12-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 39 | 2030-01-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 40 | 2030-02-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 41 | 2030-03-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 42 | 2030-04-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 43 | 2030-05-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 44 | 2030-06-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 45 | 2030-07-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 46 | 2030-08-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 47 | 2030-09-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 48 | 2030-10-01 | 3 | 40516.875 | 16206.75 | 56723.625 | 0 | 0 | 0 | 3
Growth | FRONTEND | 49 | 2030-11-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 50 | 2030-12-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 51 | 2031-01-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 52 | 2031-02-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 53 | 2031-03-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 54 | 2031-04-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 55 | 2031-05-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 56 | 2031-06-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 57 | 2031-07-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 58 | 2031-08-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 59 | 2031-09-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | FRONTEND | 60 | 2031-10-01 | 3 | 42542.7188 | 17017.0875 | 59559.8063 | 0 | 0 | 0 | 3
Growth | QA | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | QA | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | QA | 3 | 2027-01-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 6000 | 1750 | 1
Growth | QA | 4 | 2027-02-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Growth | QA | 5 | 2027-03-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Growth | QA | 6 | 2027-04-01 | 0.5 | 4583.3333 | 1833.3333 | 6416.6667 | 0 | 0 | 0 | 1
Growth | QA | 7 | 2027-05-01 | 1 | 9166.6667 | 3666.6667 | 12833.3333 | 0 | 6000 | 1750 | 1
Growth | QA | 8 | 2027-06-01 | 1 | 9166.6667 | 3666.6667 | 12833.3333 | 0 | 0 | 0 | 1
Growth | QA | 9 | 2027-07-01 | 1 | 9166.6667 | 3666.6667 | 12833.3333 | 0 | 0 | 0 | 1
Growth | QA | 10 | 2027-08-01 | 1 | 9166.6667 | 3666.6667 | 12833.3333 | 0 | 0 | 0 | 1
Growth | QA | 11 | 2027-09-01 | 1 | 9166.6667 | 3666.6667 | 12833.3333 | 0 | 0 | 0 | 1
Growth | QA | 12 | 2027-10-01 | 1 | 9166.6667 | 3666.6667 | 12833.3333 | 0 | 0 | 0 | 1
Growth | QA | 13 | 2027-11-01 | 1 | 9625 | 3850 | 13475 | 0 | 0 | 0 | 1
Growth | QA | 14 | 2027-12-01 | 1 | 9625 | 3850 | 13475 | 0 | 0 | 0 | 1
Growth | QA | 15 | 2028-01-01 | 1 | 9625 | 3850 | 13475 | 0 | 0 | 0 | 1
Growth | QA | 16 | 2028-02-01 | 2 | 19250 | 7700 | 26950 | 0 | 12000 | 3500 | 2
Growth | QA | 17 | 2028-03-01 | 2 | 19250 | 7700 | 26950 | 0 | 0 | 0 | 2
Growth | QA | 18 | 2028-04-01 | 2 | 19250 | 7700 | 26950 | 0 | 0 | 0 | 2
Growth | QA | 19 | 2028-05-01 | 2 | 19250 | 7700 | 26950 | 0 | 0 | 0 | 2
Growth | QA | 20 | 2028-06-01 | 2 | 19250 | 7700 | 26950 | 0 | 0 | 0 | 2
Growth | QA | 21 | 2028-07-01 | 2 | 19250 | 7700 | 26950 | 0 | 0 | 0 | 2
Growth | QA | 22 | 2028-08-01 | 2 | 19250 | 7700 | 26950 | 0 | 0 | 0 | 2
Growth | QA | 23 | 2028-09-01 | 2 | 19250 | 7700 | 26950 | 0 | 0 | 0 | 2
Growth | QA | 24 | 2028-10-01 | 2 | 19250 | 7700 | 26950 | 0 | 0 | 0 | 2
Growth | QA | 25 | 2028-11-01 | 2 | 20212.5 | 8085 | 28297.5 | 0 | 0 | 0 | 2
Growth | QA | 26 | 2028-12-01 | 2 | 20212.5 | 8085 | 28297.5 | 0 | 0 | 0 | 2
Growth | QA | 27 | 2029-01-01 | 2 | 20212.5 | 8085 | 28297.5 | 0 | 0 | 0 | 2
Growth | QA | 28 | 2029-02-01 | 2 | 20212.5 | 8085 | 28297.5 | 0 | 0 | 0 | 2
Growth | QA | 29 | 2029-03-01 | 2 | 20212.5 | 8085 | 28297.5 | 0 | 0 | 0 | 2
Growth | QA | 30 | 2029-04-01 | 2 | 20212.5 | 8085 | 28297.5 | 0 | 0 | 0 | 2
Growth | QA | 31 | 2029-05-01 | 3 | 30318.75 | 12127.5 | 42446.25 | 0 | 12000 | 3500 | 3
Growth | QA | 32 | 2029-06-01 | 3 | 30318.75 | 12127.5 | 42446.25 | 0 | 0 | 0 | 3
Growth | QA | 33 | 2029-07-01 | 3 | 30318.75 | 12127.5 | 42446.25 | 0 | 0 | 0 | 3
Growth | QA | 34 | 2029-08-01 | 3 | 30318.75 | 12127.5 | 42446.25 | 0 | 0 | 0 | 3
Growth | QA | 35 | 2029-09-01 | 3 | 30318.75 | 12127.5 | 42446.25 | 0 | 0 | 0 | 3
Growth | QA | 36 | 2029-10-01 | 3 | 30318.75 | 12127.5 | 42446.25 | 0 | 0 | 0 | 3
Growth | QA | 37 | 2029-11-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 38 | 2029-12-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 39 | 2030-01-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 40 | 2030-02-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 41 | 2030-03-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 42 | 2030-04-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 43 | 2030-05-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 44 | 2030-06-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 45 | 2030-07-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 46 | 2030-08-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 47 | 2030-09-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 48 | 2030-10-01 | 3 | 31834.6875 | 12733.875 | 44568.5625 | 0 | 0 | 0 | 3
Growth | QA | 49 | 2030-11-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 50 | 2030-12-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 51 | 2031-01-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 52 | 2031-02-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 53 | 2031-03-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 54 | 2031-04-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 55 | 2031-05-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 56 | 2031-06-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 57 | 2031-07-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 58 | 2031-08-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 59 | 2031-09-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | QA | 60 | 2031-10-01 | 3 | 33426.4219 | 13370.5688 | 46796.9906 | 0 | 0 | 0 | 3
Growth | OPS | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | OPS | 2 | 2026-12-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 1750 | 1
Growth | OPS | 3 | 2027-01-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 0 | 1
Growth | OPS | 4 | 2027-02-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 0 | 1
Growth | OPS | 5 | 2027-03-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 0 | 1
Growth | OPS | 6 | 2027-04-01 | 0.5 | 7916.6667 | 0 | 7916.6667 | 0 | 0 | 0 | 1
Growth | OPS | 7 | 2027-05-01 | 0.75 | 11875 | 0 | 11875 | 0 | 0 | 875 | 1
Growth | OPS | 8 | 2027-06-01 | 0.75 | 11875 | 0 | 11875 | 0 | 0 | 0 | 1
Growth | OPS | 9 | 2027-07-01 | 0.75 | 11875 | 0 | 11875 | 0 | 0 | 0 | 1
Growth | OPS | 10 | 2027-08-01 | 0.75 | 11875 | 0 | 11875 | 0 | 0 | 0 | 1
Growth | OPS | 11 | 2027-09-01 | 0.75 | 11875 | 0 | 11875 | 0 | 0 | 0 | 1
Growth | OPS | 12 | 2027-10-01 | 0.75 | 11875 | 0 | 11875 | 0 | 0 | 0 | 1
Growth | OPS | 13 | 2027-11-01 | 0.75 | 12468.75 | 0 | 12468.75 | 0 | 0 | 0 | 1
Growth | OPS | 14 | 2027-12-01 | 0.75 | 12468.75 | 0 | 12468.75 | 0 | 0 | 0 | 1
Growth | OPS | 15 | 2028-01-01 | 0.75 | 12468.75 | 0 | 12468.75 | 0 | 0 | 0 | 1
Growth | OPS | 16 | 2028-02-01 | 1 | 16625 | 0 | 16625 | 0 | 0 | 875 | 1
Growth | OPS | 17 | 2028-03-01 | 1 | 16625 | 0 | 16625 | 0 | 0 | 0 | 1
Growth | OPS | 18 | 2028-04-01 | 1 | 16625 | 0 | 16625 | 0 | 0 | 0 | 1
Growth | OPS | 19 | 2028-05-01 | 1 | 16625 | 0 | 16625 | 0 | 0 | 0 | 1
Growth | OPS | 20 | 2028-06-01 | 1 | 16625 | 0 | 16625 | 0 | 0 | 0 | 1
Growth | OPS | 21 | 2028-07-01 | 1 | 16625 | 0 | 16625 | 0 | 0 | 0 | 1
Growth | OPS | 22 | 2028-08-01 | 1 | 16625 | 0 | 16625 | 0 | 0 | 0 | 1
Growth | OPS | 23 | 2028-09-01 | 1 | 16625 | 0 | 16625 | 0 | 0 | 0 | 1
Growth | OPS | 24 | 2028-10-01 | 1 | 16625 | 0 | 16625 | 0 | 0 | 0 | 1
Growth | OPS | 25 | 2028-11-01 | 1 | 17456.25 | 0 | 17456.25 | 0 | 0 | 0 | 1
Growth | OPS | 26 | 2028-12-01 | 1 | 17456.25 | 0 | 17456.25 | 0 | 0 | 0 | 1
Growth | OPS | 27 | 2029-01-01 | 1 | 17456.25 | 0 | 17456.25 | 0 | 0 | 0 | 1
Growth | OPS | 28 | 2029-02-01 | 1 | 17456.25 | 0 | 17456.25 | 0 | 0 | 0 | 1
Growth | OPS | 29 | 2029-03-01 | 1 | 17456.25 | 0 | 17456.25 | 0 | 0 | 0 | 1
Growth | OPS | 30 | 2029-04-01 | 1 | 17456.25 | 0 | 17456.25 | 0 | 0 | 0 | 1
Growth | OPS | 31 | 2029-05-01 | 2 | 34912.5 | 0 | 34912.5 | 0 | 0 | 3500 | 2
Growth | OPS | 32 | 2029-06-01 | 2 | 34912.5 | 0 | 34912.5 | 0 | 0 | 0 | 2
Growth | OPS | 33 | 2029-07-01 | 2 | 34912.5 | 0 | 34912.5 | 0 | 0 | 0 | 2
Growth | OPS | 34 | 2029-08-01 | 2 | 34912.5 | 0 | 34912.5 | 0 | 0 | 0 | 2
Growth | OPS | 35 | 2029-09-01 | 2 | 34912.5 | 0 | 34912.5 | 0 | 0 | 0 | 2
Growth | OPS | 36 | 2029-10-01 | 2 | 34912.5 | 0 | 34912.5 | 0 | 0 | 0 | 2
Growth | OPS | 37 | 2029-11-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 38 | 2029-12-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 39 | 2030-01-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 40 | 2030-02-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 41 | 2030-03-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 42 | 2030-04-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 43 | 2030-05-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 44 | 2030-06-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 45 | 2030-07-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 46 | 2030-08-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 47 | 2030-09-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 48 | 2030-10-01 | 2 | 36658.125 | 0 | 36658.125 | 0 | 0 | 0 | 2
Growth | OPS | 49 | 2030-11-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 50 | 2030-12-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 51 | 2031-01-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 52 | 2031-02-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 53 | 2031-03-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 54 | 2031-04-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 55 | 2031-05-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 56 | 2031-06-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 57 | 2031-07-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 58 | 2031-08-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 59 | 2031-09-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | OPS | 60 | 2031-10-01 | 2 | 38491.0312 | 0 | 38491.0312 | 0 | 0 | 0 | 2
Growth | DESIGN | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | DESIGN | 2 | 2026-12-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 1750 | 1
Growth | DESIGN | 3 | 2027-01-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 4 | 2027-02-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 5 | 2027-03-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 6 | 2027-04-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 7 | 2027-05-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 8 | 2027-06-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 9 | 2027-07-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 10 | 2027-08-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 11 | 2027-09-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 12 | 2027-10-01 | 0.5 | 5416.6667 | 0 | 5416.6667 | 0 | 0 | 0 | 1
Growth | DESIGN | 13 | 2027-11-01 | 0.5 | 5687.5 | 0 | 5687.5 | 0 | 0 | 0 | 1
Growth | DESIGN | 14 | 2027-12-01 | 0.5 | 5687.5 | 0 | 5687.5 | 0 | 0 | 0 | 1
Growth | DESIGN | 15 | 2028-01-01 | 0.5 | 5687.5 | 0 | 5687.5 | 0 | 0 | 0 | 1
Growth | DESIGN | 16 | 2028-02-01 | 0.75 | 8531.25 | 0 | 8531.25 | 0 | 0 | 875 | 1
Growth | DESIGN | 17 | 2028-03-01 | 0.75 | 8531.25 | 0 | 8531.25 | 0 | 0 | 0 | 1
Growth | DESIGN | 18 | 2028-04-01 | 0.75 | 8531.25 | 0 | 8531.25 | 0 | 0 | 0 | 1
Growth | DESIGN | 19 | 2028-05-01 | 0.75 | 8531.25 | 0 | 8531.25 | 0 | 0 | 0 | 1
Growth | DESIGN | 20 | 2028-06-01 | 0.75 | 8531.25 | 0 | 8531.25 | 0 | 0 | 0 | 1
Growth | DESIGN | 21 | 2028-07-01 | 0.75 | 8531.25 | 0 | 8531.25 | 0 | 0 | 0 | 1
Growth | DESIGN | 22 | 2028-08-01 | 0.75 | 8531.25 | 0 | 8531.25 | 0 | 0 | 0 | 1
Growth | DESIGN | 23 | 2028-09-01 | 0.75 | 8531.25 | 0 | 8531.25 | 0 | 0 | 0 | 1
Growth | DESIGN | 24 | 2028-10-01 | 0.75 | 8531.25 | 0 | 8531.25 | 0 | 0 | 0 | 1
Growth | DESIGN | 25 | 2028-11-01 | 0.75 | 8957.8125 | 0 | 8957.8125 | 0 | 0 | 0 | 1
Growth | DESIGN | 26 | 2028-12-01 | 0.75 | 8957.8125 | 0 | 8957.8125 | 0 | 0 | 0 | 1
Growth | DESIGN | 27 | 2029-01-01 | 0.75 | 8957.8125 | 0 | 8957.8125 | 0 | 0 | 0 | 1
Growth | DESIGN | 28 | 2029-02-01 | 0.75 | 8957.8125 | 0 | 8957.8125 | 0 | 0 | 0 | 1
Growth | DESIGN | 29 | 2029-03-01 | 0.75 | 8957.8125 | 0 | 8957.8125 | 0 | 0 | 0 | 1
Growth | DESIGN | 30 | 2029-04-01 | 0.75 | 8957.8125 | 0 | 8957.8125 | 0 | 0 | 0 | 1
Growth | DESIGN | 31 | 2029-05-01 | 1 | 11943.75 | 0 | 11943.75 | 0 | 0 | 875 | 1
Growth | DESIGN | 32 | 2029-06-01 | 1 | 11943.75 | 0 | 11943.75 | 0 | 0 | 0 | 1
Growth | DESIGN | 33 | 2029-07-01 | 1 | 11943.75 | 0 | 11943.75 | 0 | 0 | 0 | 1
Growth | DESIGN | 34 | 2029-08-01 | 1 | 11943.75 | 0 | 11943.75 | 0 | 0 | 0 | 1
Growth | DESIGN | 35 | 2029-09-01 | 1 | 11943.75 | 0 | 11943.75 | 0 | 0 | 0 | 1
Growth | DESIGN | 36 | 2029-10-01 | 1 | 11943.75 | 0 | 11943.75 | 0 | 0 | 0 | 1
Growth | DESIGN | 37 | 2029-11-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 38 | 2029-12-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 39 | 2030-01-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 40 | 2030-02-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 41 | 2030-03-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 42 | 2030-04-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 43 | 2030-05-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 44 | 2030-06-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 45 | 2030-07-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 46 | 2030-08-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 47 | 2030-09-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 48 | 2030-10-01 | 1 | 12540.9375 | 0 | 12540.9375 | 0 | 0 | 0 | 1
Growth | DESIGN | 49 | 2030-11-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 50 | 2030-12-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 51 | 2031-01-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 52 | 2031-02-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 53 | 2031-03-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 54 | 2031-04-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 55 | 2031-05-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 56 | 2031-06-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 57 | 2031-07-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 58 | 2031-08-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 59 | 2031-09-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | DESIGN | 60 | 2031-10-01 | 1 | 13167.9844 | 0 | 13167.9844 | 0 | 0 | 0 | 1
Growth | VALIDATION | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | VALIDATION | 2 | 2026-12-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 875 | 1
Growth | VALIDATION | 3 | 2027-01-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 0 | 1
Growth | VALIDATION | 4 | 2027-02-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 0 | 1
Growth | VALIDATION | 5 | 2027-03-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 0 | 1
Growth | VALIDATION | 6 | 2027-04-01 | 0.25 | 4166.6667 | 0 | 4166.6667 | 0 | 0 | 0 | 1
Growth | VALIDATION | 7 | 2027-05-01 | 0.5 | 8333.3333 | 0 | 8333.3333 | 0 | 0 | 875 | 1
Growth | VALIDATION | 8 | 2027-06-01 | 0.5 | 8333.3333 | 0 | 8333.3333 | 0 | 0 | 0 | 1
Growth | VALIDATION | 9 | 2027-07-01 | 0.5 | 8333.3333 | 0 | 8333.3333 | 0 | 0 | 0 | 1
Growth | VALIDATION | 10 | 2027-08-01 | 0.5 | 8333.3333 | 0 | 8333.3333 | 0 | 0 | 0 | 1
Growth | VALIDATION | 11 | 2027-09-01 | 0.5 | 8333.3333 | 0 | 8333.3333 | 0 | 0 | 0 | 1
Growth | VALIDATION | 12 | 2027-10-01 | 0.5 | 8333.3333 | 0 | 8333.3333 | 0 | 0 | 0 | 1
Growth | VALIDATION | 13 | 2027-11-01 | 0.5 | 8750 | 0 | 8750 | 0 | 0 | 0 | 1
Growth | VALIDATION | 14 | 2027-12-01 | 0.5 | 8750 | 0 | 8750 | 0 | 0 | 0 | 1
Growth | VALIDATION | 15 | 2028-01-01 | 0.5 | 8750 | 0 | 8750 | 0 | 0 | 0 | 1
Growth | VALIDATION | 16 | 2028-02-01 | 0.75 | 13125 | 0 | 13125 | 0 | 0 | 875 | 1
Growth | VALIDATION | 17 | 2028-03-01 | 0.75 | 13125 | 0 | 13125 | 0 | 0 | 0 | 1
Growth | VALIDATION | 18 | 2028-04-01 | 0.75 | 13125 | 0 | 13125 | 0 | 0 | 0 | 1
Growth | VALIDATION | 19 | 2028-05-01 | 0.75 | 13125 | 0 | 13125 | 0 | 0 | 0 | 1
Growth | VALIDATION | 20 | 2028-06-01 | 0.75 | 13125 | 0 | 13125 | 0 | 0 | 0 | 1
Growth | VALIDATION | 21 | 2028-07-01 | 0.75 | 13125 | 0 | 13125 | 0 | 0 | 0 | 1
Growth | VALIDATION | 22 | 2028-08-01 | 0.75 | 13125 | 0 | 13125 | 0 | 0 | 0 | 1
Growth | VALIDATION | 23 | 2028-09-01 | 0.75 | 13125 | 0 | 13125 | 0 | 0 | 0 | 1
Growth | VALIDATION | 24 | 2028-10-01 | 0.75 | 13125 | 0 | 13125 | 0 | 0 | 0 | 1
Growth | VALIDATION | 25 | 2028-11-01 | 0.75 | 13781.25 | 0 | 13781.25 | 0 | 0 | 0 | 1
Growth | VALIDATION | 26 | 2028-12-01 | 0.75 | 13781.25 | 0 | 13781.25 | 0 | 0 | 0 | 1
Growth | VALIDATION | 27 | 2029-01-01 | 0.75 | 13781.25 | 0 | 13781.25 | 0 | 0 | 0 | 1
Growth | VALIDATION | 28 | 2029-02-01 | 0.75 | 13781.25 | 0 | 13781.25 | 0 | 0 | 0 | 1
Growth | VALIDATION | 29 | 2029-03-01 | 0.75 | 13781.25 | 0 | 13781.25 | 0 | 0 | 0 | 1
Growth | VALIDATION | 30 | 2029-04-01 | 0.75 | 13781.25 | 0 | 13781.25 | 0 | 0 | 0 | 1
Growth | VALIDATION | 31 | 2029-05-01 | 1 | 18375 | 0 | 18375 | 0 | 0 | 875 | 1
Growth | VALIDATION | 32 | 2029-06-01 | 1 | 18375 | 0 | 18375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 33 | 2029-07-01 | 1 | 18375 | 0 | 18375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 34 | 2029-08-01 | 1 | 18375 | 0 | 18375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 35 | 2029-09-01 | 1 | 18375 | 0 | 18375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 36 | 2029-10-01 | 1 | 18375 | 0 | 18375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 37 | 2029-11-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 38 | 2029-12-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 39 | 2030-01-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 40 | 2030-02-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 41 | 2030-03-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 42 | 2030-04-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 43 | 2030-05-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 44 | 2030-06-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 45 | 2030-07-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 46 | 2030-08-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 47 | 2030-09-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 48 | 2030-10-01 | 1 | 19293.75 | 0 | 19293.75 | 0 | 0 | 0 | 1
Growth | VALIDATION | 49 | 2030-11-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 50 | 2030-12-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 51 | 2031-01-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 52 | 2031-02-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 53 | 2031-03-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 54 | 2031-04-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 55 | 2031-05-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 56 | 2031-06-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 57 | 2031-07-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 58 | 2031-08-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 59 | 2031-09-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | VALIDATION | 60 | 2031-10-01 | 1 | 20258.4375 | 0 | 20258.4375 | 0 | 0 | 0 | 1
Growth | SUCCESS | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SUCCESS | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SUCCESS | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SUCCESS | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SUCCESS | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SUCCESS | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SUCCESS | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SUCCESS | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SUCCESS | 9 | 2027-07-01 | 1 | 7500 | 3000 | 10500 | 0 | 12000 | 3500 | 1
Growth | SUCCESS | 10 | 2027-08-01 | 1 | 7500 | 3000 | 10500 | 0 | 0 | 0 | 1
Growth | SUCCESS | 11 | 2027-09-01 | 1 | 7500 | 3000 | 10500 | 0 | 0 | 0 | 1
Growth | SUCCESS | 12 | 2027-10-01 | 1 | 7500 | 3000 | 10500 | 0 | 0 | 0 | 1
Growth | SUCCESS | 13 | 2027-11-01 | 1 | 7875 | 3150 | 11025 | 0 | 0 | 0 | 1
Growth | SUCCESS | 14 | 2027-12-01 | 1 | 7875 | 3150 | 11025 | 0 | 0 | 0 | 1
Growth | SUCCESS | 15 | 2028-01-01 | 1 | 7875 | 3150 | 11025 | 0 | 0 | 0 | 1
Growth | SUCCESS | 16 | 2028-02-01 | 2 | 15750 | 6300 | 22050 | 0 | 12000 | 3500 | 2
Growth | SUCCESS | 17 | 2028-03-01 | 2 | 15750 | 6300 | 22050 | 0 | 0 | 0 | 2
Growth | SUCCESS | 18 | 2028-04-01 | 2 | 15750 | 6300 | 22050 | 0 | 0 | 0 | 2
Growth | SUCCESS | 19 | 2028-05-01 | 2 | 15750 | 6300 | 22050 | 0 | 0 | 0 | 2
Growth | SUCCESS | 20 | 2028-06-01 | 2 | 15750 | 6300 | 22050 | 0 | 0 | 0 | 2
Growth | SUCCESS | 21 | 2028-07-01 | 2 | 15750 | 6300 | 22050 | 0 | 0 | 0 | 2
Growth | SUCCESS | 22 | 2028-08-01 | 2 | 15750 | 6300 | 22050 | 0 | 0 | 0 | 2
Growth | SUCCESS | 23 | 2028-09-01 | 2 | 15750 | 6300 | 22050 | 0 | 0 | 0 | 2
Growth | SUCCESS | 24 | 2028-10-01 | 2 | 15750 | 6300 | 22050 | 0 | 0 | 0 | 2
Growth | SUCCESS | 25 | 2028-11-01 | 2 | 16537.5 | 6615 | 23152.5 | 0 | 0 | 0 | 2
Growth | SUCCESS | 26 | 2028-12-01 | 2 | 16537.5 | 6615 | 23152.5 | 0 | 0 | 0 | 2
Growth | SUCCESS | 27 | 2029-01-01 | 2 | 16537.5 | 6615 | 23152.5 | 0 | 0 | 0 | 2
Growth | SUCCESS | 28 | 2029-02-01 | 2 | 16537.5 | 6615 | 23152.5 | 0 | 0 | 0 | 2
Growth | SUCCESS | 29 | 2029-03-01 | 2 | 16537.5 | 6615 | 23152.5 | 0 | 0 | 0 | 2
Growth | SUCCESS | 30 | 2029-04-01 | 2 | 16537.5 | 6615 | 23152.5 | 0 | 0 | 0 | 2
Growth | SUCCESS | 31 | 2029-05-01 | 4 | 33075 | 13230 | 46305 | 0 | 24000 | 7000 | 4
Growth | SUCCESS | 32 | 2029-06-01 | 4 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 4
Growth | SUCCESS | 33 | 2029-07-01 | 4 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 4
Growth | SUCCESS | 34 | 2029-08-01 | 4 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 4
Growth | SUCCESS | 35 | 2029-09-01 | 4 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 4
Growth | SUCCESS | 36 | 2029-10-01 | 4 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 4
Growth | SUCCESS | 37 | 2029-11-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 38 | 2029-12-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 39 | 2030-01-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 40 | 2030-02-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 41 | 2030-03-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 42 | 2030-04-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 43 | 2030-05-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 44 | 2030-06-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 45 | 2030-07-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 46 | 2030-08-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 47 | 2030-09-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 48 | 2030-10-01 | 4 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 4
Growth | SUCCESS | 49 | 2030-11-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 50 | 2030-12-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 51 | 2031-01-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 52 | 2031-02-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 53 | 2031-03-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 54 | 2031-04-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 55 | 2031-05-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 56 | 2031-06-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 57 | 2031-07-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 58 | 2031-08-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 59 | 2031-09-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SUCCESS | 60 | 2031-10-01 | 4 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 4
Growth | SALES | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | SALES | 16 | 2028-02-01 | 1 | 10500 | 4200 | 14700 | 0 | 12000 | 3500 | 1
Growth | SALES | 17 | 2028-03-01 | 1 | 10500 | 4200 | 14700 | 0 | 0 | 0 | 1
Growth | SALES | 18 | 2028-04-01 | 1 | 10500 | 4200 | 14700 | 0 | 0 | 0 | 1
Growth | SALES | 19 | 2028-05-01 | 1 | 10500 | 4200 | 14700 | 0 | 0 | 0 | 1
Growth | SALES | 20 | 2028-06-01 | 1 | 10500 | 4200 | 14700 | 0 | 0 | 0 | 1
Growth | SALES | 21 | 2028-07-01 | 1 | 10500 | 4200 | 14700 | 0 | 0 | 0 | 1
Growth | SALES | 22 | 2028-08-01 | 1 | 10500 | 4200 | 14700 | 0 | 0 | 0 | 1
Growth | SALES | 23 | 2028-09-01 | 1 | 10500 | 4200 | 14700 | 0 | 0 | 0 | 1
Growth | SALES | 24 | 2028-10-01 | 1 | 10500 | 4200 | 14700 | 0 | 0 | 0 | 1
Growth | SALES | 25 | 2028-11-01 | 1 | 11025 | 4410 | 15435 | 0 | 0 | 0 | 1
Growth | SALES | 26 | 2028-12-01 | 1 | 11025 | 4410 | 15435 | 0 | 0 | 0 | 1
Growth | SALES | 27 | 2029-01-01 | 1 | 11025 | 4410 | 15435 | 0 | 0 | 0 | 1
Growth | SALES | 28 | 2029-02-01 | 1 | 11025 | 4410 | 15435 | 0 | 0 | 0 | 1
Growth | SALES | 29 | 2029-03-01 | 1 | 11025 | 4410 | 15435 | 0 | 0 | 0 | 1
Growth | SALES | 30 | 2029-04-01 | 1 | 11025 | 4410 | 15435 | 0 | 0 | 0 | 1
Growth | SALES | 31 | 2029-05-01 | 3 | 33075 | 13230 | 46305 | 0 | 24000 | 7000 | 3
Growth | SALES | 32 | 2029-06-01 | 3 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 3
Growth | SALES | 33 | 2029-07-01 | 3 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 3
Growth | SALES | 34 | 2029-08-01 | 3 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 3
Growth | SALES | 35 | 2029-09-01 | 3 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 3
Growth | SALES | 36 | 2029-10-01 | 3 | 33075 | 13230 | 46305 | 0 | 0 | 0 | 3
Growth | SALES | 37 | 2029-11-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 38 | 2029-12-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 39 | 2030-01-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 40 | 2030-02-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 41 | 2030-03-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 42 | 2030-04-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 43 | 2030-05-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 44 | 2030-06-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 45 | 2030-07-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 46 | 2030-08-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 47 | 2030-09-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 48 | 2030-10-01 | 3 | 34728.75 | 13891.5 | 48620.25 | 0 | 0 | 0 | 3
Growth | SALES | 49 | 2030-11-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 50 | 2030-12-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 51 | 2031-01-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 52 | 2031-02-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 53 | 2031-03-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 54 | 2031-04-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 55 | 2031-05-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 56 | 2031-06-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 57 | 2031-07-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 58 | 2031-08-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 59 | 2031-09-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | SALES | 60 | 2031-10-01 | 3 | 36465.1875 | 14586.075 | 51051.2625 | 0 | 0 | 0 | 3
Growth | AI-ENG | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | AI-ENG | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-PM | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 16 | 2028-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 17 | 2028-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 18 | 2028-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 19 | 2028-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 20 | 2028-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 21 | 2028-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 22 | 2028-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 23 | 2028-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 24 | 2028-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 25 | 2028-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 26 | 2028-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 27 | 2029-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 28 | 2029-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 29 | 2029-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 30 | 2029-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 31 | 2029-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 32 | 2029-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 33 | 2029-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 34 | 2029-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 35 | 2029-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 36 | 2029-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 37 | 2029-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 38 | 2029-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 39 | 2030-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 40 | 2030-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 41 | 2030-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 42 | 2030-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 43 | 2030-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 44 | 2030-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 45 | 2030-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 46 | 2030-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 47 | 2030-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 48 | 2030-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 49 | 2030-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 50 | 2030-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 51 | 2031-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 52 | 2031-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 53 | 2031-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 54 | 2031-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 55 | 2031-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 56 | 2031-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 57 | 2031-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 58 | 2031-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 59 | 2031-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Growth | CTMS-ENG | 60 | 2031-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Date = EDATE('Start Here'!$B6,[Month]-1)

## Monthly Lean
Lean ¦ 60-month financial model | [43 empty] | Lean
Expected-value cohorts, monthly revenue recognized = active organizations × ARPA; ARR = exit-month revenue ×12, never annual revenue. Spend includes contingency; cash excludes taxes, financing fees and receivables timing.
← Start Here
Month | Date | New customers | Active customers | Users | API requests M | Storage GB | Logs GB | Total FTE | Headcount slots | Staff cash | Recruiting | Equipment | INFRA | TOOLS | LEGAL | SECURITY | COMPLIANCE | INSURANCE | ACCOUNTING | SUPPORT | MARKETING | ONBOARD | AI | CTMS | Vendor total | Contingency | Payment fees | Total spend | Monthly revenue | Exit ARR | Net burn | Financing | Opening cash | Closing cash | Cumulative spend | Funding gap | Cash if zero revenue | Unresolved vendor cash | Optional vendor cash | Unpaid founder economic | Cumulative net need | Cost-only burn | Negative flag
1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 1.75 | 2 | 19250 | 5000 | 4375 | 1250 | 98 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 1948 | 3057.3 | 0 | 33630.3 | 0 | 0 | 33630.3 | 0 | 500000 | 466369.7 | 33630.3 | 0 | 466369.7 | 1850 | 0 | 9375 | 33630.3 | 33630.3 | 0
2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2.15 | 5 | 24916.6667 | 0 | 1000 | 1250 | 147 | 20000 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 21997 | 4791.3667 | 0 | 52705.0333 | 0 | 0 | 52705.0333 | 0 | 466369.7 | 413664.6667 | 86335.3333 | 0 | 413664.6667 | 21850 | 0 | 9375 | 86335.3333 | 52705.0333 | 0
3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2.15 | 5 | 24916.6667 | 0 | 0 | 1250 | 147 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 1997 | 2691.3667 | 0 | 29605.0333 | 0 | 0 | 29605.0333 | 0 | 413664.6667 | 384059.6333 | 115940.3667 | 0 | 384059.6333 | 1850 | 0 | 9375 | 115940.3667 | 29605.0333 | 0
4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2.65 | 6 | 33375 | 2500 | 1250 | 1250 | 147 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 1997 | 3912.2 | 0 | 43034.2 | 0 | 0 | 43034.2 | 0 | 384059.6333 | 341025.4333 | 158974.5667 | 0 | 341025.4333 | 1850 | 0 | 9375 | 158974.5667 | 43034.2 | 0
5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9 | 7 | 36583.3333 | 1250 | 625 | 1250 | 147 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 1997 | 4045.5333 | 0 | 44500.8667 | 0 | 0 | 44500.8667 | 0 | 341025.4333 | 296524.5667 | 203475.4333 | 0 | 296524.5667 | 1850 | 0 | 9375 | 203475.4333 | 44500.8667 | 0
6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2.9 | 7 | 36583.3333 | 0 | 0 | 1250 | 147 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 1997 | 3858.0333 | 0 | 42438.3667 | 0 | 0 | 42438.3667 | 0 | 296524.5667 | 254086.2 | 245913.8 | 0 | 254086.2 | 1850 | 0 | 9375 | 245913.8 | 42438.3667 | 0
7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 53812.5 | 5000 | 2750 | 1250 | 196 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2046 | 6360.85 | 0 | 69969.35 | 0 | 0 | 69969.35 | 0 | 254086.2 | 184116.85 | 315883.15 | 0 | 184116.85 | 1850 | 0 | 9375 | 315883.15 | 69969.35 | 0
8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 53812.5 | 0 | 0 | 1250 | 196 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2046 | 5585.85 | 0 | 61444.35 | 0 | 0 | 61444.35 | 0 | 184116.85 | 122672.5 | 377327.5 | 0 | 122672.5 | 1850 | 0 | 9375 | 377327.5 | 61444.35 | 0
9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 53812.5 | 0 | 0 | 1250 | 196 | 0 | 0 | 0 | 12000 | 600 | 100 | 0 | 0 | 0 | 0 | 14146 | 6795.85 | 0 | 74754.35 | 0 | 0 | 74754.35 | 0 | 122672.5 | 47918.15 | 452081.85 | 0 | 47918.15 | 13850 | 0 | 9375 | 452081.85 | 74754.35 | 0
10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 53812.5 | 0 | 0 | 1250 | 196 | 0 | 18000 | 0 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 20146 | 7395.85 | 0 | 81354.35 | 0 | 0 | 81354.35 | 0 | 47918.15 | -33436.2 | 533436.2 | 33436.2 | -33436.2 | 19850 | 0 | 9375 | 533436.2 | 81354.35 | 1
11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4 | 8 | 53812.5 | 0 | 0 | 1250 | 196 | 0 | 0 | 15000 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 17146 | 7095.85 | 0 | 78054.35 | 0 | 0 | 78054.35 | 0 | -33436.2 | -111490.55 | 611490.55 | 111490.55 | -111490.55 | 16850 | 0 | 9375 | 611490.55 | 78054.35 | 1
12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.25 | 9 | 56437.5 | 1250 | 625 | 1250 | 245 | 0 | 0 | 0 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 2195 | 6050.75 | 0 | 66558.25 | 0 | 0 | 66558.25 | 0 | -111490.55 | -178048.8 | 678048.8 | 178048.8 | -178048.8 | 1850 | 0 | 9375 | 678048.8 | 66558.25 | 1
13 | 2027-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.25 | 9 | 58130.625 | 0 | 0 | 1287.5 | 252.35 | 0 | 0 | 0 | 0 | 618 | 103 | 0 | 0 | 0 | 0 | 2260.85 | 6039.1475 | 0 | 66430.6225 | 0 | 0 | 66430.6225 | 1000000 | -178048.8 | 755520.5775 | 744479.4225 | 0 | 755520.5775 | 1905.5 | 0 | 9656.25 | 744479.4225 | 66430.6225 | 0
14 | 2027-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.25 | 9 | 58130.625 | 0 | 0 | 1287.5 | 252.35 | 12360 | 0 | 0 | 0 | 618 | 103 | 0 | 0 | 0 | 0 | 14620.85 | 7275.1475 | 0 | 80026.6225 | 0 | 0 | 80026.6225 | 0 | 755520.5775 | 675493.955 | 824506.045 | 0 | 675493.955 | 14265.5 | 0 | 9656.25 | 824506.045 | 80026.6225 | 0
15 | 2028-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.25 | 9 | 58130.625 | 0 | 0 | 1287.5 | 252.35 | 0 | 0 | 0 | 0 | 618 | 103 | 0 | 0 | 0 | 0 | 2260.85 | 6039.1475 | 0 | 66430.6225 | 0 | 0 | 66430.6225 | 0 | 675493.955 | 609063.3325 | 890936.6675 | 0 | 609063.3325 | 1905.5 | 0 | 9656.25 | 890936.6675 | 66430.6225 | 0
16 | 2028-02-01 | 0.5 | 0.5 | 4 | 0.012 | 1 | 0.25 | 5.25 | 9 | 72958.3333 | 5000 | 2625 | 1289.3128 | 302.82 | 0 | 0 | 0 | 0 | 618 | 103 | 38.625 | 154.5 | 0 | 0 | 2506.2578 | 8308.9591 | 7.5 | 91406.0502 | 250 | 3000 | 91156.0502 | 0 | 609063.3325 | 517907.2823 | 982342.7177 | 0 | 517657.2823 | 1905.5 | 0 | 9656.25 | 982092.7177 | 91406.0502 | 0
17 | 2028-03-01 | 0.5 | 0.9925 | 7.94 | 0.02382 | 1.985 | 0.49625 | 5.25 | 9 | 72958.3333 | 0 | 0 | 1291.0984 | 302.82 | 0 | 0 | 0 | 0 | 618 | 103 | 76.6706 | 154.5 | 0 | 0 | 2546.089 | 7550.4422 | 14.8875 | 83069.7521 | 496.25 | 5955 | 82573.5021 | 0 | 517907.2823 | 435333.7802 | 1065412.4698 | 0 | 434587.5302 | 1905.5 | 0 | 9656.25 | 1064666.2198 | 83069.7521 | 0
18 | 2028-04-01 | 0.5 | 1.4776 | 11.8209 | 0.035463 | 2.9552 | 0.73881 | 5.25 | 9 | 72958.3333 | 0 | 0 | 1292.8572 | 302.82 | 0 | 0 | 0 | 0 | 618 | 103 | 114.1456 | 154.5 | 0 | 0 | 2585.3228 | 7554.3656 | 22.1642 | 83120.1859 | 738.8062 | 8865.675 | 82381.3797 | 0 | 435333.7802 | 352952.4005 | 1148532.6558 | 0 | 351467.3442 | 1905.5 | 0 | 9656.25 | 1147047.5995 | 83120.1859 | 0
19 | 2028-05-01 | 0.5 | 1.9554 | 15.6436 | 0.046931 | 3.9109 | 0.97772 | 5.25 | 9 | 72958.3333 | 0 | 0 | 1294.5897 | 302.82 | 0 | 0 | 0 | 0 | 618 | 103 | 151.0584 | 154.5 | 0 | 0 | 2623.9681 | 7558.2301 | 29.3317 | 83169.8633 | 977.7242 | 11732.6899 | 82192.1391 | 0 | 352952.4005 | 270760.2614 | 1231702.519 | 0 | 268297.481 | 1905.5 | 0 | 9656.25 | 1229239.7386 | 83169.8633 | 0
20 | 2028-06-01 | 0.5 | 2.4261 | 19.4089 | 0.058227 | 4.8522 | 1.2131 | 5.25 | 9 | 72958.3333 | 0 | 0 | 1296.2961 | 302.82 | 0 | 0 | 0 | 0 | 618 | 103 | 187.4175 | 154.5 | 0 | 0 | 2662.0336 | 7562.0367 | 36.3917 | 83218.7954 | 1213.0583 | 14556.6995 | 82005.7371 | 0 | 270760.2614 | 188754.5243 | 1314921.3144 | 0 | 185078.6856 | 1905.5 | 0 | 9656.25 | 1311245.4757 | 83218.7954 | 0
21 | 2028-07-01 | 0.5 | 2.8897 | 23.1178 | 0.069353 | 5.7794 | 1.4449 | 5.25 | 9 | 72958.3333 | 0 | 0 | 1297.977 | 302.82 | 0 | 0 | 0 | 12360 | 618 | 103 | 223.2312 | 154.5 | 0 | 0 | 15059.5282 | 8801.7862 | 43.3459 | 96862.9936 | 1444.8624 | 17338.349 | 95418.1312 | 0 | 188754.5243 | 93336.3931 | 1411784.308 | 0 | 88215.692 | 14265.5 | 0 | 9656.25 | 1406663.6069 | 96862.9936 | 0
22 | 2028-08-01 | 0.5 | 3.3464 | 26.771 | 0.080313 | 6.6928 | 1.6732 | 5.25 | 9 | 72958.3333 | 0 | 0 | 1299.6326 | 302.82 | 0 | 18540 | 0 | 0 | 618 | 103 | 258.5078 | 154.5 | 0 | 0 | 21276.4604 | 9423.4794 | 50.1957 | 103708.4688 | 1673.1895 | 20078.2738 | 102035.2793 | 0 | 93336.3931 | -8698.8862 | 1515492.7768 | 8698.8862 | -15492.7768 | 20445.5 | 0 | 9656.25 | 1508698.8862 | 103708.4688 | 1
23 | 2028-09-01 | 0.5 | 3.7962 | 30.3695 | 0.091108 | 7.5924 | 1.8981 | 5.25 | 9 | 72958.3333 | 0 | 0 | 1301.2634 | 302.82 | 0 | 0 | 15450 | 0 | 618 | 103 | 293.2552 | 154.5 | 0 | 0 | 18222.8386 | 9118.1172 | 56.9427 | 100356.2319 | 1898.0916 | 22777.0997 | 98458.1402 | 0 | -8698.8862 | -107157.0265 | 1615849.0087 | 107157.0265 | -115849.0087 | 17355.5 | 0 | 9656.25 | 1607157.0265 | 100356.2319 | 1
24 | 2028-10-01 | 0.5 | 4.2392 | 33.9139 | 0.10174 | 8.4785 | 2.1196 | 5.25 | 9 | 72958.3333 | 0 | 0 | 1302.8698 | 302.82 | 0 | 0 | 0 | 0 | 618 | 103 | 327.4813 | 154.5 | 0 | 0 | 2808.6711 | 7576.7004 | 63.5886 | 83407.2935 | 2119.6203 | 25435.4432 | 81287.6732 | 0 | -107157.0265 | -188444.6997 | 1699256.3022 | 188444.6997 | -199256.3022 | 1905.5 | 0 | 9656.25 | 1688444.6997 | 83407.2935 | 1
25 | 2028-11-01 | 0.5 | 4.6757 | 37.4052 | 0.11222 | 9.3513 | 2.3378 | 5.4 | 9 | 77710.925 | 1250 | 625 | 1343.5856 | 311.9046 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 372.0299 | 159.135 | 0 | 0 | 2929.2851 | 8251.521 | 70.1348 | 90836.8659 | 2337.826 | 28053.9115 | 88499.04 | 0 | -188444.6997 | -276943.7397 | 1790093.1682 | 276943.7397 | -290093.1682 | 1962.665 | 0 | 9945.9375 | 1776943.7397 | 90836.8659 | 1
26 | 2028-12-01 | 0.5 | 5.1055 | 40.8441 | 0.12253 | 10.211 | 2.5528 | 5.4 | 9 | 77710.925 | 0 | 0 | 1345.1909 | 311.9046 | 12730.8 | 0 | 0 | 0 | 636.54 | 106.09 | 406.2332 | 159.135 | 0 | 0 | 15695.8937 | 9340.6819 | 76.5828 | 102824.0833 | 2552.7586 | 30633.1029 | 100271.3248 | 0 | -276943.7397 | -377215.0645 | 1892917.2515 | 377215.0645 | -392917.2515 | 14693.465 | 0 | 9945.9375 | 1877215.0645 | 102824.0833 | 1
27 | 2029-01-01 | 0.5 | 5.5289 | 44.2315 | 0.13269 | 11.0579 | 2.7645 | 5.4 | 9 | 77710.925 | 0 | 0 | 1346.7721 | 311.9046 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 439.9235 | 159.135 | 0 | 0 | 3000.3652 | 8071.129 | 82.934 | 88865.3532 | 2764.4672 | 33173.6063 | 86100.886 | 0 | -377215.0645 | -463315.9505 | 1981782.6047 | 463315.9505 | -481782.6047 | 1962.665 | 0 | 9945.9375 | 1963315.9505 | 88865.3532 | 1
28 | 2029-02-01 | 0.625 | 6.071 | 48.568 | 0.1457 | 12.142 | 3.0355 | 5.4 | 9 | 77710.925 | 0 | 0 | 1348.7963 | 311.9046 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 483.0543 | 198.9187 | 0 | 0 | 3085.304 | 8079.6229 | 91.065 | 88966.9169 | 3035.5002 | 36426.0022 | 85931.4167 | 0 | -463315.9505 | -549247.3672 | 2070749.5216 | 549247.3672 | -570749.5216 | 1962.665 | 0 | 9945.9375 | 2049247.3672 | 88966.9169 | 1
29 | 2029-03-01 | 0.625 | 6.6049 | 52.8395 | 0.15852 | 13.2099 | 3.3025 | 5.4 | 9 | 77710.925 | 0 | 0 | 1350.7903 | 311.9046 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 525.5382 | 198.9187 | 0 | 0 | 3129.7818 | 8084.0707 | 99.074 | 89023.8515 | 3302.4677 | 39629.6122 | 85721.3838 | 0 | -549247.3672 | -634968.751 | 2159773.3731 | 634968.751 | -659773.3731 | 1962.665 | 0 | 9945.9375 | 2134968.751 | 89023.8515 | 1
30 | 2029-04-01 | 0.625 | 7.1309 | 57.0469 | 0.17114 | 14.2617 | 3.5654 | 5.4 | 9 | 77710.925 | 0 | 0 | 1352.7543 | 311.9046 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 567.3848 | 198.9187 | 0 | 0 | 3173.5924 | 8088.4517 | 106.9629 | 89079.9321 | 3565.4307 | 42785.168 | 85514.5014 | 0 | -634968.751 | -720483.2524 | 2248853.3052 | 720483.2524 | -748853.3052 | 1962.665 | 0 | 9945.9375 | 2220483.2524 | 89079.9321 | 1
31 | 2029-05-01 | 0.625 | 7.6489 | 61.1912 | 0.18357 | 15.2978 | 3.8244 | 6.95 | 9 | 99813.0083 | 6250 | 3875 | 1354.6888 | 363.8887 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 608.6037 | 198.9187 | 0 | 0 | 3268.73 | 11320.6738 | 114.7335 | 124642.1456 | 3824.4492 | 45893.3905 | 120817.6964 | 0 | -720483.2524 | -841300.9489 | 2373495.4508 | 841300.9489 | -873495.4508 | 1962.665 | 0 | 9945.9375 | 2341300.9489 | 124642.1456 | 1
32 | 2029-06-01 | 0.625 | 8.1592 | 65.2733 | 0.19582 | 16.3183 | 4.0796 | 6.95 | 9 | 99813.0083 | 0 | 0 | 1356.5943 | 363.8887 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 649.2044 | 198.9187 | 0 | 0 | 3311.2361 | 10312.4244 | 122.3875 | 113559.0564 | 4079.5825 | 48954.9896 | 109479.4739 | 0 | -841300.9489 | -950780.4228 | 2487054.5072 | 950780.4228 | -987054.5072 | 1962.665 | 0 | 9945.9375 | 2450780.4228 | 113559.0564 | 1
33 | 2029-07-01 | 0.625 | 8.6618 | 69.2942 | 0.20788 | 17.3236 | 4.3309 | 6.95 | 9 | 99813.0083 | 0 | 0 | 1358.4713 | 363.8887 | 0 | 0 | 0 | 12730.8 | 636.54 | 106.09 | 689.196 | 198.9187 | 0 | 0 | 16083.9047 | 11589.6913 | 129.9267 | 127616.531 | 4330.8887 | 51970.6648 | 123285.6423 | 0 | -950780.4228 | -1074066.065 | 2614671.0382 | 1074066.065 | -1114671.0382 | 14693.465 | 0 | 9945.9375 | 2574066.065 | 127616.531 | 1
34 | 2029-08-01 | 0.625 | 9.1569 | 73.2548 | 0.21976 | 18.3137 | 4.5784 | 6.95 | 9 | 99813.0083 | 0 | 0 | 1360.3201 | 363.8887 | 0 | 19096.2 | 0 | 0 | 636.54 | 106.09 | 728.5877 | 198.9187 | 0 | 0 | 22490.5452 | 12230.3554 | 137.3528 | 134671.2617 | 4578.4254 | 54941.1048 | 130092.8363 | 0 | -1074066.065 | -1204158.9013 | 2749342.2999 | 1204158.9013 | -1249342.2999 | 21058.865 | 0 | 9945.9375 | 2704158.9013 | 134671.2617 | 1
35 | 2029-09-01 | 0.625 | 9.6445 | 77.156 | 0.23147 | 19.289 | 4.8222 | 6.95 | 9 | 99813.0083 | 0 | 0 | 1362.1411 | 363.8887 | 0 | 0 | 15913.5 | 0 | 636.54 | 106.09 | 767.3886 | 198.9187 | 0 | 0 | 19348.4672 | 11916.1475 | 144.6675 | 131222.2905 | 4822.249 | 57866.9883 | 126400.0415 | 0 | -1204158.9013 | -1330558.9428 | 2880564.5904 | 1330558.9428 | -1380564.5904 | 17876.165 | 0 | 9945.9375 | 2830558.9428 | 131222.2905 | 1
36 | 2029-10-01 | 0.625 | 10.1248 | 80.9986 | 0.243 | 20.2497 | 5.0624 | 6.95 | 9 | 99813.0083 | 0 | 0 | 1363.9348 | 363.8887 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 805.6075 | 198.9187 | 0 | 0 | 3474.9797 | 10328.7988 | 151.8725 | 113768.6594 | 5062.4153 | 60748.9834 | 108706.2441 | 0 | -1330558.9428 | -1439265.1868 | 2994333.2497 | 1439265.1868 | -1494333.2497 | 1962.665 | 0 | 9945.9375 | 2939265.1868 | 113768.6594 | 1
37 | 2029-11-01 | 0.625 | 10.598 | 84.7837 | 0.25435 | 21.1959 | 5.299 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1406.6727 | 374.8054 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 868.5506 | 204.8863 | 0 | 0 | 3619.8239 | 10642.7223 | 158.9694 | 117228.9141 | 5298.9791 | 63587.7487 | 111929.9351 | 0 | -1439265.1868 | -1551195.1219 | 3111562.1639 | 1551195.1219 | -1611562.1639 | 2021.5449 | 0 | 10244.3156 | 3051195.1219 | 117228.9141 | 1
38 | 2029-12-01 | 0.625 | 11.064 | 88.5119 | 0.26554 | 22.128 | 5.532 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1408.4653 | 374.8054 | 13112.724 | 0 | 0 | 0 | 655.6362 | 109.2727 | 906.7439 | 204.8863 | 0 | 0 | 16772.5338 | 11957.9932 | 165.9598 | 131703.8854 | 5531.9944 | 66383.9324 | 126171.8911 | 0 | -1551195.1219 | -1677367.013 | 3243266.0493 | 1677367.013 | -1743266.0493 | 15134.2689 | 0 | 10244.3156 | 3177367.013 | 131703.8854 | 1
39 | 2030-01-01 | 0.625 | 11.523 | 92.1842 | 0.27655 | 23.0461 | 5.7615 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1410.2309 | 374.8054 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 944.3644 | 204.8863 | 0 | 0 | 3699.1959 | 10650.6594 | 172.8454 | 117330.0993 | 5761.5145 | 69138.1735 | 111568.5849 | 0 | -1677367.013 | -1788935.5978 | 3360596.1486 | 1788935.5978 | -1860596.1486 | 2021.5449 | 0 | 10244.3156 | 3288935.5978 | 117330.0993 | 1
40 | 2030-02-01 | 0.78125 | 12.1314 | 97.0515 | 0.29115 | 24.2629 | 6.0657 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1412.5711 | 374.8054 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 994.2259 | 256.1079 | 0 | 0 | 3802.6191 | 10661.0018 | 181.9715 | 117452.991 | 6065.7167 | 72788.6009 | 111387.2742 | 0 | -1788935.5978 | -1900322.8721 | 3478049.1396 | 1900322.8721 | -1978049.1396 | 2021.5449 | 0 | 10244.3156 | 3400322.8721 | 117452.991 | 1
41 | 2030-03-01 | 0.78125 | 12.7307 | 101.8457 | 0.30554 | 25.4614 | 6.3654 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1414.8761 | 374.8054 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 1043.3395 | 256.1079 | 0 | 0 | 3854.0378 | 10666.1436 | 190.9607 | 117518.5406 | 6365.356 | 76384.2718 | 111153.1847 | 0 | -1900322.8721 | -2011476.0567 | 3595567.6802 | 2011476.0567 | -2095567.6802 | 2021.5449 | 0 | 10244.3156 | 3511476.0567 | 117518.5406 | 1
42 | 2030-04-01 | 0.78125 | 13.321 | 106.568 | 0.3197 | 26.642 | 6.6605 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1417.1466 | 374.8054 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 1091.7163 | 256.1079 | 0 | 0 | 3904.6851 | 10671.2084 | 199.815 | 117583.1071 | 6660.5006 | 79926.0078 | 110922.6064 | 0 | -2011476.0567 | -2122398.6632 | 3713150.7873 | 2122398.6632 | -2213150.7873 | 2021.5449 | 0 | 10244.3156 | 3622398.6632 | 117583.1071 | 1
43 | 2030-05-01 | 0.78125 | 13.9024 | 111.2195 | 0.33366 | 27.8049 | 6.9512 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1419.3831 | 374.8054 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 1139.3676 | 256.1079 | 0 | 0 | 3954.5728 | 10676.1971 | 208.5365 | 117646.705 | 6951.2181 | 83414.6177 | 110695.4869 | 0 | -2122398.6632 | -2233094.1501 | 3830797.4924 | 2233094.1501 | -2330797.4924 | 2021.5449 | 0 | 10244.3156 | 3733094.1501 | 117646.705 | 1
44 | 2030-06-01 | 0.78125 | 14.4751 | 115.8012 | 0.3474 | 28.9503 | 7.2376 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1421.586 | 374.8054 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 1186.304 | 256.1079 | 0 | 0 | 4003.7121 | 10681.1111 | 217.1272 | 117709.349 | 7237.5749 | 86850.8984 | 110471.7742 | 0 | -2233094.1501 | -2343565.9242 | 3948506.8414 | 2343565.9242 | -2448506.8414 | 2021.5449 | 0 | 10244.3156 | 3843565.9242 | 117709.349 | 1
45 | 2030-07-01 | 0.78125 | 15.0393 | 120.3142 | 0.36094 | 30.0785 | 7.5196 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1423.7558 | 374.8054 | 0 | 0 | 0 | 13112.724 | 655.6362 | 109.2727 | 1232.5364 | 256.1079 | 0 | 0 | 17164.8384 | 11997.2237 | 225.5891 | 132195.0497 | 7519.6362 | 90235.6349 | 124675.4135 | 0 | -2343565.9242 | -2468241.3377 | 4080701.8911 | 2468241.3377 | -2580701.8911 | 15134.2689 | 0 | 10244.3156 | 3968241.3377 | 132195.0497 | 1
46 | 2030-08-01 | 0.78125 | 15.5949 | 124.7595 | 0.37428 | 31.1899 | 7.7975 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1425.8931 | 374.8054 | 0 | 19669.086 | 0 | 0 | 655.6362 | 109.2727 | 1278.0754 | 256.1079 | 0 | 0 | 23768.8766 | 12657.6275 | 233.924 | 139467.8267 | 7797.4667 | 93569.6004 | 131670.36 | 0 | -2468241.3377 | -2599911.6977 | 4220169.7178 | 2599911.6977 | -2720169.7178 | 21690.6309 | 0 | 10244.3156 | 4099911.6977 | 139467.8267 | 1
47 | 2030-09-01 | 0.78125 | 16.1423 | 129.1381 | 0.38741 | 32.2845 | 8.0711 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1427.9983 | 374.8054 | 0 | 0 | 16390.905 | 0 | 655.6362 | 109.2727 | 1322.9312 | 256.1079 | 0 | 0 | 20537.6567 | 12334.5055 | 242.1339 | 135921.6947 | 8071.1297 | 96853.5564 | 127850.565 | 0 | -2599911.6977 | -2727762.2627 | 4356091.4125 | 2727762.2627 | -2856091.4125 | 18412.4499 | 0 | 10244.3156 | 4227762.2627 | 135921.6947 | 1
48 | 2030-10-01 | 0.78125 | 16.6814 | 133.451 | 0.40035 | 33.3628 | 8.3407 | 6.95 | 9 | 102807.3986 | 0 | 0 | 1430.072 | 374.8054 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 1367.1142 | 256.1079 | 0 | 0 | 4193.0083 | 10700.0407 | 250.2206 | 117950.6682 | 8340.6878 | 100088.253 | 109609.9805 | 0 | -2727762.2627 | -2837372.2432 | 4474042.0808 | 2837372.2432 | -2974042.0808 | 2021.5449 | 0 | 10244.3156 | 4337372.2432 | 117950.6682 | 1
49 | 2030-11-01 | 0.78125 | 17.2124 | 137.6992 | 0.4131 | 34.4248 | 8.6062 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1475.078 | 386.0495 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 1452.9535 | 263.7911 | 0 | 0 | 4365.7283 | 11025.7349 | 258.1861 | 121541.2698 | 8606.2024 | 103274.4292 | 112935.0673 | 0 | -2837372.2432 | -2950307.3105 | 4595583.3505 | 2950307.3105 | -3095583.3505 | 2082.1913 | 0 | 10551.6451 | 4450307.3105 | 121541.2698 | 1
50 | 2030-12-01 | 0.78125 | 17.7355 | 141.8838 | 0.42565 | 35.4709 | 8.8677 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1477.1502 | 386.0495 | 13506.1057 | 0 | 0 | 0 | 675.3053 | 112.5509 | 1497.107 | 263.7911 | 0 | 0 | 17918.0597 | 12380.968 | 266.032 | 136456.6804 | 8867.7344 | 106412.8128 | 127588.9459 | 0 | -2950307.3105 | -3077896.2565 | 4732040.0309 | 3077896.2565 | -3232040.0309 | 15588.297 | 0 | 10551.6451 | 4577896.2565 | 136456.6804 | 1
51 | 2031-01-01 | 0.78125 | 18.2507 | 146.0055 | 0.43802 | 36.5014 | 9.1253 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1479.1914 | 386.0495 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 1540.5982 | 263.7911 | 0 | 0 | 4457.4864 | 11034.9107 | 273.7603 | 121657.7779 | 9125.3434 | 109504.1206 | 112532.4345 | 0 | -3077896.2565 | -3190428.691 | 4853697.8088 | 3190428.691 | -3353697.8088 | 2082.1913 | 0 | 10551.6451 | 4690428.691 | 121657.7779 | 1
52 | 2031-02-01 | 0.97656 | 18.9535 | 151.6279 | 0.45488 | 37.907 | 9.4767 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1481.9758 | 386.0495 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 1599.9239 | 329.7389 | 0 | 0 | 4585.5443 | 11047.7165 | 284.3023 | 121809.1836 | 9476.7445 | 113720.9338 | 112332.4392 | 0 | -3190428.691 | -3302761.1302 | 4975506.9924 | 3302761.1302 | -3475506.9924 | 2082.1913 | 0 | 10551.6451 | 4802761.1302 | 121809.1836 | 1
53 | 2031-03-01 | 0.97656 | 19.6457 | 157.166 | 0.4715 | 39.2915 | 9.8229 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1484.7184 | 386.0495 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 1658.3598 | 329.7389 | 0 | 0 | 4646.7227 | 11053.8343 | 294.6862 | 121886.8638 | 9822.8746 | 117874.4948 | 112063.9893 | 0 | -3302761.1302 | -3414825.1195 | 5097393.8563 | 3414825.1195 | -3597393.8563 | 2082.1913 | 0 | 10551.6451 | 4914825.1195 | 121886.8638 | 1
54 | 2031-04-01 | 0.97656 | 20.3276 | 162.621 | 0.48786 | 40.6553 | 10.1638 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1487.4198 | 386.0495 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 1715.9191 | 329.7389 | 0 | 0 | 4706.9835 | 11059.8604 | 304.9144 | 121963.3789 | 10163.8127 | 121965.7524 | 111799.5662 | 0 | -3414825.1195 | -3526624.6856 | 5219357.2351 | 3526624.6856 | -3719357.2351 | 2082.1913 | 0 | 10551.6451 | 5026624.6856 | 121963.3789 | 1
55 | 2031-05-01 | 0.97656 | 20.9993 | 167.9942 | 0.50398 | 41.9985 | 10.4996 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1490.0807 | 386.0495 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 1772.6151 | 329.7389 | 0 | 0 | 4766.3404 | 11065.7961 | 314.9891 | 122038.7461 | 10499.6368 | 125995.6411 | 111539.1094 | 0 | -3526624.6856 | -3638163.795 | 5341395.9813 | 3638163.795 | -3841395.9813 | 2082.1913 | 0 | 10551.6451 | 5138163.795 | 122038.7461 | 1
56 | 2031-06-01 | 0.97656 | 21.6608 | 173.2868 | 0.51986 | 43.3217 | 10.8304 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1492.7018 | 386.0495 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 1828.4606 | 329.7389 | 0 | 0 | 4824.8069 | 11071.6427 | 324.9127 | 122112.9829 | 10830.4235 | 129965.0815 | 111282.5594 | 0 | -3638163.795 | -3749446.3544 | 5463508.9642 | 3749446.3544 | -3963508.9642 | 2082.1913 | 0 | 10551.6451 | 5249446.3544 | 122112.9829 | 1
57 | 2031-07-01 | 0.97656 | 22.3125 | 178.5 | 0.5355 | 44.625 | 11.1562 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1495.2835 | 386.0495 | 0 | 0 | 0 | 13506.1057 | 675.3053 | 112.5509 | 1883.4684 | 329.7389 | 0 | 0 | 18388.5022 | 12428.0123 | 334.6875 | 137042.8224 | 11156.2484 | 133874.9802 | 125886.5741 | 0 | -3749446.3544 | -3875332.9285 | 5600551.7866 | 3875332.9285 | -4100551.7866 | 15588.297 | 0 | 10551.6451 | 5375332.9285 | 137042.8224 | 1
58 | 2031-08-01 | 0.97656 | 22.9544 | 183.635 | 0.5509 | 45.9087 | 11.4772 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1497.8264 | 386.0495 | 0 | 20259.1586 | 0 | 0 | 675.3053 | 112.5509 | 1937.6511 | 329.7389 | 0 | 0 | 25198.2807 | 13108.9901 | 344.3156 | 144543.2069 | 11477.1859 | 137726.2305 | 133066.021 | 0 | -3875332.9285 | -4008398.9496 | 5745094.9935 | 4008398.9496 | -4245094.9935 | 22341.3499 | 0 | 10551.6451 | 5508398.9496 | 144543.2069 | 1
59 | 2031-09-01 | 0.97656 | 23.5866 | 188.6929 | 0.56608 | 47.1732 | 11.7933 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1500.3313 | 386.0495 | 0 | 0 | 16882.6322 | 0 | 675.3053 | 112.5509 | 1991.021 | 329.7389 | 0 | 0 | 21877.629 | 12776.925 | 353.7993 | 140899.9738 | 11793.3093 | 141519.7121 | 129106.6645 | 0 | -4008398.9496 | -4137505.614 | 5885994.9673 | 4137505.614 | -4385994.9673 | 18964.8234 | 0 | 10551.6451 | 5637505.614 | 140899.9738 | 1
60 | 2031-10-01 | 0.97656 | 24.2094 | 193.6751 | 0.58103 | 48.4188 | 12.1047 | 6.95 | 9 | 105891.6205 | 0 | 0 | 1502.7985 | 386.0495 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 2043.5904 | 329.7389 | 0 | 0 | 5050.0336 | 11094.1654 | 363.1407 | 122398.9602 | 12104.691 | 145256.2914 | 110294.2693 | 0 | -4137505.614 | -4247799.8833 | 6008393.9276 | 4247799.8833 | -4508393.9276 | 2082.1913 | 0 | 10551.6451 | 5747799.8833 | 122398.9602 | 1
Formulas:
Date = EDATE('Start Here'!$B6,[Month]-1)

## Monthly Base
Base ¦ 60-month financial model | [43 empty] | Base
Expected-value cohorts, monthly revenue recognized = active organizations × ARPA; ARR = exit-month revenue ×12, never annual revenue. Spend includes contingency; cash excludes taxes, financing fees and receivables timing.
← Start Here
Month | Date | New customers | Active customers | Users | API requests M | Storage GB | Logs GB | Total FTE | Headcount slots | Staff cash | Recruiting | Equipment | INFRA | TOOLS | LEGAL | SECURITY | COMPLIANCE | INSURANCE | ACCOUNTING | SUPPORT | MARKETING | ONBOARD | AI | CTMS | Vendor total | Contingency | Payment fees | Total spend | Monthly revenue | Exit ARR | Net burn | Financing | Opening cash | Closing cash | Cumulative spend | Funding gap | Cash if zero revenue | Unresolved vendor cash | Optional vendor cash | Unpaid founder economic | Cumulative net need | Cost-only burn | Negative flag
1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 19250 | 8000 | 6000 | 1250 | 98 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 1948 | 5279.7 | 0 | 40477.7 | 0 | 0 | 40477.7 | 0 | 1000000 | 959522.3 | 40477.7 | 0 | 959522.3 | 1850 | 0 | 15000 | 40477.7 | 40477.7 | 0
2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2.65 | 5 | 28416.6667 | 0 | 1950 | 1250 | 147 | 20000 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 21997 | 7854.55 | 0 | 60218.2167 | 0 | 0 | 60218.2167 | 0 | 959522.3 | 899304.0833 | 100695.9167 | 0 | 899304.0833 | 21850 | 0 | 15000 | 100695.9167 | 60218.2167 | 0
3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 3.65 | 6 | 45333.3333 | 8000 | 3000 | 1250 | 196 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2046 | 8756.9 | 0 | 67136.2333 | 0 | 0 | 67136.2333 | 0 | 899304.0833 | 832167.85 | 167832.15 | 0 | 832167.85 | 1850 | 0 | 15000 | 167832.15 | 67136.2333 | 0
4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.65 | 8 | 59916.6667 | 8000 | 3000 | 1250 | 245 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2095 | 10951.75 | 0 | 83963.4167 | 0 | 0 | 83963.4167 | 0 | 832167.85 | 748204.4333 | 251795.5667 | 0 | 748204.4333 | 1850 | 0 | 15000 | 251795.5667 | 83963.4167 | 0
5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.65 | 8 | 59916.6667 | 0 | 0 | 1250 | 245 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2095 | 9301.75 | 0 | 71313.4167 | 0 | 0 | 71313.4167 | 0 | 748204.4333 | 676891.0167 | 323108.9833 | 0 | 676891.0167 | 1850 | 0 | 15000 | 323108.9833 | 71313.4167 | 0
6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.65 | 8 | 59916.6667 | 0 | 0 | 1250 | 245 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2095 | 9301.75 | 0 | 71313.4167 | 0 | 0 | 71313.4167 | 0 | 676891.0167 | 605577.6 | 394422.4 | 0 | 605577.6 | 1850 | 0 | 15000 | 394422.4 | 71313.4167 | 0
7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76916.6667 | 6000 | 3300 | 1250 | 294 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2144 | 13254.1 | 0 | 101614.7667 | 0 | 0 | 101614.7667 | 0 | 605577.6 | 503962.8333 | 496037.1667 | 0 | 503962.8333 | 1850 | 0 | 15000 | 496037.1667 | 101614.7667 | 0
8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76916.6667 | 0 | 0 | 1250 | 294 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2144 | 11859.1 | 0 | 90919.7667 | 0 | 0 | 90919.7667 | 0 | 503962.8333 | 413043.0667 | 586956.9333 | 0 | 413043.0667 | 1850 | 0 | 15000 | 586956.9333 | 90919.7667 | 0
9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76916.6667 | 0 | 0 | 1250 | 294 | 0 | 0 | 0 | 12000 | 600 | 100 | 0 | 0 | 0 | 0 | 14244 | 13674.1 | 0 | 104834.7667 | 0 | 0 | 104834.7667 | 0 | 413043.0667 | 308208.3 | 691791.7 | 0 | 308208.3 | 13850 | 0 | 15000 | 691791.7 | 104834.7667 | 0
10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 6.25 | 9 | 82166.6667 | 4000 | 1500 | 1250 | 343 | 0 | 18000 | 0 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 20293 | 16193.95 | 0 | 124153.6167 | 0 | 0 | 124153.6167 | 0 | 308208.3 | 184054.6833 | 815945.3167 | 0 | 184054.6833 | 19850 | 0 | 15000 | 815945.3167 | 124153.6167 | 0
11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 6.25 | 9 | 82166.6667 | 0 | 0 | 1250 | 343 | 0 | 0 | 15000 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 17293 | 14918.95 | 0 | 114378.6167 | 0 | 0 | 114378.6167 | 0 | 184054.6833 | 69676.0667 | 930323.9333 | 0 | 69676.0667 | 16850 | 0 | 15000 | 930323.9333 | 114378.6167 | 0
12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 6.25 | 9 | 82166.6667 | 0 | 0 | 1250 | 343 | 0 | 0 | 0 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 2293 | 12668.95 | 0 | 97128.6167 | 0 | 0 | 97128.6167 | 0 | 69676.0667 | -27452.55 | 1027452.55 | 27452.55 | -27452.55 | 1850 | 0 | 15000 | 1027452.55 | 97128.6167 | 1
13 | 2027-11-01 | 1 | 1 | 15 | 0.0675 | 5 | 1 | 6.25 | 9 | 85453.3333 | 0 | 0 | 1295.5083 | 353.29 | 0 | 0 | 0 | 0 | 618 | 103 | 77.25 | 309 | 0 | 0 | 2756.0482 | 13231.4072 | 27 | 101467.7888 | 900 | 10800 | 100567.7888 | 3000000 | -27452.55 | 2871979.6612 | 1128920.3388 | 0 | 2871079.6612 | 1905.5 | 0 | 15600 | 1128020.3388 | 101467.7888 | 0
14 | 2027-12-01 | 1 | 1.99 | 29.85 | 0.13432 | 9.95 | 1.99 | 6.25 | 9 | 85453.3333 | 0 | 0 | 1303.4364 | 353.29 | 12360 | 0 | 0 | 0 | 618 | 103 | 153.7275 | 309 | 0 | 0 | 15200.4539 | 15098.0681 | 53.73 | 115805.5853 | 1791 | 21492 | 114014.5853 | 0 | 2871979.6612 | 2757965.0758 | 1244725.9242 | 0 | 2755274.0758 | 14265.5 | 0 | 15600 | 1242034.9242 | 115805.5853 | 0
15 | 2028-01-01 | 1 | 2.9701 | 44.5515 | 0.20048 | 14.8505 | 2.9701 | 6.25 | 9 | 85453.3333 | 0 | 0 | 1311.2853 | 353.29 | 0 | 0 | 0 | 0 | 618 | 103 | 229.4402 | 309 | 0 | 0 | 2924.0155 | 13256.6023 | 80.1927 | 101714.1439 | 2673.09 | 32077.08 | 99041.0539 | 0 | 2757965.0758 | 2658924.0219 | 1346440.0681 | 0 | 2653559.9319 | 1905.5 | 0 | 15600 | 1341075.9781 | 101714.1439 | 0
16 | 2028-02-01 | 1 | 3.9404 | 59.106 | 0.26598 | 19.702 | 3.9404 | 8.25 | 10 | 115960 | 14000 | 6000 | 1319.0557 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 304.3958 | 309 | 0 | 0 | 3107.6815 | 20860.1522 | 106.3908 | 160034.2245 | 3546.3591 | 42556.3092 | 156487.8654 | 0 | 2658924.0219 | 2502436.1565 | 1506474.2926 | 0 | 2493525.7074 | 1905.5 | 0 | 15600 | 1497563.8435 | 160034.2245 | 0
17 | 2028-03-01 | 1 | 4.901 | 73.5149 | 0.33082 | 24.505 | 4.901 | 8.25 | 10 | 115960 | 0 | 0 | 1326.7484 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 378.6019 | 309 | 0 | 0 | 3189.5803 | 17872.437 | 132.3269 | 137154.3442 | 4410.8955 | 52930.7461 | 132743.4487 | 0 | 2502436.1565 | 2369692.7079 | 1643628.6367 | 0 | 2356371.3633 | 1905.5 | 0 | 15600 | 1630307.2921 | 137154.3442 | 0
18 | 2028-04-01 | 1 | 5.852 | 87.7798 | 0.39501 | 29.2599 | 5.852 | 8.25 | 10 | 115960 | 0 | 0 | 1334.3642 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 452.0658 | 309 | 0 | 0 | 3270.66 | 17884.599 | 158.0036 | 137273.2626 | 5266.7866 | 63201.4386 | 132006.476 | 0 | 2369692.7079 | 2237686.2318 | 1780901.8993 | 0 | 2219098.1007 | 1905.5 | 0 | 15600 | 1762313.7682 | 137273.2626 | 0
19 | 2028-05-01 | 1 | 6.7935 | 101.902 | 0.45856 | 33.9673 | 6.7935 | 8.75 | 11 | 123240 | 4000 | 1500 | 1341.9038 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 524.7952 | 309 | 0 | 0 | 3350.929 | 19813.6393 | 183.4236 | 152087.9919 | 6114.1187 | 73369.4243 | 145973.8732 | 0 | 2237686.2318 | 2091712.3587 | 1932989.8912 | 0 | 2067010.1088 | 1905.5 | 0 | 15600 | 1908287.6413 | 152087.9919 | 0
20 | 2028-06-01 | 1 | 7.7255 | 115.883 | 0.52147 | 38.6277 | 7.7255 | 8.75 | 11 | 123240 | 0 | 0 | 1349.368 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 596.7972 | 309 | 0 | 0 | 3430.3952 | 19000.5593 | 208.5893 | 145879.5438 | 6952.9775 | 83435.73 | 138926.5663 | 0 | 2091712.3587 | 1952785.7923 | 2078869.435 | 0 | 1921130.565 | 1905.5 | 0 | 15600 | 2047214.2077 | 145879.5438 | 0
21 | 2028-07-01 | 1 | 8.6483 | 129.7241 | 0.58376 | 43.2414 | 8.6483 | 8.75 | 11 | 123240 | 0 | 0 | 1356.7576 | 454.23 | 0 | 0 | 0 | 12360 | 618 | 103 | 668.0793 | 309 | 0 | 0 | 15869.0668 | 20866.36 | 233.5034 | 160208.9303 | 7783.4477 | 93401.3727 | 152425.4825 | 0 | 1952785.7923 | 1800360.3098 | 2239078.3653 | 0 | 1760921.6347 | 14265.5 | 0 | 15600 | 2199639.6902 | 160208.9303 | 0
22 | 2028-08-01 | 1 | 9.5618 | 143.4269 | 0.64542 | 47.809 | 9.5618 | 8.75 | 11 | 123240 | 0 | 0 | 1364.0732 | 454.23 | 0 | 18540 | 0 | 0 | 618 | 103 | 738.6485 | 309 | 0 | 0 | 22126.9517 | 21805.0428 | 258.1684 | 167430.1628 | 8605.6132 | 103267.359 | 158824.5496 | 0 | 1800360.3098 | 1641535.7602 | 2406508.5281 | 0 | 1593491.4719 | 20445.5 | 0 | 15600 | 2358464.2398 | 167430.1628 | 0
23 | 2028-09-01 | 1 | 10.4662 | 156.9926 | 0.70647 | 52.3309 | 10.4662 | 8.75 | 11 | 123240 | 0 | 0 | 1371.3157 | 454.23 | 0 | 0 | 15450 | 0 | 618 | 103 | 808.512 | 309 | 0 | 0 | 19114.0577 | 21353.1087 | 282.5867 | 163989.7531 | 9419.5571 | 113034.6854 | 154570.196 | 0 | 1641535.7602 | 1486965.5642 | 2570498.2812 | 0 | 1429501.7188 | 17355.5 | 0 | 15600 | 2513034.4358 | 163989.7531 | 0
24 | 2028-10-01 | 1 | 11.3615 | 170.4227 | 0.7669 | 56.8076 | 11.3615 | 8.75 | 11 | 123240 | 0 | 0 | 1378.4858 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 877.6769 | 309 | 0 | 0 | 3740.3927 | 19047.0589 | 306.7608 | 146334.2125 | 10225.3615 | 122704.3385 | 136108.8509 | 0 | 1486965.5642 | 1350856.7133 | 2716832.4937 | 0 | 1283167.5063 | 1905.5 | 0 | 15600 | 2649143.2867 | 146334.2125 | 0
25 | 2028-11-01 | 1.5 | 12.7479 | 191.2185 | 0.86048 | 63.7395 | 12.7479 | 8.75 | 11 | 128169.6 | 0 | 0 | 1431.276 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1014.3184 | 477.405 | 0 | 0 | 4133.4863 | 19845.4629 | 344.1932 | 152492.7424 | 11473.1079 | 137677.2952 | 141019.6345 | 0 | 1350856.7133 | 1209837.0788 | 2869325.2361 | 0 | 1130674.7639 | 1962.665 | 0 | 16224 | 2790162.9212 | 152492.7424 | 0
26 | 2028-12-01 | 1.5 | 14.1204 | 211.8063 | 0.95313 | 70.6021 | 14.1204 | 8.75 | 11 | 128169.6 | 0 | 0 | 1442.5972 | 467.8569 | 12730.8 | 0 | 0 | 0 | 636.54 | 106.09 | 1123.5264 | 477.405 | 0 | 0 | 16984.8156 | 21773.1623 | 381.2513 | 167308.8292 | 12708.3769 | 152500.5222 | 154600.4523 | 0 | 1209837.0788 | 1055236.6265 | 3036634.0653 | 0 | 963365.9347 | 14693.465 | 0 | 16224 | 2944763.3735 | 167308.8292 | 0
27 | 2029-01-01 | 1.5 | 15.4792 | 232.1882 | 1.0448 | 77.3961 | 15.4792 | 8.75 | 11 | 128169.6 | 0 | 0 | 1453.8053 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1231.6424 | 477.405 | 0 | 0 | 4373.3396 | 19881.4409 | 417.9388 | 152842.3193 | 13931.2931 | 167175.517 | 138911.0262 | 0 | 1055236.6265 | 916325.6002 | 3189476.3846 | 0 | 810523.6154 | 1962.665 | 0 | 16224 | 3083674.3998 | 152842.3193 | 0
28 | 2029-02-01 | 1.5 | 16.8244 | 252.3663 | 1.1356 | 84.1221 | 16.8244 | 8.75 | 11 | 128169.6 | 0 | 0 | 1464.9012 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1338.6772 | 477.405 | 0 | 0 | 4491.4703 | 19899.1606 | 454.2594 | 153014.4903 | 15141.9802 | 181703.7618 | 137872.5101 | 0 | 916325.6002 | 778453.0901 | 3342490.8749 | 0 | 657509.1251 | 1962.665 | 0 | 16224 | 3221546.9099 | 153014.4903 | 0
29 | 2029-03-01 | 1.5 | 18.1562 | 272.3427 | 1.2255 | 90.7809 | 18.1562 | 8.75 | 11 | 128169.6 | 0 | 0 | 1475.8862 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1444.6417 | 477.405 | 0 | 0 | 4608.4198 | 19916.703 | 490.2168 | 153184.9396 | 16340.5603 | 196086.7242 | 136844.3792 | 0 | 778453.0901 | 641608.7109 | 3495675.8145 | 0 | 504324.1855 | 1962.665 | 0 | 16224 | 3358391.2891 | 153184.9396 | 0
30 | 2029-04-01 | 1.5 | 19.4746 | 292.1192 | 1.3145 | 97.3731 | 19.4746 | 8.75 | 11 | 128169.6 | 0 | 0 | 1486.7613 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1549.5465 | 477.405 | 0 | 0 | 4724.1998 | 19934.07 | 525.8146 | 153353.6844 | 17527.1547 | 210325.857 | 135826.5296 | 0 | 641608.7109 | 505782.1813 | 3649029.4988 | 0 | 350970.5012 | 1962.665 | 0 | 16224 | 3494217.8187 | 153353.6844 | 0
31 | 2029-05-01 | 1.5 | 20.7799 | 311.6981 | 1.4026 | 103.8994 | 20.7799 | 12.75 | 14 | 187432.2667 | 28000 | 12000 | 1497.5277 | 675.7933 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1653.4023 | 477.405 | 0 | 0 | 5046.7583 | 34871.8537 | 561.0565 | 267911.9352 | 18701.8832 | 224422.5984 | 249210.052 | 0 | 505782.1813 | 256572.1292 | 3916941.4341 | 0 | 83058.5659 | 1962.665 | 0 | 16224 | 3743427.8708 | 267911.9352 | 0
32 | 2029-06-01 | 1.5 | 22.0721 | 331.0811 | 1.4899 | 110.3604 | 22.0721 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1508.1864 | 675.7933 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1756.2196 | 477.405 | 0 | 0 | 5160.2343 | 28888.8751 | 595.9459 | 222077.322 | 19864.8644 | 238378.3724 | 202212.4576 | 0 | 256572.1292 | 54359.6716 | 4139018.7561 | 0 | -139018.7561 | 1962.665 | 0 | 16224 | 3945640.3284 | 222077.322 | 0
33 | 2029-07-01 | 1.5 | 23.3514 | 350.2703 | 1.5762 | 116.7568 | 23.3514 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1518.7386 | 675.7933 | 0 | 0 | 0 | 12730.8 | 636.54 | 106.09 | 1858.0086 | 477.405 | 0 | 0 | 18003.3755 | 30815.3463 | 630.4865 | 236881.4749 | 21016.2157 | 252194.5887 | 215865.2592 | 0 | 54359.6716 | -161505.5876 | 4375900.231 | 161505.5876 | -375900.231 | 14693.465 | 0 | 16224 | 4161505.5876 | 236881.4749 | 1
34 | 2029-08-01 | 1.5 | 24.6178 | 369.2676 | 1.6617 | 123.0892 | 24.6178 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1529.1852 | 675.7933 | 0 | 19096.2 | 0 | 0 | 636.54 | 106.09 | 1958.7798 | 477.405 | 0 | 0 | 24479.9932 | 31786.839 | 664.6816 | 244363.7805 | 22156.0536 | 265872.6428 | 222207.7269 | 0 | -161505.5876 | -383713.3146 | 4620264.0115 | 383713.3146 | -620264.0115 | 21058.865 | 0 | 16224 | 4383713.3146 | 244363.7805 | 1
35 | 2029-09-01 | 1.5 | 25.8717 | 388.0749 | 1.7463 | 129.3583 | 25.8717 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1539.5273 | 675.7933 | 0 | 0 | 15913.5 | 0 | 636.54 | 106.09 | 2058.5432 | 477.405 | 0 | 0 | 21407.3988 | 31325.9498 | 698.5348 | 240864.1501 | 23284.493 | 279413.9164 | 217579.6571 | 0 | -383713.3146 | -601292.9717 | 4861128.1616 | 601292.9717 | -861128.1616 | 17876.165 | 0 | 16224 | 4601292.9717 | 240864.1501 | 1
36 | 2029-10-01 | 1.5 | 27.1129 | 406.6941 | 1.8301 | 135.5647 | 27.1129 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1549.766 | 675.7933 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 2157.309 | 477.405 | 0 | 0 | 5602.9034 | 28955.2755 | 732.0494 | 222722.495 | 24401.6481 | 292819.7772 | 198320.8469 | 0 | -601292.9717 | -799613.8185 | 5083850.6566 | 799613.8185 | -1083850.6566 | 1962.665 | 0 | 16224 | 4799613.8185 | 222722.495 | 1
37 | 2029-11-01 | 2.25 | 29.0918 | 436.3772 | 1.9637 | 145.4591 | 29.0918 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1613.0714 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 2384.2057 | 737.5907 | 0 | 0 | 6195.8438 | 29711.8342 | 785.4789 | 228576.2076 | 26182.6316 | 314191.5794 | 202393.576 | 0 | -799613.8185 | -1002007.3946 | 5312426.8643 | 1002007.3946 | -1312426.8643 | 2021.5449 | 0 | 16872.96 | 5002007.3946 | 228576.2076 | 1
38 | 2029-12-01 | 2.25 | 31.0509 | 465.7634 | 2.0959 | 155.2545 | 31.0509 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1629.7157 | 696.0671 | 13112.724 | 0 | 0 | 0 | 655.6362 | 109.2727 | 2544.7613 | 737.5907 | 0 | 0 | 19485.7677 | 31705.3228 | 838.3742 | 243912.5153 | 27945.8053 | 335349.6636 | 215966.71 | 0 | -1002007.3946 | -1217974.1046 | 5556339.3796 | 1217974.1046 | -1556339.3796 | 15134.2689 | 0 | 16872.96 | 5217974.1046 | 243912.5153 | 1
39 | 2030-01-01 | 2.25 | 32.9904 | 494.8558 | 2.2269 | 164.9519 | 32.9904 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1646.1935 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 2703.7114 | 737.5907 | 0 | 0 | 6548.4716 | 29764.7283 | 890.7404 | 229086.9911 | 29691.3472 | 356296.167 | 199395.6438 | 0 | -1217974.1046 | -1417369.7484 | 5785426.3706 | 1417369.7484 | -1785426.3706 | 2021.5449 | 0 | 16872.96 | 5417369.7484 | 229086.9911 | 1
40 | 2030-02-01 | 2.25 | 34.9105 | 523.6572 | 2.3565 | 174.5524 | 34.9105 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1662.5065 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 2861.072 | 737.5907 | 0 | 0 | 6722.1452 | 29790.7794 | 942.583 | 229338.5583 | 31419.4338 | 377033.2053 | 197919.1245 | 0 | -1417369.7484 | -1615288.8729 | 6014764.9289 | 1615288.8729 | -2014764.9289 | 2021.5449 | 0 | 16872.96 | 5615288.8729 | 229338.5583 | 1
41 | 2030-03-01 | 2.25 | 36.8114 | 552.1707 | 2.4848 | 184.0569 | 36.8114 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1678.6565 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 3016.8589 | 737.5907 | 0 | 0 | 6894.0821 | 29816.5699 | 993.9072 | 229587.6099 | 33130.2394 | 397562.8733 | 196457.3704 | 0 | -1615288.8729 | -1811746.2433 | 6244352.5388 | 1811746.2433 | -2244352.5388 | 2021.5449 | 0 | 16872.96 | 5811746.2433 | 229587.6099 | 1
42 | 2030-04-01 | 2.25 | 38.6933 | 580.399 | 2.6118 | 193.4663 | 38.6933 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1694.6449 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 3171.088 | 737.5907 | 0 | 0 | 7064.2996 | 29842.1025 | 1044.7181 | 229834.1709 | 34823.937 | 417887.2445 | 195010.2339 | 0 | -1811746.2433 | -2006756.4772 | 6474186.7098 | 2006756.4772 | -2474186.7098 | 2021.5449 | 0 | 16872.96 | 6006756.4772 | 229834.1709 | 1
43 | 2030-05-01 | 2.25 | 40.5563 | 608.345 | 2.7376 | 202.7817 | 40.5563 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1710.4734 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 3323.7748 | 737.5907 | 0 | 0 | 7232.815 | 29867.3798 | 1095.0209 | 230078.2664 | 36500.6977 | 438008.3721 | 193577.5687 | 0 | -2006756.4772 | -2200334.0459 | 6704264.9761 | 2200334.0459 | -2704264.9761 | 2021.5449 | 0 | 16872.96 | 6200334.0459 | 230078.2664 | 1
44 | 2030-06-01 | 2.25 | 42.4008 | 636.0115 | 2.8621 | 212.0038 | 42.4008 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1726.1437 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 3474.9348 | 737.5907 | 0 | 0 | 7399.6451 | 29892.4044 | 1144.8207 | 230319.9209 | 38160.6907 | 457928.2884 | 192159.2302 | 0 | -2200334.0459 | -2392493.2761 | 6934584.897 | 2392493.2761 | -2934584.897 | 2021.5449 | 0 | 16872.96 | 6392493.2761 | 230319.9209 | 1
45 | 2030-07-01 | 2.25 | 44.2268 | 663.4014 | 2.9853 | 221.1338 | 44.2268 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1741.6572 | 696.0671 | 0 | 0 | 0 | 13112.724 | 655.6362 | 109.2727 | 3624.5831 | 737.5907 | 0 | 0 | 20677.531 | 31884.0873 | 1194.1225 | 245638.7914 | 39804.0838 | 477649.0055 | 205834.7077 | 0 | -2392493.2761 | -2598327.9838 | 7180223.6885 | 2598327.9838 | -3180223.6885 | 15134.2689 | 0 | 16872.96 | 6598327.9838 | 245638.7914 | 1
46 | 2030-08-01 | 2.25 | 46.0345 | 690.5174 | 3.1073 | 230.1725 | 46.0345 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1757.0156 | 696.0671 | 0 | 19669.086 | 0 | 0 | 655.6362 | 109.2727 | 3772.7349 | 737.5907 | 0 | 0 | 27397.4033 | 32892.0681 | 1242.9313 | 253415.4533 | 41431.043 | 497172.5154 | 211984.4104 | 0 | -2598327.9838 | -2810312.3942 | 7433639.1418 | 2810312.3942 | -3433639.1418 | 21690.6309 | 0 | 16872.96 | 6810312.3942 | 253415.4533 | 1
47 | 2030-09-01 | 2.25 | 47.8241 | 717.3622 | 3.2281 | 239.1207 | 47.8241 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1772.2204 | 696.0671 | 0 | 0 | 16390.905 | 0 | 655.6362 | 109.2727 | 3919.4053 | 737.5907 | 0 | 0 | 24281.0974 | 32424.6222 | 1291.252 | 249880.0223 | 43041.7325 | 516500.7903 | 206838.2898 | 0 | -2810312.3942 | -3017150.6839 | 7683519.1641 | 3017150.6839 | -3683519.1641 | 18412.4499 | 0 | 16872.96 | 7017150.6839 | 249880.0223 | 1
48 | 2030-10-01 | 2.25 | 49.5959 | 743.9386 | 3.3477 | 247.9795 | 49.5959 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1787.2732 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 4064.6089 | 737.5907 | 0 | 0 | 8050.4488 | 29990.0249 | 1339.0895 | 231262.6139 | 44636.3152 | 535635.7824 | 186626.2987 | 0 | -3017150.6839 | -3203776.9826 | 7914781.7779 | 3203776.9826 | -3914781.7779 | 2021.5449 | 0 | 16872.96 | 7203776.9826 | 231262.6139 | 1
49 | 2030-11-01 | 3.375 | 52.4749 | 787.1242 | 3.5421 | 262.3747 | 52.4749 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1866.0854 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 4429.5761 | 1139.5777 | 0 | 0 | 8940.0445 | 31274.7626 | 1416.8236 | 241190.0033 | 47227.452 | 566729.4246 | 193962.5512 | 0 | -3203776.9826 | -3397739.5338 | 8155971.7812 | 3397739.5338 | -4155971.7812 | 2082.1913 | 0 | 17547.8784 | 7397739.5338 | 241190.0033 | 1
50 | 2030-12-01 | 3.375 | 55.3252 | 829.878 | 3.7345 | 276.626 | 55.3252 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1891.0275 | 716.9491 | 13506.1057 | 0 | 0 | 0 | 675.3053 | 112.5509 | 4670.1748 | 1139.5777 | 0 | 0 | 22711.6909 | 33340.5095 | 1493.7803 | 257104.3535 | 49792.6775 | 597512.1303 | 207311.6759 | 0 | -3397739.5338 | -3605051.2098 | 8413076.1347 | 3605051.2098 | -4413076.1347 | 15588.297 | 0 | 17547.8784 | 7605051.2098 | 257104.3535 | 1
51 | 2031-01-01 | 3.375 | 58.1469 | 872.2042 | 3.9249 | 290.7347 | 58.1469 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1915.7201 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 4908.3674 | 1139.5777 | 0 | 0 | 9468.4705 | 31354.0265 | 1569.9675 | 241950.8372 | 52332.2508 | 627987.009 | 189618.5864 | 0 | -3605051.2098 | -3794669.7962 | 8655026.9719 | 3794669.7962 | -4655026.9719 | 2082.1913 | 0 | 17547.8784 | 7794669.7962 | 241950.8372 | 1
52 | 2031-02-01 | 3.375 | 60.9405 | 914.1071 | 4.1135 | 304.7024 | 60.9405 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1940.1658 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 5144.1782 | 1139.5777 | 0 | 0 | 9728.7269 | 31393.0649 | 1645.3928 | 242325.5574 | 54846.4282 | 658157.1389 | 187479.1292 | 0 | -3794669.7962 | -3982148.9254 | 8897352.5293 | 3982148.9254 | -4897352.5293 | 2082.1913 | 0 | 17547.8784 | 7982148.9254 | 242325.5574 | 1
53 | 2031-03-01 | 3.375 | 63.7061 | 955.5911 | 4.3002 | 318.5304 | 63.7061 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1964.3671 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 5377.6308 | 1139.5777 | 0 | 0 | 9986.3808 | 31431.713 | 1720.0639 | 242696.5305 | 57335.464 | 688025.5675 | 185361.0665 | 0 | -3982148.9254 | -4167509.9919 | 9140049.0598 | 4167509.9919 | -5140049.0598 | 2082.1913 | 0 | 17547.8784 | 8167509.9919 | 242696.5305 | 1
54 | 2031-04-01 | 3.375 | 66.444 | 996.6602 | 4.485 | 332.2201 | 66.444 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1988.3263 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 5608.7489 | 1139.5777 | 0 | 0 | 10241.4582 | 31469.9746 | 1793.9883 | 243063.7938 | 59799.6093 | 717595.3119 | 183264.1845 | 0 | -4167509.9919 | -4350774.1764 | 9383112.8536 | 4350774.1764 | -5383112.8536 | 2082.1913 | 0 | 17547.8784 | 8350774.1764 | 243063.7938 | 1
55 | 2031-05-01 | 3.375 | 69.1546 | 1037.3186 | 4.6679 | 345.7729 | 69.1546 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2012.046 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 5837.5559 | 1139.5777 | 0 | 0 | 10493.9848 | 31507.8536 | 1867.1734 | 243427.3845 | 62239.1132 | 746869.3587 | 181188.2713 | 0 | -4350774.1764 | -4531962.4477 | 9626540.2381 | 4531962.4477 | -5626540.2381 | 2082.1913 | 0 | 17547.8784 | 8531962.4477 | 243427.3845 | 1
56 | 2031-06-01 | 3.375 | 71.838 | 1077.5704 | 4.8491 | 359.1901 | 71.838 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2035.5284 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 6064.0747 | 1139.5777 | 0 | 0 | 10743.9861 | 31545.3538 | 1939.6267 | 243787.3393 | 64654.2221 | 775850.6651 | 179133.1172 | 0 | -4531962.4477 | -4711095.5648 | 9870327.5774 | 4711095.5648 | -5870327.5774 | 2082.1913 | 0 | 17547.8784 | 8711095.5648 | 243787.3393 | 1
57 | 2031-07-01 | 3.375 | 74.4946 | 1117.4197 | 5.0284 | 372.4732 | 74.4946 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2058.7761 | 716.9491 | 0 | 0 | 0 | 13506.1057 | 675.3053 | 112.5509 | 6288.3284 | 1139.5777 | 0 | 0 | 24497.5931 | 33608.3949 | 2011.3554 | 259675.7161 | 67045.1799 | 804542.1585 | 192630.5362 | 0 | -4711095.5648 | -4903726.101 | 10130003.2934 | 4903726.101 | -6130003.2934 | 15588.297 | 0 | 17547.8784 | 8903726.101 | 259675.7161 | 1
58 | 2031-08-01 | 3.375 | 77.1247 | 1156.8705 | 5.2059 | 385.6235 | 77.1247 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2081.7912 | 716.9491 | 0 | 20259.1586 | 0 | 0 | 675.3053 | 112.5509 | 6510.3395 | 1139.5777 | 0 | 0 | 31495.6723 | 34658.1067 | 2082.3668 | 267794.5185 | 69412.2281 | 832946.7369 | 198382.2905 | 0 | -4903726.101 | -5102108.3915 | 10397797.812 | 5102108.3915 | -6397797.812 | 22341.3499 | 0 | 17547.8784 | 9102108.3915 | 267794.5185 | 1
59 | 2031-09-01 | 3.375 | 79.7285 | 1195.9268 | 5.3817 | 398.6423 | 79.7285 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2104.5762 | 716.9491 | 0 | 0 | 16882.6322 | 0 | 675.3053 | 112.5509 | 6730.1305 | 1139.5777 | 0 | 0 | 28361.7219 | 34188.0142 | 2152.6682 | 264260.7769 | 71755.6058 | 861067.2695 | 192505.1711 | 0 | -5102108.3915 | -5294613.5626 | 10662058.5889 | 5294613.5626 | -6662058.5889 | 18964.8234 | 0 | 17547.8784 | 9294613.5626 | 264260.7769 | 1
60 | 2031-10-01 | 3.375 | 82.3062 | 1234.5925 | 5.5557 | 411.5308 | 82.3062 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2127.1334 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 6947.7237 | 1139.5777 | 0 | 0 | 11719.24 | 31691.6419 | 2222.2665 | 245191.5211 | 74075.5497 | 888906.5968 | 171115.9713 | 0 | -5294613.5626 | -5465729.5339 | 10907250.1099 | 5465729.5339 | -6907250.1099 | 2082.1913 | 0 | 17547.8784 | 9465729.5339 | 245191.5211 | 1
Formulas:
Date = EDATE('Start Here'!$B6,[Month]-1)

## Monthly Growth
Growth ¦ 60-month financial model | [43 empty] | Growth
Expected-value cohorts, monthly revenue recognized = active organizations × ARPA; ARR = exit-month revenue ×12, never annual revenue. Spend includes contingency; cash excludes taxes, financing fees and receivables timing.
← Start Here
Month | Date | New customers | Active customers | Users | API requests M | Storage GB | Logs GB | Total FTE | Headcount slots | Staff cash | Recruiting | Equipment | INFRA | TOOLS | LEGAL | SECURITY | COMPLIANCE | INSURANCE | ACCOUNTING | SUPPORT | MARKETING | ONBOARD | AI | CTMS | Vendor total | Contingency | Payment fees | Total spend | Monthly revenue | Exit ARR | Net burn | Financing | Opening cash | Closing cash | Cumulative spend | Funding gap | Cash if zero revenue | Unresolved vendor cash | Optional vendor cash | Unpaid founder economic | Cumulative net need | Cost-only burn | Negative flag
1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 19250 | 12000 | 7000 | 1250 | 98 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 1948 | 8039.6 | 0 | 48237.6 | 0 | 0 | 48237.6 | 0 | 2000000 | 1951762.4 | 48237.6 | 0 | 1951762.4 | 1850 | 0 | 16666.6667 | 48237.6 | 48237.6 | 0
2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.25 | 6 | 53666.6667 | 12000 | 7875 | 1250 | 245 | 20000 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 22095 | 19127.3333 | 0 | 114764 | 0 | 0 | 114764 | 0 | 1951762.4 | 1836998.4 | 163001.6 | 0 | 1836998.4 | 21850 | 0 | 16666.6667 | 163001.6 | 114764 | 0
3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76416.6667 | 18000 | 5250 | 1250 | 294 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2144 | 20362.1333 | 0 | 122172.8 | 0 | 0 | 122172.8 | 0 | 1836998.4 | 1714825.6 | 285174.4 | 0 | 1714825.6 | 1850 | 0 | 16666.6667 | 285174.4 | 122172.8 | 0
4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76416.6667 | 0 | 0 | 1250 | 294 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2144 | 15712.1333 | 0 | 94272.8 | 0 | 0 | 94272.8 | 0 | 1714825.6 | 1620552.8 | 379447.2 | 0 | 1620552.8 | 1850 | 0 | 16666.6667 | 379447.2 | 94272.8 | 0
5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76416.6667 | 0 | 0 | 1250 | 294 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2144 | 15712.1333 | 0 | 94272.8 | 0 | 0 | 94272.8 | 0 | 1620552.8 | 1526280 | 473720 | 0 | 1526280 | 1850 | 0 | 16666.6667 | 473720 | 94272.8 | 0
6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76416.6667 | 0 | 0 | 1250 | 294 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2144 | 15712.1333 | 0 | 94272.8 | 0 | 0 | 94272.8 | 0 | 1526280 | 1432007.2 | 567992.8 | 0 | 1432007.2 | 1850 | 0 | 16666.6667 | 567992.8 | 94272.8 | 0
7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 7.75 | 9 | 107875 | 18000 | 7000 | 1250 | 392 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2242 | 27023.4 | 0 | 162140.4 | 0 | 0 | 162140.4 | 0 | 1432007.2 | 1269866.8 | 730133.2 | 0 | 1269866.8 | 1850 | 0 | 16666.6667 | 730133.2 | 162140.4 | 0
8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 7.75 | 9 | 107875 | 0 | 0 | 1250 | 392 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2242 | 22023.4 | 0 | 132140.4 | 0 | 0 | 132140.4 | 0 | 1269866.8 | 1137726.4 | 862273.6 | 0 | 1137726.4 | 1850 | 0 | 16666.6667 | 862273.6 | 132140.4 | 0
9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 10 | 118375 | 12000 | 3500 | 1250 | 441 | 0 | 0 | 0 | 12000 | 600 | 100 | 0 | 0 | 0 | 0 | 14391 | 29653.2 | 0 | 177919.2 | 0 | 0 | 177919.2 | 0 | 1137726.4 | 959807.2 | 1040192.8 | 0 | 959807.2 | 13850 | 0 | 16666.6667 | 1040192.8 | 177919.2 | 0
10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 10 | 118375 | 0 | 0 | 1250 | 441 | 0 | 18000 | 0 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 20391 | 27753.2 | 0 | 166519.2 | 0 | 0 | 166519.2 | 6000000 | 959807.2 | 6793288 | 1206712 | 0 | 6793288 | 19850 | 0 | 16666.6667 | 1206712 | 166519.2 | 0
11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 8.75 | 10 | 118375 | 0 | 0 | 1250 | 441 | 0 | 0 | 15000 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 17391 | 27153.2 | 0 | 162919.2 | 0 | 0 | 162919.2 | 0 | 6793288 | 6630368.8 | 1369631.2 | 0 | 6630368.8 | 16850 | 0 | 16666.6667 | 1369631.2 | 162919.2 | 0
12 | 2027-10-01 | 2 | 2 | 50 | 0.375 | 20 | 4 | 8.75 | 10 | 118375 | 0 | 0 | 1284.25 | 441 | 0 | 0 | 0 | 0 | 600 | 100 | 150 | 600 | 0 | 0 | 3175.25 | 24310.05 | 84 | 145944.3 | 2800 | 33600 | 143144.3 | 0 | 6630368.8 | 6487224.5 | 1515575.5 | 0 | 6484424.5 | 1850 | 0 | 16666.6667 | 1512775.5 | 145944.3 | 0
13 | 2027-11-01 | 2 | 3.98 | 99.5 | 0.74625 | 39.8 | 7.96 | 8.75 | 10 | 124293.75 | 0 | 0 | 1370.8838 | 458.64 | 0 | 0 | 0 | 0 | 624 | 104 | 310.44 | 624 | 0 | 0 | 3491.9638 | 25557.1428 | 167.16 | 153510.0166 | 5572 | 66864 | 147938.0166 | 0 | 6487224.5 | 6339286.4834 | 1669085.5166 | 0 | 6330914.4834 | 1924 | 0 | 17500 | 1660713.5166 | 153510.0166 | 0
14 | 2027-12-01 | 2 | 5.9402 | 148.505 | 1.1138 | 59.402 | 11.8804 | 8.75 | 10 | 124293.75 | 0 | 0 | 1405.795 | 458.64 | 12480 | 0 | 0 | 0 | 624 | 104 | 463.3356 | 624 | 0 | 0 | 16159.7706 | 28090.7041 | 249.4884 | 168793.7131 | 8316.28 | 99795.36 | 160477.4331 | 0 | 6339286.4834 | 6178809.0504 | 1837879.2296 | 0 | 6162120.7704 | 14404 | 0 | 17500 | 1821190.9496 | 168793.7131 | 0
15 | 2028-01-01 | 2 | 7.8808 | 197.0199 | 1.4776 | 78.808 | 15.7616 | 8.75 | 10 | 124293.75 | 0 | 0 | 1440.357 | 458.64 | 0 | 0 | 0 | 0 | 624 | 104 | 614.7022 | 624 | 0 | 0 | 3865.6993 | 25631.8899 | 330.9935 | 154122.3326 | 11033.1172 | 132397.4064 | 143089.2154 | 0 | 6178809.0504 | 6035719.8349 | 1992001.5623 | 0 | 6007998.4377 | 1924 | 0 | 17500 | 1964280.1651 | 154122.3326 | 0
16 | 2028-02-01 | 2 | 9.802 | 245.0498 | 1.8379 | 98.0199 | 19.604 | 14.5 | 15 | 209781.25 | 60000 | 20125 | 1474.5734 | 764.4 | 0 | 0 | 0 | 0 | 624 | 104 | 764.5552 | 624 | 0 | 0 | 4355.5287 | 58852.3557 | 411.6836 | 353525.818 | 13722.786 | 164673.4323 | 339803.0319 | 0 | 6035719.8349 | 5695916.803 | 2345527.3802 | 0 | 5654472.6198 | 1924 | 0 | 17500 | 2304083.197 | 353525.818 | 0
17 | 2028-03-01 | 2 | 11.704 | 292.5993 | 2.1945 | 117.0397 | 23.4079 | 14.5 | 15 | 209781.25 | 0 | 0 | 1508.4477 | 764.4 | 0 | 0 | 0 | 0 | 624 | 104 | 912.9097 | 624 | 0 | 0 | 4537.7574 | 42863.8015 | 491.5667 | 257674.3756 | 16385.5582 | 196626.698 | 241288.8174 | 0 | 5695916.803 | 5454627.9856 | 2603201.7558 | 0 | 5396798.2442 | 1924 | 0 | 17500 | 2545372.0144 | 257674.3756 | 0
18 | 2028-04-01 | 2 | 13.5869 | 339.6733 | 2.5475 | 135.8693 | 27.1739 | 14.5 | 15 | 209781.25 | 0 | 0 | 1541.9832 | 764.4 | 0 | 0 | 0 | 0 | 624 | 104 | 1059.7806 | 624 | 0 | 0 | 4718.1638 | 42899.8828 | 570.6511 | 257969.9476 | 19021.7026 | 228260.431 | 238948.2451 | 0 | 5454627.9856 | 5215679.7405 | 2861171.7035 | 0 | 5138828.2965 | 1924 | 0 | 17500 | 2784320.2595 | 257969.9476 | 0
19 | 2028-05-01 | 2 | 15.4511 | 386.2765 | 2.8971 | 154.5106 | 30.9021 | 14.5 | 15 | 209781.25 | 0 | 0 | 1575.1834 | 764.4 | 0 | 0 | 0 | 0 | 624 | 104 | 1205.1828 | 624 | 0 | 0 | 4896.7662 | 42935.6032 | 648.9446 | 258262.564 | 21631.4856 | 259577.8267 | 236631.0784 | 0 | 5215679.7405 | 4979048.6621 | 3119434.2674 | 0 | 4880565.7326 | 1924 | 0 | 17500 | 3020951.3379 | 258262.564 | 0
20 | 2028-06-01 | 2 | 17.2966 | 432.4138 | 3.2431 | 172.9655 | 34.5931 | 14.5 | 15 | 209781.25 | 0 | 0 | 1608.0516 | 764.4 | 0 | 0 | 0 | 0 | 624 | 104 | 1349.1309 | 624 | 0 | 0 | 5073.5825 | 42970.9665 | 726.4551 | 258552.2541 | 24215.1707 | 290582.0485 | 234337.0834 | 0 | 4979048.6621 | 4744711.5787 | 3377986.5216 | 0 | 4622013.4784 | 1924 | 0 | 17500 | 3255288.4213 | 258552.2541 | 0
21 | 2028-07-01 | 2 | 19.1236 | 478.0896 | 3.5857 | 191.2358 | 38.2472 | 14.5 | 15 | 209781.25 | 0 | 0 | 1640.591 | 764.4 | 0 | 0 | 0 | 12480 | 624 | 104 | 1491.6396 | 624 | 0 | 0 | 17728.6307 | 45501.9761 | 803.1906 | 273815.0474 | 26773.019 | 321276.228 | 247042.0284 | 0 | 4744711.5787 | 4497669.5503 | 3651801.5689 | 0 | 4348198.4311 | 14404 | 0 | 17500 | 3502330.4497 | 273815.0474 | 0
22 | 2028-08-01 | 2 | 20.9323 | 523.3087 | 3.9248 | 209.3235 | 41.8647 | 14.5 | 15 | 209781.25 | 0 | 0 | 1672.8051 | 764.4 | 0 | 18720 | 0 | 0 | 624 | 104 | 1632.7232 | 624 | 0 | 0 | 24141.9284 | 46784.6357 | 879.1587 | 281586.9727 | 29305.2888 | 351663.4657 | 252281.6839 | 0 | 4497669.5503 | 4245387.8664 | 3933388.5417 | 0 | 4066611.4583 | 20644 | 0 | 17500 | 3754612.1336 | 281586.9727 | 0
23 | 2028-09-01 | 2 | 22.723 | 568.0756 | 4.2606 | 227.2303 | 45.4461 | 14.5 | 15 | 209781.25 | 0 | 0 | 1704.6971 | 764.4 | 0 | 0 | 15600 | 0 | 624 | 104 | 1772.396 | 624 | 0 | 0 | 21193.4931 | 46194.9486 | 954.3671 | 278124.0588 | 31812.2359 | 381746.831 | 246311.8229 | 0 | 4245387.8664 | 3999076.0435 | 4211512.6004 | 0 | 3788487.3996 | 17524 | 0 | 17500 | 4000923.9565 | 278124.0588 | 0
24 | 2028-10-01 | 3.4 | 25.8958 | 647.3949 | 4.8555 | 258.958 | 51.7916 | 14.5 | 15 | 209781.25 | 0 | 0 | 1761.2041 | 764.4 | 0 | 0 | 0 | 0 | 624 | 104 | 2019.872 | 1060.8 | 0 | 0 | 6334.2762 | 43223.1052 | 1087.6234 | 260426.2548 | 36254.1136 | 435049.3627 | 224172.1412 | 0 | 3999076.0435 | 3774903.9023 | 4471938.8552 | 0 | 3528061.1448 | 1924 | 0 | 17500 | 4225096.0977 | 260426.2548 | 0
25 | 2028-11-01 | 3.4 | 29.0368 | 725.9209 | 5.4444 | 290.3684 | 58.0737 | 14.5 | 15 | 220270.3125 | 0 | 0 | 1889.8319 | 794.976 | 0 | 0 | 0 | 0 | 648.96 | 108.16 | 2355.4683 | 1103.232 | 0 | 0 | 6900.6282 | 45434.1881 | 1219.5472 | 273824.676 | 40651.5724 | 487818.8691 | 233173.1036 | 0 | 3774903.9023 | 3541730.7987 | 4745763.5312 | 0 | 3254236.4688 | 2000.96 | 0 | 18375 | 4458269.2013 | 273824.676 | 0
26 | 2028-12-01 | 3.4 | 32.1465 | 803.6617 | 6.0275 | 321.4647 | 64.2929 | 14.5 | 15 | 220270.3125 | 0 | 0 | 1947.4298 | 794.976 | 12979.2 | 0 | 0 | 0 | 648.96 | 108.16 | 2607.7216 | 1103.232 | 0 | 0 | 20189.6793 | 48091.9984 | 1350.1517 | 289902.1419 | 45005.0567 | 540060.6804 | 244897.0852 | 0 | 3541730.7987 | 3296833.7135 | 5035665.6731 | 0 | 2964334.3269 | 14980.16 | 0 | 18375 | 4703166.2865 | 289902.1419 | 0
27 | 2029-01-01 | 3.4 | 35.225 | 880.6251 | 6.6047 | 352.25 | 70.45 | 14.5 | 15 | 220270.3125 | 0 | 0 | 2004.4516 | 794.976 | 0 | 0 | 0 | 0 | 648.96 | 108.16 | 2857.4524 | 1103.232 | 0 | 0 | 7517.232 | 45557.5089 | 1479.4502 | 274824.5036 | 49315.0061 | 591780.0736 | 225509.4974 | 0 | 3296833.7135 | 3071324.2161 | 5310490.1767 | 0 | 2689509.8233 | 2000.96 | 0 | 18375 | 4928675.7839 | 274824.5036 | 0
28 | 2029-02-01 | 3.4 | 38.2728 | 956.8189 | 7.1761 | 382.7275 | 76.5455 | 14.5 | 15 | 220270.3125 | 0 | 0 | 2060.9033 | 794.976 | 0 | 0 | 0 | 0 | 648.96 | 108.16 | 3104.6858 | 1103.232 | 0 | 0 | 7820.9171 | 45618.2459 | 1607.4557 | 275316.9312 | 53581.8561 | 642982.2729 | 221735.0751 | 0 | 3071324.2161 | 2849589.141 | 5585807.1079 | 0 | 2414192.8921 | 2000.96 | 0 | 18375 | 5150410.859 | 275316.9312 | 0
29 | 2029-03-01 | 3.4 | 41.29 | 1032.2507 | 7.7419 | 412.9003 | 82.5801 | 14.5 | 15 | 220270.3125 | 0 | 0 | 2116.7904 | 794.976 | 0 | 0 | 0 | 0 | 648.96 | 108.16 | 3349.447 | 1103.232 | 0 | 0 | 8121.5654 | 45678.3756 | 1734.1811 | 275804.4346 | 57806.0375 | 693672.4501 | 217998.3971 | 0 | 2849589.141 | 2631590.7439 | 5861611.5424 | 0 | 2138388.4576 | 2000.96 | 0 | 18375 | 5368409.2561 | 275804.4346 | 0
30 | 2029-04-01 | 3.4 | 44.2771 | 1106.9282 | 8.302 | 442.7713 | 88.5543 | 14.5 | 15 | 220270.3125 | 0 | 0 | 2172.1186 | 794.976 | 0 | 0 | 0 | 0 | 648.96 | 108.16 | 3591.7605 | 1103.232 | 0 | 0 | 8419.2072 | 45737.9039 | 1859.6393 | 276287.0629 | 61987.9771 | 743855.7256 | 214299.0858 | 0 | 2631590.7439 | 2417291.6582 | 6137898.6053 | 0 | 1862101.3947 | 2000.96 | 0 | 18375 | 5582708.3418 | 276287.0629 | 0
31 | 2029-05-01 | 3.4 | 47.2344 | 1180.8589 | 8.8564 | 472.3436 | 94.4687 | 23 | 23 | 350135.625 | 84000 | 29750 | 2226.8936 | 1218.9632 | 0 | 0 | 0 | 0 | 648.96 | 108.16 | 3831.6509 | 1103.232 | 0 | 0 | 9137.8597 | 94604.6969 | 1983.8429 | 569612.0246 | 66128.0974 | 793537.1684 | 503483.9272 | 0 | 2417291.6582 | 1913807.731 | 6707510.6299 | 0 | 1292489.3701 | 2000.96 | 0 | 18375 | 6086192.269 | 569612.0246 | 0
32 | 2029-06-01 | 3.4 | 50.162 | 1254.0503 | 9.4054 | 501.6201 | 100.324 | 23 | 23 | 350135.625 | 0 | 0 | 2281.1208 | 1218.9632 | 0 | 0 | 0 | 0 | 648.96 | 108.16 | 4069.1424 | 1103.232 | 0 | 0 | 9429.5784 | 71913.0407 | 2106.8045 | 433585.0486 | 70226.8164 | 842721.7967 | 363358.2322 | 0 | 1913807.731 | 1550449.4987 | 7141095.6785 | 0 | 858904.3215 | 2000.96 | 0 | 18375 | 6449550.5013 | 433585.0486 | 0
33 | 2029-07-01 | 3.4 | 53.0604 | 1326.5098 | 9.9488 | 530.6039 | 106.1208 | 23 | 23 | 350135.625 | 0 | 0 | 2334.8058 | 1218.9632 | 0 | 0 | 0 | 12979.2 | 648.96 | 108.16 | 4304.259 | 1103.232 | 0 | 0 | 22697.58 | 74566.641 | 2228.5364 | 449628.3824 | 74284.5482 | 891414.5787 | 375343.8342 | 0 | 1550449.4987 | 1175105.6646 | 7590724.0609 | 0 | 409275.9391 | 14980.16 | 0 | 18375 | 6824894.3354 | 449628.3824 | 0
34 | 2029-08-01 | 3.4 | 55.9298 | 1398.2447 | 10.4868 | 559.2979 | 111.8596 | 23 | 23 | 350135.625 | 0 | 0 | 2387.9539 | 1218.9632 | 0 | 19468.8 | 0 | 0 | 648.96 | 108.16 | 4537.0244 | 1103.232 | 0 | 0 | 29473.0935 | 75921.7437 | 2349.0511 | 457879.5133 | 78301.7027 | 939620.4329 | 379577.8105 | 0 | 1175105.6646 | 795527.8541 | 8048603.5742 | 0 | -48603.5742 | 21469.76 | 0 | 18375 | 7204472.1459 | 457879.5133 | 0
35 | 2029-09-01 | 3.4 | 58.7705 | 1469.2622 | 11.0195 | 587.7049 | 117.541 | 23 | 23 | 350135.625 | 0 | 0 | 2440.5705 | 1218.9632 | 0 | 0 | 16224 | 0 | 648.96 | 108.16 | 4767.4621 | 1103.232 | 0 | 0 | 26511.3479 | 75329.3946 | 2468.3606 | 454444.728 | 82278.6857 | 987344.2286 | 372166.0423 | 0 | 795527.8541 | 423361.8118 | 8503048.3022 | 0 | -503048.3022 | 18224.96 | 0 | 18375 | 7576638.1882 | 454444.728 | 0
36 | 2029-10-01 | 5.78 | 63.9628 | 1599.0696 | 11.993 | 639.6278 | 127.9256 | 23 | 23 | 350135.625 | 0 | 0 | 2536.7443 | 1218.9632 | 0 | 0 | 0 | 0 | 648.96 | 108.16 | 5188.6611 | 1875.4944 | 0 | 0 | 11576.983 | 72342.5216 | 2686.437 | 436741.5666 | 89547.8989 | 1074574.7863 | 347193.6677 | 0 | 423361.8118 | 76168.1441 | 8939789.8687 | 0 | -939789.8687 | 2000.96 | 0 | 18375 | 7923831.8559 | 436741.5666 | 0
37 | 2029-11-01 | 5.78 | 69.1032 | 1727.5789 | 12.9568 | 691.0316 | 138.2063 | 23 | 23 | 367642.4062 | 0 | 0 | 2737.2346 | 1267.7217 | 0 | 0 | 0 | 0 | 674.9184 | 112.4864 | 5829.874 | 1950.5142 | 0 | 0 | 12572.7493 | 76043.0311 | 2902.3326 | 459160.5193 | 96744.4199 | 1160933.0385 | 362416.0994 | 0 | 76168.1441 | -286247.9553 | 9398950.388 | 286247.9553 | -1398950.388 | 2080.9984 | 0 | 19293.75 | 8286247.9553 | 459160.5193 | 1
38 | 2029-12-01 | 5.78 | 74.1921 | 1854.8031 | 13.911 | 741.9213 | 148.3843 | 23 | 23 | 367642.4062 | 0 | 0 | 2835.2649 | 1267.7217 | 13498.368 | 0 | 0 | 0 | 674.9184 | 112.4864 | 6259.2038 | 1950.5142 | 0 | 0 | 26598.4774 | 78848.1767 | 3116.0693 | 476205.1297 | 103868.9757 | 1246427.7081 | 372336.154 | 0 | -286247.9553 | -658584.1093 | 9875155.5177 | 658584.1093 | -1875155.5177 | 15579.3664 | 0 | 19293.75 | 8658584.1093 | 476205.1297 | 1
39 | 2030-01-01 | 5.78 | 79.2302 | 1980.7551 | 14.8557 | 792.302 | 158.4604 | 23 | 23 | 367642.4062 | 0 | 0 | 2932.3149 | 1267.7217 | 0 | 0 | 0 | 0 | 674.9184 | 112.4864 | 6684.2403 | 1950.5142 | 0 | 0 | 13622.1959 | 76252.9204 | 3327.6686 | 460845.1912 | 110922.2859 | 1331067.431 | 349922.9053 | 0 | -658584.1093 | -1008507.0145 | 10336000.7088 | 1008507.0145 | -2336000.7088 | 2080.9984 | 0 | 19293.75 | 9008507.0145 | 460845.1912 | 1
40 | 2030-02-01 | 5.78 | 84.2179 | 2105.4476 | 15.7909 | 842.179 | 168.4358 | 23 | 23 | 367642.4062 | 0 | 0 | 3028.3944 | 1267.7217 | 0 | 0 | 0 | 0 | 674.9184 | 112.4864 | 7105.0265 | 1950.5142 | 0 | 0 | 14139.0616 | 76356.2936 | 3537.1519 | 461674.9133 | 117905.0631 | 1414860.7567 | 343769.8502 | 0 | -1008507.0145 | -1352276.8648 | 10797675.6221 | 1352276.8648 | -2797675.6221 | 2080.9984 | 0 | 19293.75 | 9352276.8648 | 461674.9133 | 1
41 | 2030-03-01 | 5.78 | 89.1557 | 2228.8931 | 16.7167 | 891.5572 | 178.3114 | 23 | 23 | 367642.4062 | 0 | 0 | 3123.5131 | 1267.7217 | 0 | 0 | 0 | 0 | 674.9184 | 112.4864 | 7521.6048 | 1950.5142 | 0 | 0 | 14650.7585 | 76458.633 | 3744.5404 | 462496.3381 | 124818.0124 | 1497816.1491 | 337678.3257 | 0 | -1352276.8648 | -1689955.1904 | 11260171.9602 | 1689955.1904 | -3260171.9602 | 2080.9984 | 0 | 19293.75 | 9689955.1904 | 462496.3381 | 1
42 | 2030-04-01 | 5.78 | 94.0442 | 2351.1041 | 17.6333 | 940.4417 | 188.0883 | 23 | 23 | 367642.4062 | 0 | 0 | 3217.6806 | 1267.7217 | 0 | 0 | 0 | 0 | 674.9184 | 112.4864 | 7934.0172 | 1950.5142 | 0 | 0 | 15157.3386 | 76559.949 | 3949.855 | 463309.5487 | 131661.8323 | 1579941.9876 | 331647.7164 | 0 | -1689955.1904 | -2021602.9069 | 11723481.509 | 2021602.9069 | -3723481.509 | 2080.9984 | 0 | 19293.75 | 10021602.9069 | 463309.5487 | 1
43 | 2030-05-01 | 5.78 | 98.8837 | 2472.0931 | 18.5407 | 988.8372 | 197.7674 | 23 | 23 | 367642.4062 | 0 | 0 | 3310.9065 | 1267.7217 | 0 | 0 | 0 | 0 | 674.9184 | 112.4864 | 8342.3056 | 1950.5142 | 0 | 0 | 15658.8528 | 76660.2518 | 4153.1164 | 464114.6273 | 138437.214 | 1661246.5678 | 325677.4133 | 0 | -2021602.9069 | -2347280.3202 | 12187596.1362 | 2347280.3202 | -4187596.1362 | 2080.9984 | 0 | 19293.75 | 10347280.3202 | 464114.6273 | 1
44 | 2030-06-01 | 5.78 | 103.6749 | 2591.8722 | 19.439 | 1036.7489 | 207.3498 | 23 | 23 | 367642.4062 | 0 | 0 | 3403.2 | 1267.7217 | 0 | 0 | 0 | 0 | 674.9184 | 112.4864 | 8746.5111 | 1950.5142 | 0 | 0 | 16155.3518 | 76759.5516 | 4354.3453 | 464911.655 | 145144.8418 | 1741738.1021 | 319766.8131 | 0 | -2347280.3202 | -2667047.1333 | 12652507.7912 | 2667047.1333 | -4652507.7912 | 2080.9984 | 0 | 19293.75 | 10667047.1333 | 464911.655 | 1
45 | 2030-07-01 | 5.78 | 108.4181 | 2710.4535 | 20.3284 | 1084.1814 | 216.8363 | 23 | 23 | 367642.4062 | 0 | 0 | 3494.5707 | 1267.7217 | 0 | 0 | 0 | 13498.368 | 674.9184 | 112.4864 | 9146.6745 | 1950.5142 | 0 | 0 | 30145.2539 | 79557.532 | 4553.5618 | 481898.754 | 151785.3934 | 1821424.7211 | 330113.3606 | 0 | -2667047.1333 | -2997160.4939 | 13134406.5452 | 2997160.4939 | -5134406.5452 | 15579.3664 | 0 | 19293.75 | 10997160.4939 | 481898.754 | 1
46 | 2030-08-01 | 5.78 | 113.114 | 2827.8489 | 21.2089 | 1131.1396 | 226.2279 | 23 | 23 | 367642.4062 | 0 | 0 | 3585.0276 | 1267.7217 | 0 | 20247.552 | 0 | 0 | 674.9184 | 112.4864 | 9542.8363 | 1950.5142 | 0 | 0 | 37381.0567 | 81004.6926 | 4750.7862 | 490778.9417 | 158359.5395 | 1900314.4738 | 332419.4022 | 0 | -2997160.4939 | -3329579.8961 | 13625185.4869 | 3329579.8961 | -5625185.4869 | 22328.5504 | 0 | 19293.75 | 11329579.8961 | 490778.9417 | 1
47 | 2030-09-01 | 5.78 | 117.7628 | 2944.0704 | 22.0805 | 1177.6282 | 235.5256 | 23 | 23 | 367642.4062 | 0 | 0 | 3674.58 | 1267.7217 | 0 | 0 | 16872.96 | 0 | 674.9184 | 112.4864 | 9935.0365 | 1950.5142 | 0 | 0 | 34488.2172 | 80426.1247 | 4946.0383 | 487502.7865 | 164867.9441 | 1978415.3291 | 322634.8424 | 0 | -3329579.8961 | -3652214.7385 | 14112688.2734 | 3652214.7385 | -6112688.2734 | 18953.9584 | 0 | 19293.75 | 11652214.7385 | 487502.7865 | 1
48 | 2030-10-01 | 9.826 | 126.4112 | 3160.2797 | 23.7021 | 1264.1119 | 252.8224 | 23 | 23 | 367642.4062 | 0 | 0 | 3841.1762 | 1267.7217 | 0 | 0 | 0 | 0 | 674.9184 | 112.4864 | 10664.6547 | 3315.8741 | 0 | 0 | 19876.8315 | 77503.8475 | 5309.2699 | 470332.3552 | 176975.6647 | 2123707.9758 | 293356.6905 | 0 | -3652214.7385 | -3945571.4291 | 14583020.6286 | 3945571.4291 | -6583020.6286 | 2080.9984 | 0 | 19293.75 | 11945571.4291 | 470332.3552 | 1
49 | 2030-11-01 | 9.826 | 134.9731 | 3374.3269 | 25.3075 | 1349.7308 | 269.9462 | 23 | 23 | 386024.5266 | 0 | 0 | 4166.3506 | 1318.4306 | 0 | 0 | 0 | 0 | 701.9151 | 116.9859 | 11842.4557 | 3448.5091 | 0 | 0 | 21594.647 | 81523.8347 | 5668.8692 | 494811.8775 | 188962.308 | 2267547.6961 | 305849.5695 | 0 | -3945571.4291 | -4251420.9985 | 15077832.5061 | 4251420.9985 | -7077832.5061 | 2164.2383 | 0 | 20258.4375 | 12251420.9985 | 494811.8775 | 1
50 | 2030-12-01 | 9.826 | 143.4493 | 3586.2337 | 26.8968 | 1434.4935 | 286.8987 | 23 | 23 | 386024.5266 | 0 | 0 | 4336.1627 | 1318.4306 | 14038.3027 | 0 | 0 | 0 | 701.9151 | 116.9859 | 12586.1584 | 3448.5091 | 0 | 0 | 36546.4645 | 84514.1982 | 6024.8725 | 513110.0618 | 200829.0849 | 2409949.0191 | 312280.9769 | 0 | -4251420.9985 | -4563701.9754 | 15590942.5679 | 4563701.9754 | -7590942.5679 | 16202.5411 | 0 | 20258.4375 | 12563701.9754 | 513110.0618 | 1
51 | 2031-01-01 | 9.826 | 151.8409 | 3796.0213 | 28.4702 | 1518.4085 | 303.6817 | 23 | 23 | 386024.5266 | 0 | 0 | 4504.2767 | 1318.4306 | 0 | 0 | 0 | 0 | 701.9151 | 116.9859 | 13322.4241 | 3448.5091 | 0 | 0 | 23412.5415 | 81887.4136 | 6377.3158 | 497701.7975 | 212577.1941 | 2550926.3289 | 285124.6034 | 0 | -4563701.9754 | -4848826.5788 | 16088644.3654 | 4848826.5788 | -8088644.3654 | 2164.2383 | 0 | 20258.4375 | 12848826.5788 | 497701.7975 | 1
52 | 2031-02-01 | 9.826 | 160.1484 | 4003.7111 | 30.0278 | 1601.4844 | 320.2969 | 23 | 23 | 386024.5266 | 0 | 0 | 4670.7096 | 1318.4306 | 0 | 0 | 0 | 0 | 701.9151 | 116.9859 | 14051.3271 | 3448.5091 | 0 | 0 | 24307.8774 | 82066.4808 | 6726.2347 | 499125.1194 | 224207.8221 | 2690493.8656 | 274917.2972 | 0 | -4848826.5788 | -5123743.8761 | 16587769.4847 | 5123743.8761 | -8587769.4847 | 2164.2383 | 0 | 20258.4375 | 13123743.8761 | 499125.1194 | 1
53 | 2031-03-01 | 9.826 | 168.373 | 4209.324 | 31.5699 | 1683.7296 | 336.7459 | 23 | 23 | 386024.5266 | 0 | 0 | 4835.4781 | 1318.4306 | 0 | 0 | 0 | 0 | 701.9151 | 116.9859 | 14772.9411 | 3448.5091 | 0 | 0 | 25194.2599 | 82243.7573 | 7071.6643 | 500534.208 | 235722.1439 | 2828665.727 | 264812.0641 | 0 | -5123743.8761 | -5388555.9402 | 17088303.6928 | 5388555.9402 | -9088303.6928 | 2164.2383 | 0 | 20258.4375 | 13388555.9402 | 500534.208 | 1
54 | 2031-04-01 | 9.826 | 176.5152 | 4412.8808 | 33.0966 | 1765.1523 | 353.0305 | 23 | 23 | 386024.5266 | 0 | 0 | 4998.5989 | 1318.4306 | 0 | 0 | 0 | 0 | 701.9151 | 116.9859 | 15487.339 | 3448.5091 | 0 | 0 | 26071.7786 | 82419.261 | 7413.6397 | 501929.2058 | 247121.3225 | 2965455.8697 | 254807.8834 | 0 | -5388555.9402 | -5643363.8236 | 17590232.8986 | 5643363.8236 | -9590232.8986 | 2164.2383 | 0 | 20258.4375 | 13643363.8236 | 501929.2058 | 1
55 | 2031-05-01 | 9.826 | 184.5761 | 4614.402 | 34.608 | 1845.7608 | 369.1522 | 23 | 23 | 386024.5266 | 0 | 0 | 5160.0886 | 1318.4306 | 0 | 0 | 0 | 0 | 701.9151 | 116.9859 | 16194.5929 | 3448.5091 | 0 | 0 | 26940.5221 | 82593.0097 | 7752.1953 | 503310.2537 | 258406.5092 | 3100878.111 | 244903.7444 | 0 | -5643363.8236 | -5888267.568 | 18093543.1523 | 5888267.568 | -10093543.1523 | 2164.2383 | 0 | 20258.4375 | 13888267.568 | 503310.2537 | 1
56 | 2031-06-01 | 9.826 | 192.5563 | 4813.9079 | 36.1043 | 1925.5632 | 385.1126 | 23 | 23 | 386024.5266 | 0 | 0 | 5319.9633 | 1318.4306 | 0 | 0 | 0 | 0 | 701.9151 | 116.9859 | 16894.7742 | 3448.5091 | 0 | 0 | 27800.5782 | 82765.0209 | 8087.3653 | 504677.491 | 269578.8442 | 3234946.1299 | 235098.6468 | 0 | -5888267.568 | -6123366.2148 | 18598220.6433 | 6123366.2148 | -10598220.6433 | 2164.2383 | 0 | 20258.4375 | 14123366.2148 | 504677.491 | 1
57 | 2031-07-01 | 9.826 | 200.4568 | 5011.4189 | 37.5856 | 2004.5675 | 400.9135 | 23 | 23 | 386024.5266 | 0 | 0 | 5478.2393 | 1318.4306 | 0 | 0 | 0 | 14038.3027 | 701.9151 | 116.9859 | 17587.9537 | 3448.5091 | 0 | 0 | 42690.3364 | 85742.9726 | 8419.1837 | 522877.0192 | 280639.4557 | 3367673.4686 | 242237.5635 | 0 | -6123366.2148 | -6365603.7783 | 19121097.6625 | 6365603.7783 | -11121097.6625 | 16202.5411 | 0 | 20258.4375 | 14365603.7783 | 522877.0192 | 1
58 | 2031-08-01 | 9.826 | 208.2782 | 5206.9547 | 39.0522 | 2082.7819 | 416.5564 | 23 | 23 | 386024.5266 | 0 | 0 | 5634.9325 | 1318.4306 | 0 | 21057.4541 | 0 | 0 | 701.9151 | 116.9859 | 18274.2015 | 3448.5091 | 0 | 0 | 50552.4287 | 87315.3911 | 8747.6838 | 532640.0302 | 291589.4612 | 3499073.5339 | 241050.569 | 0 | -6365603.7783 | -6606654.3473 | 19653737.6927 | 6606654.3473 | -11653737.6927 | 23221.6924 | 0 | 20258.4375 | 14606654.3473 | 532640.0302 | 1
59 | 2031-09-01 | 9.826 | 216.0214 | 5400.5351 | 40.504 | 2160.214 | 432.0428 | 23 | 23 | 386024.5266 | 0 | 0 | 5790.0588 | 1318.4306 | 0 | 0 | 17547.8784 | 0 | 701.9151 | 116.9859 | 18953.5867 | 3448.5091 | 0 | 0 | 47877.3646 | 86780.3782 | 9072.899 | 529755.1684 | 302429.9665 | 3629159.5986 | 227325.2018 | 0 | -6606654.3473 | -6833979.5492 | 20183492.861 | 6833979.5492 | -12183492.861 | 19712.1167 | 0 | 20258.4375 | 14833979.5492 | 529755.1684 | 1
60 | 2031-10-01 | 16.7042 | 230.5654 | 5764.1348 | 43.231 | 2305.6539 | 461.1308 | 23 | 23 | 386024.5266 | 0 | 0 | 6081.4305 | 1318.4306 | 0 | 0 | 0 | 0 | 701.9151 | 116.9859 | 20229.6672 | 5862.4654 | 0 | 0 | 34310.8947 | 84067.0843 | 9683.7464 | 514086.252 | 322791.5469 | 3873498.5626 | 191294.7051 | 0 | -6833979.5492 | -7025274.2542 | 20697579.113 | 7025274.2542 | -12697579.113 | 2164.2383 | 0 | 20258.4375 | 15025274.2542 | 514086.252 | 1
Formulas:
Date = EDATE('Start Here'!$B6,[Month]-1)

## Monthly Model
Selected scenario ¦ monthly cash and workload
Select scenario on Start Here. Grouped columns expand to show workload/category detail. Financing is hypothetical. Cost-only cash keeps forecast usage/costs but removes revenue receipts (conservative sensitivity).
← Start Here
Month | Date | New customers | Active customers | Users | API requests M | Storage GB | Logs GB | Total FTE | Headcount slots | Staff cash | Recruiting | Equipment | INFRA | TOOLS | LEGAL | SECURITY | COMPLIANCE | INSURANCE | ACCOUNTING | SUPPORT | MARKETING | ONBOARD | AI | CTMS | Vendor total | Contingency | Payment fees | Total spend | Monthly revenue | Exit ARR | Net burn | Financing | Opening cash | Closing cash | Cumulative spend | Funding gap | Cash if zero revenue | Unresolved vendor cash | Optional vendor cash | Unpaid founder economic | Cumulative net need | Cost-only burn | Negative flag
1 | 2026-11-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 19250 | 8000 | 6000 | 1250 | 98 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 1948 | 5279.7 | 0 | 40477.7 | 0 | 0 | 40477.7 | 0 | 1000000 | 959522.3 | 40477.7 | 0 | 959522.3 | 1850 | 0 | 15000 | 40477.7 | 40477.7 | 0
2 | 2026-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 2.65 | 5 | 28416.6667 | 0 | 1950 | 1250 | 147 | 20000 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 21997 | 7854.55 | 0 | 60218.2167 | 0 | 0 | 60218.2167 | 0 | 959522.3 | 899304.0833 | 100695.9167 | 0 | 899304.0833 | 21850 | 0 | 15000 | 100695.9167 | 60218.2167 | 0
3 | 2027-01-01 | 0 | 0 | 0 | 0 | 0 | 0 | 3.65 | 6 | 45333.3333 | 8000 | 3000 | 1250 | 196 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2046 | 8756.9 | 0 | 67136.2333 | 0 | 0 | 67136.2333 | 0 | 899304.0833 | 832167.85 | 167832.15 | 0 | 832167.85 | 1850 | 0 | 15000 | 167832.15 | 67136.2333 | 0
4 | 2027-02-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.65 | 8 | 59916.6667 | 8000 | 3000 | 1250 | 245 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2095 | 10951.75 | 0 | 83963.4167 | 0 | 0 | 83963.4167 | 0 | 832167.85 | 748204.4333 | 251795.5667 | 0 | 748204.4333 | 1850 | 0 | 15000 | 251795.5667 | 83963.4167 | 0
5 | 2027-03-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.65 | 8 | 59916.6667 | 0 | 0 | 1250 | 245 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2095 | 9301.75 | 0 | 71313.4167 | 0 | 0 | 71313.4167 | 0 | 748204.4333 | 676891.0167 | 323108.9833 | 0 | 676891.0167 | 1850 | 0 | 15000 | 323108.9833 | 71313.4167 | 0
6 | 2027-04-01 | 0 | 0 | 0 | 0 | 0 | 0 | 4.65 | 8 | 59916.6667 | 0 | 0 | 1250 | 245 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2095 | 9301.75 | 0 | 71313.4167 | 0 | 0 | 71313.4167 | 0 | 676891.0167 | 605577.6 | 394422.4 | 0 | 605577.6 | 1850 | 0 | 15000 | 394422.4 | 71313.4167 | 0
7 | 2027-05-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76916.6667 | 6000 | 3300 | 1250 | 294 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2144 | 13254.1 | 0 | 101614.7667 | 0 | 0 | 101614.7667 | 0 | 605577.6 | 503962.8333 | 496037.1667 | 0 | 503962.8333 | 1850 | 0 | 15000 | 496037.1667 | 101614.7667 | 0
8 | 2027-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76916.6667 | 0 | 0 | 1250 | 294 | 0 | 0 | 0 | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 2144 | 11859.1 | 0 | 90919.7667 | 0 | 0 | 90919.7667 | 0 | 503962.8333 | 413043.0667 | 586956.9333 | 0 | 413043.0667 | 1850 | 0 | 15000 | 586956.9333 | 90919.7667 | 0
9 | 2027-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 5.75 | 8 | 76916.6667 | 0 | 0 | 1250 | 294 | 0 | 0 | 0 | 12000 | 600 | 100 | 0 | 0 | 0 | 0 | 14244 | 13674.1 | 0 | 104834.7667 | 0 | 0 | 104834.7667 | 0 | 413043.0667 | 308208.3 | 691791.7 | 0 | 308208.3 | 13850 | 0 | 15000 | 691791.7 | 104834.7667 | 0
10 | 2027-08-01 | 0 | 0 | 0 | 0 | 0 | 0 | 6.25 | 9 | 82166.6667 | 4000 | 1500 | 1250 | 343 | 0 | 18000 | 0 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 20293 | 16193.95 | 0 | 124153.6167 | 0 | 0 | 124153.6167 | 0 | 308208.3 | 184054.6833 | 815945.3167 | 0 | 184054.6833 | 19850 | 0 | 15000 | 815945.3167 | 124153.6167 | 0
11 | 2027-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 6.25 | 9 | 82166.6667 | 0 | 0 | 1250 | 343 | 0 | 0 | 15000 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 17293 | 14918.95 | 0 | 114378.6167 | 0 | 0 | 114378.6167 | 0 | 184054.6833 | 69676.0667 | 930323.9333 | 0 | 69676.0667 | 16850 | 0 | 15000 | 930323.9333 | 114378.6167 | 0
12 | 2027-10-01 | 0 | 0 | 0 | 0 | 0 | 0 | 6.25 | 9 | 82166.6667 | 0 | 0 | 1250 | 343 | 0 | 0 | 0 | 0 | 600 | 100 | 0 | 0 | 0 | 0 | 2293 | 12668.95 | 0 | 97128.6167 | 0 | 0 | 97128.6167 | 0 | 69676.0667 | -27452.55 | 1027452.55 | 27452.55 | -27452.55 | 1850 | 0 | 15000 | 1027452.55 | 97128.6167 | 1
13 | 2027-11-01 | 1 | 1 | 15 | 0.0675 | 5 | 1 | 6.25 | 9 | 85453.3333 | 0 | 0 | 1295.5083 | 353.29 | 0 | 0 | 0 | 0 | 618 | 103 | 77.25 | 309 | 0 | 0 | 2756.0482 | 13231.4072 | 27 | 101467.7888 | 900 | 10800 | 100567.7888 | 3000000 | -27452.55 | 2871979.6612 | 1128920.3388 | 0 | 2871079.6612 | 1905.5 | 0 | 15600 | 1128020.3388 | 101467.7888 | 0
14 | 2027-12-01 | 1 | 1.99 | 29.85 | 0.13432 | 9.95 | 1.99 | 6.25 | 9 | 85453.3333 | 0 | 0 | 1303.4364 | 353.29 | 12360 | 0 | 0 | 0 | 618 | 103 | 153.7275 | 309 | 0 | 0 | 15200.4539 | 15098.0681 | 53.73 | 115805.5853 | 1791 | 21492 | 114014.5853 | 0 | 2871979.6612 | 2757965.0758 | 1244725.9242 | 0 | 2755274.0758 | 14265.5 | 0 | 15600 | 1242034.9242 | 115805.5853 | 0
15 | 2028-01-01 | 1 | 2.9701 | 44.5515 | 0.20048 | 14.8505 | 2.9701 | 6.25 | 9 | 85453.3333 | 0 | 0 | 1311.2853 | 353.29 | 0 | 0 | 0 | 0 | 618 | 103 | 229.4402 | 309 | 0 | 0 | 2924.0155 | 13256.6023 | 80.1927 | 101714.1439 | 2673.09 | 32077.08 | 99041.0539 | 0 | 2757965.0758 | 2658924.0219 | 1346440.0681 | 0 | 2653559.9319 | 1905.5 | 0 | 15600 | 1341075.9781 | 101714.1439 | 0
16 | 2028-02-01 | 1 | 3.9404 | 59.106 | 0.26598 | 19.702 | 3.9404 | 8.25 | 10 | 115960 | 14000 | 6000 | 1319.0557 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 304.3958 | 309 | 0 | 0 | 3107.6815 | 20860.1522 | 106.3908 | 160034.2245 | 3546.3591 | 42556.3092 | 156487.8654 | 0 | 2658924.0219 | 2502436.1565 | 1506474.2926 | 0 | 2493525.7074 | 1905.5 | 0 | 15600 | 1497563.8435 | 160034.2245 | 0
17 | 2028-03-01 | 1 | 4.901 | 73.5149 | 0.33082 | 24.505 | 4.901 | 8.25 | 10 | 115960 | 0 | 0 | 1326.7484 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 378.6019 | 309 | 0 | 0 | 3189.5803 | 17872.437 | 132.3269 | 137154.3442 | 4410.8955 | 52930.7461 | 132743.4487 | 0 | 2502436.1565 | 2369692.7079 | 1643628.6367 | 0 | 2356371.3633 | 1905.5 | 0 | 15600 | 1630307.2921 | 137154.3442 | 0
18 | 2028-04-01 | 1 | 5.852 | 87.7798 | 0.39501 | 29.2599 | 5.852 | 8.25 | 10 | 115960 | 0 | 0 | 1334.3642 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 452.0658 | 309 | 0 | 0 | 3270.66 | 17884.599 | 158.0036 | 137273.2626 | 5266.7866 | 63201.4386 | 132006.476 | 0 | 2369692.7079 | 2237686.2318 | 1780901.8993 | 0 | 2219098.1007 | 1905.5 | 0 | 15600 | 1762313.7682 | 137273.2626 | 0
19 | 2028-05-01 | 1 | 6.7935 | 101.902 | 0.45856 | 33.9673 | 6.7935 | 8.75 | 11 | 123240 | 4000 | 1500 | 1341.9038 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 524.7952 | 309 | 0 | 0 | 3350.929 | 19813.6393 | 183.4236 | 152087.9919 | 6114.1187 | 73369.4243 | 145973.8732 | 0 | 2237686.2318 | 2091712.3587 | 1932989.8912 | 0 | 2067010.1088 | 1905.5 | 0 | 15600 | 1908287.6413 | 152087.9919 | 0
20 | 2028-06-01 | 1 | 7.7255 | 115.883 | 0.52147 | 38.6277 | 7.7255 | 8.75 | 11 | 123240 | 0 | 0 | 1349.368 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 596.7972 | 309 | 0 | 0 | 3430.3952 | 19000.5593 | 208.5893 | 145879.5438 | 6952.9775 | 83435.73 | 138926.5663 | 0 | 2091712.3587 | 1952785.7923 | 2078869.435 | 0 | 1921130.565 | 1905.5 | 0 | 15600 | 2047214.2077 | 145879.5438 | 0
21 | 2028-07-01 | 1 | 8.6483 | 129.7241 | 0.58376 | 43.2414 | 8.6483 | 8.75 | 11 | 123240 | 0 | 0 | 1356.7576 | 454.23 | 0 | 0 | 0 | 12360 | 618 | 103 | 668.0793 | 309 | 0 | 0 | 15869.0668 | 20866.36 | 233.5034 | 160208.9303 | 7783.4477 | 93401.3727 | 152425.4825 | 0 | 1952785.7923 | 1800360.3098 | 2239078.3653 | 0 | 1760921.6347 | 14265.5 | 0 | 15600 | 2199639.6902 | 160208.9303 | 0
22 | 2028-08-01 | 1 | 9.5618 | 143.4269 | 0.64542 | 47.809 | 9.5618 | 8.75 | 11 | 123240 | 0 | 0 | 1364.0732 | 454.23 | 0 | 18540 | 0 | 0 | 618 | 103 | 738.6485 | 309 | 0 | 0 | 22126.9517 | 21805.0428 | 258.1684 | 167430.1628 | 8605.6132 | 103267.359 | 158824.5496 | 0 | 1800360.3098 | 1641535.7602 | 2406508.5281 | 0 | 1593491.4719 | 20445.5 | 0 | 15600 | 2358464.2398 | 167430.1628 | 0
23 | 2028-09-01 | 1 | 10.4662 | 156.9926 | 0.70647 | 52.3309 | 10.4662 | 8.75 | 11 | 123240 | 0 | 0 | 1371.3157 | 454.23 | 0 | 0 | 15450 | 0 | 618 | 103 | 808.512 | 309 | 0 | 0 | 19114.0577 | 21353.1087 | 282.5867 | 163989.7531 | 9419.5571 | 113034.6854 | 154570.196 | 0 | 1641535.7602 | 1486965.5642 | 2570498.2812 | 0 | 1429501.7188 | 17355.5 | 0 | 15600 | 2513034.4358 | 163989.7531 | 0
24 | 2028-10-01 | 1 | 11.3615 | 170.4227 | 0.7669 | 56.8076 | 11.3615 | 8.75 | 11 | 123240 | 0 | 0 | 1378.4858 | 454.23 | 0 | 0 | 0 | 0 | 618 | 103 | 877.6769 | 309 | 0 | 0 | 3740.3927 | 19047.0589 | 306.7608 | 146334.2125 | 10225.3615 | 122704.3385 | 136108.8509 | 0 | 1486965.5642 | 1350856.7133 | 2716832.4937 | 0 | 1283167.5063 | 1905.5 | 0 | 15600 | 2649143.2867 | 146334.2125 | 0
25 | 2028-11-01 | 1.5 | 12.7479 | 191.2185 | 0.86048 | 63.7395 | 12.7479 | 8.75 | 11 | 128169.6 | 0 | 0 | 1431.276 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1014.3184 | 477.405 | 0 | 0 | 4133.4863 | 19845.4629 | 344.1932 | 152492.7424 | 11473.1079 | 137677.2952 | 141019.6345 | 0 | 1350856.7133 | 1209837.0788 | 2869325.2361 | 0 | 1130674.7639 | 1962.665 | 0 | 16224 | 2790162.9212 | 152492.7424 | 0
26 | 2028-12-01 | 1.5 | 14.1204 | 211.8063 | 0.95313 | 70.6021 | 14.1204 | 8.75 | 11 | 128169.6 | 0 | 0 | 1442.5972 | 467.8569 | 12730.8 | 0 | 0 | 0 | 636.54 | 106.09 | 1123.5264 | 477.405 | 0 | 0 | 16984.8156 | 21773.1623 | 381.2513 | 167308.8292 | 12708.3769 | 152500.5222 | 154600.4523 | 0 | 1209837.0788 | 1055236.6265 | 3036634.0653 | 0 | 963365.9347 | 14693.465 | 0 | 16224 | 2944763.3735 | 167308.8292 | 0
27 | 2029-01-01 | 1.5 | 15.4792 | 232.1882 | 1.0448 | 77.3961 | 15.4792 | 8.75 | 11 | 128169.6 | 0 | 0 | 1453.8053 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1231.6424 | 477.405 | 0 | 0 | 4373.3396 | 19881.4409 | 417.9388 | 152842.3193 | 13931.2931 | 167175.517 | 138911.0262 | 0 | 1055236.6265 | 916325.6002 | 3189476.3846 | 0 | 810523.6154 | 1962.665 | 0 | 16224 | 3083674.3998 | 152842.3193 | 0
28 | 2029-02-01 | 1.5 | 16.8244 | 252.3663 | 1.1356 | 84.1221 | 16.8244 | 8.75 | 11 | 128169.6 | 0 | 0 | 1464.9012 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1338.6772 | 477.405 | 0 | 0 | 4491.4703 | 19899.1606 | 454.2594 | 153014.4903 | 15141.9802 | 181703.7618 | 137872.5101 | 0 | 916325.6002 | 778453.0901 | 3342490.8749 | 0 | 657509.1251 | 1962.665 | 0 | 16224 | 3221546.9099 | 153014.4903 | 0
29 | 2029-03-01 | 1.5 | 18.1562 | 272.3427 | 1.2255 | 90.7809 | 18.1562 | 8.75 | 11 | 128169.6 | 0 | 0 | 1475.8862 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1444.6417 | 477.405 | 0 | 0 | 4608.4198 | 19916.703 | 490.2168 | 153184.9396 | 16340.5603 | 196086.7242 | 136844.3792 | 0 | 778453.0901 | 641608.7109 | 3495675.8145 | 0 | 504324.1855 | 1962.665 | 0 | 16224 | 3358391.2891 | 153184.9396 | 0
30 | 2029-04-01 | 1.5 | 19.4746 | 292.1192 | 1.3145 | 97.3731 | 19.4746 | 8.75 | 11 | 128169.6 | 0 | 0 | 1486.7613 | 467.8569 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1549.5465 | 477.405 | 0 | 0 | 4724.1998 | 19934.07 | 525.8146 | 153353.6844 | 17527.1547 | 210325.857 | 135826.5296 | 0 | 641608.7109 | 505782.1813 | 3649029.4988 | 0 | 350970.5012 | 1962.665 | 0 | 16224 | 3494217.8187 | 153353.6844 | 0
31 | 2029-05-01 | 1.5 | 20.7799 | 311.6981 | 1.4026 | 103.8994 | 20.7799 | 12.75 | 14 | 187432.2667 | 28000 | 12000 | 1497.5277 | 675.7933 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1653.4023 | 477.405 | 0 | 0 | 5046.7583 | 34871.8537 | 561.0565 | 267911.9352 | 18701.8832 | 224422.5984 | 249210.052 | 0 | 505782.1813 | 256572.1292 | 3916941.4341 | 0 | 83058.5659 | 1962.665 | 0 | 16224 | 3743427.8708 | 267911.9352 | 0
32 | 2029-06-01 | 1.5 | 22.0721 | 331.0811 | 1.4899 | 110.3604 | 22.0721 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1508.1864 | 675.7933 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 1756.2196 | 477.405 | 0 | 0 | 5160.2343 | 28888.8751 | 595.9459 | 222077.322 | 19864.8644 | 238378.3724 | 202212.4576 | 0 | 256572.1292 | 54359.6716 | 4139018.7561 | 0 | -139018.7561 | 1962.665 | 0 | 16224 | 3945640.3284 | 222077.322 | 0
33 | 2029-07-01 | 1.5 | 23.3514 | 350.2703 | 1.5762 | 116.7568 | 23.3514 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1518.7386 | 675.7933 | 0 | 0 | 0 | 12730.8 | 636.54 | 106.09 | 1858.0086 | 477.405 | 0 | 0 | 18003.3755 | 30815.3463 | 630.4865 | 236881.4749 | 21016.2157 | 252194.5887 | 215865.2592 | 0 | 54359.6716 | -161505.5876 | 4375900.231 | 161505.5876 | -375900.231 | 14693.465 | 0 | 16224 | 4161505.5876 | 236881.4749 | 1
34 | 2029-08-01 | 1.5 | 24.6178 | 369.2676 | 1.6617 | 123.0892 | 24.6178 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1529.1852 | 675.7933 | 0 | 19096.2 | 0 | 0 | 636.54 | 106.09 | 1958.7798 | 477.405 | 0 | 0 | 24479.9932 | 31786.839 | 664.6816 | 244363.7805 | 22156.0536 | 265872.6428 | 222207.7269 | 0 | -161505.5876 | -383713.3146 | 4620264.0115 | 383713.3146 | -620264.0115 | 21058.865 | 0 | 16224 | 4383713.3146 | 244363.7805 | 1
35 | 2029-09-01 | 1.5 | 25.8717 | 388.0749 | 1.7463 | 129.3583 | 25.8717 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1539.5273 | 675.7933 | 0 | 0 | 15913.5 | 0 | 636.54 | 106.09 | 2058.5432 | 477.405 | 0 | 0 | 21407.3988 | 31325.9498 | 698.5348 | 240864.1501 | 23284.493 | 279413.9164 | 217579.6571 | 0 | -383713.3146 | -601292.9717 | 4861128.1616 | 601292.9717 | -861128.1616 | 17876.165 | 0 | 16224 | 4601292.9717 | 240864.1501 | 1
36 | 2029-10-01 | 1.5 | 27.1129 | 406.6941 | 1.8301 | 135.5647 | 27.1129 | 12.75 | 14 | 187432.2667 | 0 | 0 | 1549.766 | 675.7933 | 0 | 0 | 0 | 0 | 636.54 | 106.09 | 2157.309 | 477.405 | 0 | 0 | 5602.9034 | 28955.2755 | 732.0494 | 222722.495 | 24401.6481 | 292819.7772 | 198320.8469 | 0 | -601292.9717 | -799613.8185 | 5083850.6566 | 799613.8185 | -1083850.6566 | 1962.665 | 0 | 16224 | 4799613.8185 | 222722.495 | 1
37 | 2029-11-01 | 2.25 | 29.0918 | 436.3772 | 1.9637 | 145.4591 | 29.0918 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1613.0714 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 2384.2057 | 737.5907 | 0 | 0 | 6195.8438 | 29711.8342 | 785.4789 | 228576.2076 | 26182.6316 | 314191.5794 | 202393.576 | 0 | -799613.8185 | -1002007.3946 | 5312426.8643 | 1002007.3946 | -1312426.8643 | 2021.5449 | 0 | 16872.96 | 5002007.3946 | 228576.2076 | 1
38 | 2029-12-01 | 2.25 | 31.0509 | 465.7634 | 2.0959 | 155.2545 | 31.0509 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1629.7157 | 696.0671 | 13112.724 | 0 | 0 | 0 | 655.6362 | 109.2727 | 2544.7613 | 737.5907 | 0 | 0 | 19485.7677 | 31705.3228 | 838.3742 | 243912.5153 | 27945.8053 | 335349.6636 | 215966.71 | 0 | -1002007.3946 | -1217974.1046 | 5556339.3796 | 1217974.1046 | -1556339.3796 | 15134.2689 | 0 | 16872.96 | 5217974.1046 | 243912.5153 | 1
39 | 2030-01-01 | 2.25 | 32.9904 | 494.8558 | 2.2269 | 164.9519 | 32.9904 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1646.1935 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 2703.7114 | 737.5907 | 0 | 0 | 6548.4716 | 29764.7283 | 890.7404 | 229086.9911 | 29691.3472 | 356296.167 | 199395.6438 | 0 | -1217974.1046 | -1417369.7484 | 5785426.3706 | 1417369.7484 | -1785426.3706 | 2021.5449 | 0 | 16872.96 | 5417369.7484 | 229086.9911 | 1
40 | 2030-02-01 | 2.25 | 34.9105 | 523.6572 | 2.3565 | 174.5524 | 34.9105 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1662.5065 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 2861.072 | 737.5907 | 0 | 0 | 6722.1452 | 29790.7794 | 942.583 | 229338.5583 | 31419.4338 | 377033.2053 | 197919.1245 | 0 | -1417369.7484 | -1615288.8729 | 6014764.9289 | 1615288.8729 | -2014764.9289 | 2021.5449 | 0 | 16872.96 | 5615288.8729 | 229338.5583 | 1
41 | 2030-03-01 | 2.25 | 36.8114 | 552.1707 | 2.4848 | 184.0569 | 36.8114 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1678.6565 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 3016.8589 | 737.5907 | 0 | 0 | 6894.0821 | 29816.5699 | 993.9072 | 229587.6099 | 33130.2394 | 397562.8733 | 196457.3704 | 0 | -1615288.8729 | -1811746.2433 | 6244352.5388 | 1811746.2433 | -2244352.5388 | 2021.5449 | 0 | 16872.96 | 5811746.2433 | 229587.6099 | 1
42 | 2030-04-01 | 2.25 | 38.6933 | 580.399 | 2.6118 | 193.4663 | 38.6933 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1694.6449 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 3171.088 | 737.5907 | 0 | 0 | 7064.2996 | 29842.1025 | 1044.7181 | 229834.1709 | 34823.937 | 417887.2445 | 195010.2339 | 0 | -1811746.2433 | -2006756.4772 | 6474186.7098 | 2006756.4772 | -2474186.7098 | 2021.5449 | 0 | 16872.96 | 6006756.4772 | 229834.1709 | 1
43 | 2030-05-01 | 2.25 | 40.5563 | 608.345 | 2.7376 | 202.7817 | 40.5563 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1710.4734 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 3323.7748 | 737.5907 | 0 | 0 | 7232.815 | 29867.3798 | 1095.0209 | 230078.2664 | 36500.6977 | 438008.3721 | 193577.5687 | 0 | -2006756.4772 | -2200334.0459 | 6704264.9761 | 2200334.0459 | -2704264.9761 | 2021.5449 | 0 | 16872.96 | 6200334.0459 | 230078.2664 | 1
44 | 2030-06-01 | 2.25 | 42.4008 | 636.0115 | 2.8621 | 212.0038 | 42.4008 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1726.1437 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 3474.9348 | 737.5907 | 0 | 0 | 7399.6451 | 29892.4044 | 1144.8207 | 230319.9209 | 38160.6907 | 457928.2884 | 192159.2302 | 0 | -2200334.0459 | -2392493.2761 | 6934584.897 | 2392493.2761 | -2934584.897 | 2021.5449 | 0 | 16872.96 | 6392493.2761 | 230319.9209 | 1
45 | 2030-07-01 | 2.25 | 44.2268 | 663.4014 | 2.9853 | 221.1338 | 44.2268 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1741.6572 | 696.0671 | 0 | 0 | 0 | 13112.724 | 655.6362 | 109.2727 | 3624.5831 | 737.5907 | 0 | 0 | 20677.531 | 31884.0873 | 1194.1225 | 245638.7914 | 39804.0838 | 477649.0055 | 205834.7077 | 0 | -2392493.2761 | -2598327.9838 | 7180223.6885 | 2598327.9838 | -3180223.6885 | 15134.2689 | 0 | 16872.96 | 6598327.9838 | 245638.7914 | 1
46 | 2030-08-01 | 2.25 | 46.0345 | 690.5174 | 3.1073 | 230.1725 | 46.0345 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1757.0156 | 696.0671 | 0 | 19669.086 | 0 | 0 | 655.6362 | 109.2727 | 3772.7349 | 737.5907 | 0 | 0 | 27397.4033 | 32892.0681 | 1242.9313 | 253415.4533 | 41431.043 | 497172.5154 | 211984.4104 | 0 | -2598327.9838 | -2810312.3942 | 7433639.1418 | 2810312.3942 | -3433639.1418 | 21690.6309 | 0 | 16872.96 | 6810312.3942 | 253415.4533 | 1
47 | 2030-09-01 | 2.25 | 47.8241 | 717.3622 | 3.2281 | 239.1207 | 47.8241 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1772.2204 | 696.0671 | 0 | 0 | 16390.905 | 0 | 655.6362 | 109.2727 | 3919.4053 | 737.5907 | 0 | 0 | 24281.0974 | 32424.6222 | 1291.252 | 249880.0223 | 43041.7325 | 516500.7903 | 206838.2898 | 0 | -2810312.3942 | -3017150.6839 | 7683519.1641 | 3017150.6839 | -3683519.1641 | 18412.4499 | 0 | 16872.96 | 7017150.6839 | 249880.0223 | 1
48 | 2030-10-01 | 2.25 | 49.5959 | 743.9386 | 3.3477 | 247.9795 | 49.5959 | 12.5 | 13 | 191883.0507 | 0 | 0 | 1787.2732 | 696.0671 | 0 | 0 | 0 | 0 | 655.6362 | 109.2727 | 4064.6089 | 737.5907 | 0 | 0 | 8050.4488 | 29990.0249 | 1339.0895 | 231262.6139 | 44636.3152 | 535635.7824 | 186626.2987 | 0 | -3017150.6839 | -3203776.9826 | 7914781.7779 | 3203776.9826 | -3914781.7779 | 2021.5449 | 0 | 16872.96 | 7203776.9826 | 231262.6139 | 1
49 | 2030-11-01 | 3.375 | 52.4749 | 787.1242 | 3.5421 | 262.3747 | 52.4749 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1866.0854 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 4429.5761 | 1139.5777 | 0 | 0 | 8940.0445 | 31274.7626 | 1416.8236 | 241190.0033 | 47227.452 | 566729.4246 | 193962.5512 | 0 | -3203776.9826 | -3397739.5338 | 8155971.7812 | 3397739.5338 | -4155971.7812 | 2082.1913 | 0 | 17547.8784 | 7397739.5338 | 241190.0033 | 1
50 | 2030-12-01 | 3.375 | 55.3252 | 829.878 | 3.7345 | 276.626 | 55.3252 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1891.0275 | 716.9491 | 13506.1057 | 0 | 0 | 0 | 675.3053 | 112.5509 | 4670.1748 | 1139.5777 | 0 | 0 | 22711.6909 | 33340.5095 | 1493.7803 | 257104.3535 | 49792.6775 | 597512.1303 | 207311.6759 | 0 | -3397739.5338 | -3605051.2098 | 8413076.1347 | 3605051.2098 | -4413076.1347 | 15588.297 | 0 | 17547.8784 | 7605051.2098 | 257104.3535 | 1
51 | 2031-01-01 | 3.375 | 58.1469 | 872.2042 | 3.9249 | 290.7347 | 58.1469 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1915.7201 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 4908.3674 | 1139.5777 | 0 | 0 | 9468.4705 | 31354.0265 | 1569.9675 | 241950.8372 | 52332.2508 | 627987.009 | 189618.5864 | 0 | -3605051.2098 | -3794669.7962 | 8655026.9719 | 3794669.7962 | -4655026.9719 | 2082.1913 | 0 | 17547.8784 | 7794669.7962 | 241950.8372 | 1
52 | 2031-02-01 | 3.375 | 60.9405 | 914.1071 | 4.1135 | 304.7024 | 60.9405 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1940.1658 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 5144.1782 | 1139.5777 | 0 | 0 | 9728.7269 | 31393.0649 | 1645.3928 | 242325.5574 | 54846.4282 | 658157.1389 | 187479.1292 | 0 | -3794669.7962 | -3982148.9254 | 8897352.5293 | 3982148.9254 | -4897352.5293 | 2082.1913 | 0 | 17547.8784 | 7982148.9254 | 242325.5574 | 1
53 | 2031-03-01 | 3.375 | 63.7061 | 955.5911 | 4.3002 | 318.5304 | 63.7061 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1964.3671 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 5377.6308 | 1139.5777 | 0 | 0 | 9986.3808 | 31431.713 | 1720.0639 | 242696.5305 | 57335.464 | 688025.5675 | 185361.0665 | 0 | -3982148.9254 | -4167509.9919 | 9140049.0598 | 4167509.9919 | -5140049.0598 | 2082.1913 | 0 | 17547.8784 | 8167509.9919 | 242696.5305 | 1
54 | 2031-04-01 | 3.375 | 66.444 | 996.6602 | 4.485 | 332.2201 | 66.444 | 12.5 | 13 | 199558.3727 | 0 | 0 | 1988.3263 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 5608.7489 | 1139.5777 | 0 | 0 | 10241.4582 | 31469.9746 | 1793.9883 | 243063.7938 | 59799.6093 | 717595.3119 | 183264.1845 | 0 | -4167509.9919 | -4350774.1764 | 9383112.8536 | 4350774.1764 | -5383112.8536 | 2082.1913 | 0 | 17547.8784 | 8350774.1764 | 243063.7938 | 1
55 | 2031-05-01 | 3.375 | 69.1546 | 1037.3186 | 4.6679 | 345.7729 | 69.1546 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2012.046 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 5837.5559 | 1139.5777 | 0 | 0 | 10493.9848 | 31507.8536 | 1867.1734 | 243427.3845 | 62239.1132 | 746869.3587 | 181188.2713 | 0 | -4350774.1764 | -4531962.4477 | 9626540.2381 | 4531962.4477 | -5626540.2381 | 2082.1913 | 0 | 17547.8784 | 8531962.4477 | 243427.3845 | 1
56 | 2031-06-01 | 3.375 | 71.838 | 1077.5704 | 4.8491 | 359.1901 | 71.838 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2035.5284 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 6064.0747 | 1139.5777 | 0 | 0 | 10743.9861 | 31545.3538 | 1939.6267 | 243787.3393 | 64654.2221 | 775850.6651 | 179133.1172 | 0 | -4531962.4477 | -4711095.5648 | 9870327.5774 | 4711095.5648 | -5870327.5774 | 2082.1913 | 0 | 17547.8784 | 8711095.5648 | 243787.3393 | 1
57 | 2031-07-01 | 3.375 | 74.4946 | 1117.4197 | 5.0284 | 372.4732 | 74.4946 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2058.7761 | 716.9491 | 0 | 0 | 0 | 13506.1057 | 675.3053 | 112.5509 | 6288.3284 | 1139.5777 | 0 | 0 | 24497.5931 | 33608.3949 | 2011.3554 | 259675.7161 | 67045.1799 | 804542.1585 | 192630.5362 | 0 | -4711095.5648 | -4903726.101 | 10130003.2934 | 4903726.101 | -6130003.2934 | 15588.297 | 0 | 17547.8784 | 8903726.101 | 259675.7161 | 1
58 | 2031-08-01 | 3.375 | 77.1247 | 1156.8705 | 5.2059 | 385.6235 | 77.1247 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2081.7912 | 716.9491 | 0 | 20259.1586 | 0 | 0 | 675.3053 | 112.5509 | 6510.3395 | 1139.5777 | 0 | 0 | 31495.6723 | 34658.1067 | 2082.3668 | 267794.5185 | 69412.2281 | 832946.7369 | 198382.2905 | 0 | -4903726.101 | -5102108.3915 | 10397797.812 | 5102108.3915 | -6397797.812 | 22341.3499 | 0 | 17547.8784 | 9102108.3915 | 267794.5185 | 1
59 | 2031-09-01 | 3.375 | 79.7285 | 1195.9268 | 5.3817 | 398.6423 | 79.7285 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2104.5762 | 716.9491 | 0 | 0 | 16882.6322 | 0 | 675.3053 | 112.5509 | 6730.1305 | 1139.5777 | 0 | 0 | 28361.7219 | 34188.0142 | 2152.6682 | 264260.7769 | 71755.6058 | 861067.2695 | 192505.1711 | 0 | -5102108.3915 | -5294613.5626 | 10662058.5889 | 5294613.5626 | -6662058.5889 | 18964.8234 | 0 | 17547.8784 | 9294613.5626 | 264260.7769 | 1
60 | 2031-10-01 | 3.375 | 82.3062 | 1234.5925 | 5.5557 | 411.5308 | 82.3062 | 12.5 | 13 | 199558.3727 | 0 | 0 | 2127.1334 | 716.9491 | 0 | 0 | 0 | 0 | 675.3053 | 112.5509 | 6947.7237 | 1139.5777 | 0 | 0 | 11719.24 | 31691.6419 | 2222.2665 | 245191.5211 | 74075.5497 | 888906.5968 | 171115.9713 | 0 | -5294613.5626 | -5465729.5339 | 10907250.1099 | 5465729.5339 | -6907250.1099 | 2082.1913 | 0 | 17547.8784 | 9465729.5339 | 245191.5211 | 1

## Vendor Months
Vendor monthly quantity × rate audit trail
Unknown prices are explicit allowances, never missing-as-free. Stack and scope gates applied before quantity. Inflation steps on project anniversaries. Infrastructure allowances include dev/stage/prod; not audited COGS.
← Start Here
Scenario | Cost ID | Month | Date | Enabled quantity | Escalated unit rate | Cash | Unresolved cash | Optional cash | Category
Lean | INFRA-APP | 1 | 2026-11-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 2 | 2026-12-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 3 | 2027-01-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 4 | 2027-02-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 5 | 2027-03-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 6 | 2027-04-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 7 | 2027-05-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 8 | 2027-06-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 9 | 2027-07-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 10 | 2027-08-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 11 | 2027-09-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 12 | 2027-10-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Lean | INFRA-APP | 13 | 2027-11-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 14 | 2027-12-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 15 | 2028-01-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 16 | 2028-02-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 17 | 2028-03-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 18 | 2028-04-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 19 | 2028-05-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 20 | 2028-06-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 21 | 2028-07-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 22 | 2028-08-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 23 | 2028-09-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 24 | 2028-10-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Lean | INFRA-APP | 25 | 2028-11-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 26 | 2028-12-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 27 | 2029-01-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 28 | 2029-02-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 29 | 2029-03-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 30 | 2029-04-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 31 | 2029-05-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 32 | 2029-06-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 33 | 2029-07-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 34 | 2029-08-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 35 | 2029-09-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 36 | 2029-10-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Lean | INFRA-APP | 37 | 2029-11-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 38 | 2029-12-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 39 | 2030-01-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 40 | 2030-02-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 41 | 2030-03-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 42 | 2030-04-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 43 | 2030-05-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 44 | 2030-06-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 45 | 2030-07-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 46 | 2030-08-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 47 | 2030-09-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 48 | 2030-10-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Lean | INFRA-APP | 49 | 2030-11-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 50 | 2030-12-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 51 | 2031-01-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 52 | 2031-02-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 53 | 2031-03-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 54 | 2031-04-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 55 | 2031-05-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 56 | 2031-06-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 57 | 2031-07-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 58 | 2031-08-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 59 | 2031-09-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-APP | 60 | 2031-10-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Lean | INFRA-DB | 1 | 2026-11-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 2 | 2026-12-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 3 | 2027-01-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 4 | 2027-02-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 5 | 2027-03-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 6 | 2027-04-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 7 | 2027-05-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 8 | 2027-06-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 9 | 2027-07-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 10 | 2027-08-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 11 | 2027-09-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 12 | 2027-10-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Lean | INFRA-DB | 13 | 2027-11-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 14 | 2027-12-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 15 | 2028-01-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 16 | 2028-02-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 17 | 2028-03-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 18 | 2028-04-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 19 | 2028-05-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 20 | 2028-06-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 21 | 2028-07-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 22 | 2028-08-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 23 | 2028-09-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 24 | 2028-10-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Lean | INFRA-DB | 25 | 2028-11-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 26 | 2028-12-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 27 | 2029-01-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 28 | 2029-02-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 29 | 2029-03-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 30 | 2029-04-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 31 | 2029-05-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 32 | 2029-06-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 33 | 2029-07-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 34 | 2029-08-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 35 | 2029-09-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 36 | 2029-10-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Lean | INFRA-DB | 37 | 2029-11-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 38 | 2029-12-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 39 | 2030-01-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 40 | 2030-02-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 41 | 2030-03-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 42 | 2030-04-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 43 | 2030-05-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 44 | 2030-06-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 45 | 2030-07-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 46 | 2030-08-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 47 | 2030-09-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 48 | 2030-10-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Lean | INFRA-DB | 49 | 2030-11-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 50 | 2030-12-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 51 | 2031-01-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 52 | 2031-02-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 53 | 2031-03-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 54 | 2031-04-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 55 | 2031-05-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 56 | 2031-06-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 57 | 2031-07-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 58 | 2031-08-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 59 | 2031-09-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-DB | 60 | 2031-10-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Lean | INFRA-AWS | 1 | 2026-11-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 2 | 2026-12-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 3 | 2027-01-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 4 | 2027-02-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 5 | 2027-03-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 6 | 2027-04-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 7 | 2027-05-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 8 | 2027-06-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 9 | 2027-07-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 10 | 2027-08-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 11 | 2027-09-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 12 | 2027-10-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 13 | 2027-11-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 14 | 2027-12-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 15 | 2028-01-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 16 | 2028-02-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 17 | 2028-03-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 18 | 2028-04-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 19 | 2028-05-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 20 | 2028-06-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 21 | 2028-07-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 22 | 2028-08-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 23 | 2028-09-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 24 | 2028-10-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 25 | 2028-11-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 26 | 2028-12-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 27 | 2029-01-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 28 | 2029-02-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 29 | 2029-03-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 30 | 2029-04-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 31 | 2029-05-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 32 | 2029-06-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 33 | 2029-07-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 34 | 2029-08-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 35 | 2029-09-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 36 | 2029-10-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 37 | 2029-11-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 38 | 2029-12-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 39 | 2030-01-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 40 | 2030-02-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 41 | 2030-03-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 42 | 2030-04-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 43 | 2030-05-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 44 | 2030-06-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 45 | 2030-07-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 46 | 2030-08-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 47 | 2030-09-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 48 | 2030-10-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 49 | 2030-11-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 50 | 2030-12-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 51 | 2031-01-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 52 | 2031-02-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 53 | 2031-03-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 54 | 2031-04-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 55 | 2031-05-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 56 | 2031-06-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 57 | 2031-07-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 58 | 2031-08-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 59 | 2031-09-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-AWS | 60 | 2031-10-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Lean | INFRA-EDGE | 1 | 2026-11-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 2 | 2026-12-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 3 | 2027-01-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 4 | 2027-02-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 5 | 2027-03-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 6 | 2027-04-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 7 | 2027-05-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 8 | 2027-06-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 9 | 2027-07-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 10 | 2027-08-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 11 | 2027-09-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 12 | 2027-10-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Lean | INFRA-EDGE | 13 | 2027-11-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 14 | 2027-12-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 15 | 2028-01-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 16 | 2028-02-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 17 | 2028-03-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 18 | 2028-04-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 19 | 2028-05-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 20 | 2028-06-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 21 | 2028-07-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 22 | 2028-08-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 23 | 2028-09-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 24 | 2028-10-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Lean | INFRA-EDGE | 25 | 2028-11-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 26 | 2028-12-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 27 | 2029-01-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 28 | 2029-02-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 29 | 2029-03-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 30 | 2029-04-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 31 | 2029-05-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 32 | 2029-06-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 33 | 2029-07-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 34 | 2029-08-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 35 | 2029-09-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 36 | 2029-10-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Lean | INFRA-EDGE | 37 | 2029-11-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 38 | 2029-12-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 39 | 2030-01-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 40 | 2030-02-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 41 | 2030-03-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 42 | 2030-04-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 43 | 2030-05-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 44 | 2030-06-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 45 | 2030-07-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 46 | 2030-08-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 47 | 2030-09-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 48 | 2030-10-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Lean | INFRA-EDGE | 49 | 2030-11-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 50 | 2030-12-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 51 | 2031-01-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 52 | 2031-02-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 53 | 2031-03-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 54 | 2031-04-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 55 | 2031-05-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 56 | 2031-06-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 57 | 2031-07-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 58 | 2031-08-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 59 | 2031-09-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-EDGE | 60 | 2031-10-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Lean | INFRA-STORE | 1 | 2026-11-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 2 | 2026-12-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 3 | 2027-01-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 4 | 2027-02-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 5 | 2027-03-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 6 | 2027-04-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 7 | 2027-05-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 8 | 2027-06-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 9 | 2027-07-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 10 | 2027-08-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 11 | 2027-09-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 12 | 2027-10-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 13 | 2027-11-01 | 0 | 0.1545 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 14 | 2027-12-01 | 0 | 0.1545 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 15 | 2028-01-01 | 0 | 0.1545 | 0 | 0 | 0 | INFRA
Lean | INFRA-STORE | 16 | 2028-02-01 | 1 | 0.1545 | 0.1545 | 0 | 0 | INFRA
Lean | INFRA-STORE | 17 | 2028-03-01 | 1.985 | 0.1545 | 0.30668 | 0 | 0 | INFRA
Lean | INFRA-STORE | 18 | 2028-04-01 | 2.9552 | 0.1545 | 0.45658 | 0 | 0 | INFRA
Lean | INFRA-STORE | 19 | 2028-05-01 | 3.9109 | 0.1545 | 0.60423 | 0 | 0 | INFRA
Lean | INFRA-STORE | 20 | 2028-06-01 | 4.8522 | 0.1545 | 0.74967 | 0 | 0 | INFRA
Lean | INFRA-STORE | 21 | 2028-07-01 | 5.7794 | 0.1545 | 0.89292 | 0 | 0 | INFRA
Lean | INFRA-STORE | 22 | 2028-08-01 | 6.6928 | 0.1545 | 1.034 | 0 | 0 | INFRA
Lean | INFRA-STORE | 23 | 2028-09-01 | 7.5924 | 0.1545 | 1.173 | 0 | 0 | INFRA
Lean | INFRA-STORE | 24 | 2028-10-01 | 8.4785 | 0.1545 | 1.3099 | 0 | 0 | INFRA
Lean | INFRA-STORE | 25 | 2028-11-01 | 9.3513 | 0.15913 | 1.4881 | 0 | 0 | INFRA
Lean | INFRA-STORE | 26 | 2028-12-01 | 10.211 | 0.15913 | 1.6249 | 0 | 0 | INFRA
Lean | INFRA-STORE | 27 | 2029-01-01 | 11.0579 | 0.15913 | 1.7597 | 0 | 0 | INFRA
Lean | INFRA-STORE | 28 | 2029-02-01 | 12.142 | 0.15913 | 1.9322 | 0 | 0 | INFRA
Lean | INFRA-STORE | 29 | 2029-03-01 | 13.2099 | 0.15913 | 2.1022 | 0 | 0 | INFRA
Lean | INFRA-STORE | 30 | 2029-04-01 | 14.2617 | 0.15913 | 2.2695 | 0 | 0 | INFRA
Lean | INFRA-STORE | 31 | 2029-05-01 | 15.2978 | 0.15913 | 2.4344 | 0 | 0 | INFRA
Lean | INFRA-STORE | 32 | 2029-06-01 | 16.3183 | 0.15913 | 2.5968 | 0 | 0 | INFRA
Lean | INFRA-STORE | 33 | 2029-07-01 | 17.3236 | 0.15913 | 2.7568 | 0 | 0 | INFRA
Lean | INFRA-STORE | 34 | 2029-08-01 | 18.3137 | 0.15913 | 2.9144 | 0 | 0 | INFRA
Lean | INFRA-STORE | 35 | 2029-09-01 | 19.289 | 0.15913 | 3.0696 | 0 | 0 | INFRA
Lean | INFRA-STORE | 36 | 2029-10-01 | 20.2497 | 0.15913 | 3.2224 | 0 | 0 | INFRA
Lean | INFRA-STORE | 37 | 2029-11-01 | 21.1959 | 0.16391 | 3.4742 | 0 | 0 | INFRA
Lean | INFRA-STORE | 38 | 2029-12-01 | 22.128 | 0.16391 | 3.627 | 0 | 0 | INFRA
Lean | INFRA-STORE | 39 | 2030-01-01 | 23.0461 | 0.16391 | 3.7775 | 0 | 0 | INFRA
Lean | INFRA-STORE | 40 | 2030-02-01 | 24.2629 | 0.16391 | 3.9769 | 0 | 0 | INFRA
Lean | INFRA-STORE | 41 | 2030-03-01 | 25.4614 | 0.16391 | 4.1734 | 0 | 0 | INFRA
Lean | INFRA-STORE | 42 | 2030-04-01 | 26.642 | 0.16391 | 4.3669 | 0 | 0 | INFRA
Lean | INFRA-STORE | 43 | 2030-05-01 | 27.8049 | 0.16391 | 4.5575 | 0 | 0 | INFRA
Lean | INFRA-STORE | 44 | 2030-06-01 | 28.9503 | 0.16391 | 4.7452 | 0 | 0 | INFRA
Lean | INFRA-STORE | 45 | 2030-07-01 | 30.0785 | 0.16391 | 4.9301 | 0 | 0 | INFRA
Lean | INFRA-STORE | 46 | 2030-08-01 | 31.1899 | 0.16391 | 5.1123 | 0 | 0 | INFRA
Lean | INFRA-STORE | 47 | 2030-09-01 | 32.2845 | 0.16391 | 5.2917 | 0 | 0 | INFRA
Lean | INFRA-STORE | 48 | 2030-10-01 | 33.3628 | 0.16391 | 5.4685 | 0 | 0 | INFRA
Lean | INFRA-STORE | 49 | 2030-11-01 | 34.4248 | 0.16883 | 5.8118 | 0 | 0 | INFRA
Lean | INFRA-STORE | 50 | 2030-12-01 | 35.4709 | 0.16883 | 5.9884 | 0 | 0 | INFRA
Lean | INFRA-STORE | 51 | 2031-01-01 | 36.5014 | 0.16883 | 6.1624 | 0 | 0 | INFRA
Lean | INFRA-STORE | 52 | 2031-02-01 | 37.907 | 0.16883 | 6.3997 | 0 | 0 | INFRA
Lean | INFRA-STORE | 53 | 2031-03-01 | 39.2915 | 0.16883 | 6.6334 | 0 | 0 | INFRA
Lean | INFRA-STORE | 54 | 2031-04-01 | 40.6553 | 0.16883 | 6.8637 | 0 | 0 | INFRA
Lean | INFRA-STORE | 55 | 2031-05-01 | 41.9985 | 0.16883 | 7.0905 | 0 | 0 | INFRA
Lean | INFRA-STORE | 56 | 2031-06-01 | 43.3217 | 0.16883 | 7.3138 | 0 | 0 | INFRA
Lean | INFRA-STORE | 57 | 2031-07-01 | 44.625 | 0.16883 | 7.5339 | 0 | 0 | INFRA
Lean | INFRA-STORE | 58 | 2031-08-01 | 45.9087 | 0.16883 | 7.7506 | 0 | 0 | INFRA
Lean | INFRA-STORE | 59 | 2031-09-01 | 47.1732 | 0.16883 | 7.9641 | 0 | 0 | INFRA
Lean | INFRA-STORE | 60 | 2031-10-01 | 48.4188 | 0.16883 | 8.1744 | 0 | 0 | INFRA
Lean | INFRA-LOG | 1 | 2026-11-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 2 | 2026-12-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 3 | 2027-01-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 4 | 2027-02-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 5 | 2027-03-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 6 | 2027-04-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 7 | 2027-05-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 8 | 2027-06-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 9 | 2027-07-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 10 | 2027-08-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 11 | 2027-09-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 12 | 2027-10-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 13 | 2027-11-01 | 0 | 5.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 14 | 2027-12-01 | 0 | 5.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 15 | 2028-01-01 | 0 | 5.15 | 0 | 0 | 0 | INFRA
Lean | INFRA-LOG | 16 | 2028-02-01 | 0.25 | 5.15 | 1.2875 | 0 | 0 | INFRA
Lean | INFRA-LOG | 17 | 2028-03-01 | 0.49625 | 5.15 | 2.5557 | 0 | 0 | INFRA
Lean | INFRA-LOG | 18 | 2028-04-01 | 0.73881 | 5.15 | 3.8049 | 0 | 0 | INFRA
Lean | INFRA-LOG | 19 | 2028-05-01 | 0.97772 | 5.15 | 5.0353 | 0 | 0 | INFRA
Lean | INFRA-LOG | 20 | 2028-06-01 | 1.2131 | 5.15 | 6.2473 | 0 | 0 | INFRA
Lean | INFRA-LOG | 21 | 2028-07-01 | 1.4449 | 5.15 | 7.441 | 0 | 0 | INFRA
Lean | INFRA-LOG | 22 | 2028-08-01 | 1.6732 | 5.15 | 8.6169 | 0 | 0 | INFRA
Lean | INFRA-LOG | 23 | 2028-09-01 | 1.8981 | 5.15 | 9.7752 | 0 | 0 | INFRA
Lean | INFRA-LOG | 24 | 2028-10-01 | 2.1196 | 5.15 | 10.916 | 0 | 0 | INFRA
Lean | INFRA-LOG | 25 | 2028-11-01 | 2.3378 | 5.3045 | 12.401 | 0 | 0 | INFRA
Lean | INFRA-LOG | 26 | 2028-12-01 | 2.5528 | 5.3045 | 13.5411 | 0 | 0 | INFRA
Lean | INFRA-LOG | 27 | 2029-01-01 | 2.7645 | 5.3045 | 14.6641 | 0 | 0 | INFRA
Lean | INFRA-LOG | 28 | 2029-02-01 | 3.0355 | 5.3045 | 16.1018 | 0 | 0 | INFRA
Lean | INFRA-LOG | 29 | 2029-03-01 | 3.3025 | 5.3045 | 17.5179 | 0 | 0 | INFRA
Lean | INFRA-LOG | 30 | 2029-04-01 | 3.5654 | 5.3045 | 18.9128 | 0 | 0 | INFRA
Lean | INFRA-LOG | 31 | 2029-05-01 | 3.8244 | 5.3045 | 20.2868 | 0 | 0 | INFRA
Lean | INFRA-LOG | 32 | 2029-06-01 | 4.0796 | 5.3045 | 21.6401 | 0 | 0 | INFRA
Lean | INFRA-LOG | 33 | 2029-07-01 | 4.3309 | 5.3045 | 22.9732 | 0 | 0 | INFRA
Lean | INFRA-LOG | 34 | 2029-08-01 | 4.5784 | 5.3045 | 24.2863 | 0 | 0 | INFRA
Lean | INFRA-LOG | 35 | 2029-09-01 | 4.8222 | 5.3045 | 25.5796 | 0 | 0 | INFRA
Lean | INFRA-LOG | 36 | 2029-10-01 | 5.0624 | 5.3045 | 26.8536 | 0 | 0 | INFRA
Lean | INFRA-LOG | 37 | 2029-11-01 | 5.299 | 5.4636 | 28.9517 | 0 | 0 | INFRA
Lean | INFRA-LOG | 38 | 2029-12-01 | 5.532 | 5.4636 | 30.2248 | 0 | 0 | INFRA
Lean | INFRA-LOG | 39 | 2030-01-01 | 5.7615 | 5.4636 | 31.4788 | 0 | 0 | INFRA
Lean | INFRA-LOG | 40 | 2030-02-01 | 6.0657 | 5.4636 | 33.1409 | 0 | 0 | INFRA
Lean | INFRA-LOG | 41 | 2030-03-01 | 6.3654 | 5.4636 | 34.778 | 0 | 0 | INFRA
Lean | INFRA-LOG | 42 | 2030-04-01 | 6.6605 | 5.4636 | 36.3905 | 0 | 0 | INFRA
Lean | INFRA-LOG | 43 | 2030-05-01 | 6.9512 | 5.4636 | 37.9789 | 0 | 0 | INFRA
Lean | INFRA-LOG | 44 | 2030-06-01 | 7.2376 | 5.4636 | 39.5435 | 0 | 0 | INFRA
Lean | INFRA-LOG | 45 | 2030-07-01 | 7.5196 | 5.4636 | 41.0845 | 0 | 0 | INFRA
Lean | INFRA-LOG | 46 | 2030-08-01 | 7.7975 | 5.4636 | 42.6025 | 0 | 0 | INFRA
Lean | INFRA-LOG | 47 | 2030-09-01 | 8.0711 | 5.4636 | 44.0977 | 0 | 0 | INFRA
Lean | INFRA-LOG | 48 | 2030-10-01 | 8.3407 | 5.4636 | 45.5705 | 0 | 0 | INFRA
Lean | INFRA-LOG | 49 | 2030-11-01 | 8.6062 | 5.6275 | 48.4318 | 0 | 0 | INFRA
Lean | INFRA-LOG | 50 | 2030-12-01 | 8.8677 | 5.6275 | 49.9036 | 0 | 0 | INFRA
Lean | INFRA-LOG | 51 | 2031-01-01 | 9.1253 | 5.6275 | 51.3533 | 0 | 0 | INFRA
Lean | INFRA-LOG | 52 | 2031-02-01 | 9.4767 | 5.6275 | 53.3308 | 0 | 0 | INFRA
Lean | INFRA-LOG | 53 | 2031-03-01 | 9.8229 | 5.6275 | 55.2787 | 0 | 0 | INFRA
Lean | INFRA-LOG | 54 | 2031-04-01 | 10.1638 | 5.6275 | 57.1973 | 0 | 0 | INFRA
Lean | INFRA-LOG | 55 | 2031-05-01 | 10.4996 | 5.6275 | 59.0872 | 0 | 0 | INFRA
Lean | INFRA-LOG | 56 | 2031-06-01 | 10.8304 | 5.6275 | 60.9487 | 0 | 0 | INFRA
Lean | INFRA-LOG | 57 | 2031-07-01 | 11.1562 | 5.6275 | 62.7823 | 0 | 0 | INFRA
Lean | INFRA-LOG | 58 | 2031-08-01 | 11.4772 | 5.6275 | 64.5884 | 0 | 0 | INFRA
Lean | INFRA-LOG | 59 | 2031-09-01 | 11.7933 | 5.6275 | 66.3674 | 0 | 0 | INFRA
Lean | INFRA-LOG | 60 | 2031-10-01 | 12.1047 | 5.6275 | 68.1197 | 0 | 0 | INFRA
Lean | INFRA-REQ | 1 | 2026-11-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 2 | 2026-12-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 3 | 2027-01-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 4 | 2027-02-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 5 | 2027-03-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 6 | 2027-04-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 7 | 2027-05-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 8 | 2027-06-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 9 | 2027-07-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 10 | 2027-08-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 11 | 2027-09-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 12 | 2027-10-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 13 | 2027-11-01 | 0 | 30.9 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 14 | 2027-12-01 | 0 | 30.9 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 15 | 2028-01-01 | 0 | 30.9 | 0 | 0 | 0 | INFRA
Lean | INFRA-REQ | 16 | 2028-02-01 | 0.012 | 30.9 | 0.3708 | 0 | 0 | INFRA
Lean | INFRA-REQ | 17 | 2028-03-01 | 0.02382 | 30.9 | 0.73604 | 0 | 0 | INFRA
Lean | INFRA-REQ | 18 | 2028-04-01 | 0.035463 | 30.9 | 1.0958 | 0 | 0 | INFRA
Lean | INFRA-REQ | 19 | 2028-05-01 | 0.046931 | 30.9 | 1.4502 | 0 | 0 | INFRA
Lean | INFRA-REQ | 20 | 2028-06-01 | 0.058227 | 30.9 | 1.7992 | 0 | 0 | INFRA
Lean | INFRA-REQ | 21 | 2028-07-01 | 0.069353 | 30.9 | 2.143 | 0 | 0 | INFRA
Lean | INFRA-REQ | 22 | 2028-08-01 | 0.080313 | 30.9 | 2.4817 | 0 | 0 | INFRA
Lean | INFRA-REQ | 23 | 2028-09-01 | 0.091108 | 30.9 | 2.8152 | 0 | 0 | INFRA
Lean | INFRA-REQ | 24 | 2028-10-01 | 0.10174 | 30.9 | 3.1438 | 0 | 0 | INFRA
Lean | INFRA-REQ | 25 | 2028-11-01 | 0.11222 | 31.827 | 3.5715 | 0 | 0 | INFRA
Lean | INFRA-REQ | 26 | 2028-12-01 | 0.12253 | 31.827 | 3.8998 | 0 | 0 | INFRA
Lean | INFRA-REQ | 27 | 2029-01-01 | 0.13269 | 31.827 | 4.2233 | 0 | 0 | INFRA
Lean | INFRA-REQ | 28 | 2029-02-01 | 0.1457 | 31.827 | 4.6373 | 0 | 0 | INFRA
Lean | INFRA-REQ | 29 | 2029-03-01 | 0.15852 | 31.827 | 5.0452 | 0 | 0 | INFRA
Lean | INFRA-REQ | 30 | 2029-04-01 | 0.17114 | 31.827 | 5.4469 | 0 | 0 | INFRA
Lean | INFRA-REQ | 31 | 2029-05-01 | 0.18357 | 31.827 | 5.8426 | 0 | 0 | INFRA
Lean | INFRA-REQ | 32 | 2029-06-01 | 0.19582 | 31.827 | 6.2324 | 0 | 0 | INFRA
Lean | INFRA-REQ | 33 | 2029-07-01 | 0.20788 | 31.827 | 6.6163 | 0 | 0 | INFRA
Lean | INFRA-REQ | 34 | 2029-08-01 | 0.21976 | 31.827 | 6.9944 | 0 | 0 | INFRA
Lean | INFRA-REQ | 35 | 2029-09-01 | 0.23147 | 31.827 | 7.3669 | 0 | 0 | INFRA
Lean | INFRA-REQ | 36 | 2029-10-01 | 0.243 | 31.827 | 7.7338 | 0 | 0 | INFRA
Lean | INFRA-REQ | 37 | 2029-11-01 | 0.25435 | 32.7818 | 8.3381 | 0 | 0 | INFRA
Lean | INFRA-REQ | 38 | 2029-12-01 | 0.26554 | 32.7818 | 8.7047 | 0 | 0 | INFRA
Lean | INFRA-REQ | 39 | 2030-01-01 | 0.27655 | 32.7818 | 9.0659 | 0 | 0 | INFRA
Lean | INFRA-REQ | 40 | 2030-02-01 | 0.29115 | 32.7818 | 9.5446 | 0 | 0 | INFRA
Lean | INFRA-REQ | 41 | 2030-03-01 | 0.30554 | 32.7818 | 10.0161 | 0 | 0 | INFRA
Lean | INFRA-REQ | 42 | 2030-04-01 | 0.3197 | 32.7818 | 10.4805 | 0 | 0 | INFRA
Lean | INFRA-REQ | 43 | 2030-05-01 | 0.33366 | 32.7818 | 10.9379 | 0 | 0 | INFRA
Lean | INFRA-REQ | 44 | 2030-06-01 | 0.3474 | 32.7818 | 11.3885 | 0 | 0 | INFRA
Lean | INFRA-REQ | 45 | 2030-07-01 | 0.36094 | 32.7818 | 11.8323 | 0 | 0 | INFRA
Lean | INFRA-REQ | 46 | 2030-08-01 | 0.37428 | 32.7818 | 12.2695 | 0 | 0 | INFRA
Lean | INFRA-REQ | 47 | 2030-09-01 | 0.38741 | 32.7818 | 12.7001 | 0 | 0 | INFRA
Lean | INFRA-REQ | 48 | 2030-10-01 | 0.40035 | 32.7818 | 13.1243 | 0 | 0 | INFRA
Lean | INFRA-REQ | 49 | 2030-11-01 | 0.4131 | 33.7653 | 13.9484 | 0 | 0 | INFRA
Lean | INFRA-REQ | 50 | 2030-12-01 | 0.42565 | 33.7653 | 14.3722 | 0 | 0 | INFRA
Lean | INFRA-REQ | 51 | 2031-01-01 | 0.43802 | 33.7653 | 14.7897 | 0 | 0 | INFRA
Lean | INFRA-REQ | 52 | 2031-02-01 | 0.45488 | 33.7653 | 15.3593 | 0 | 0 | INFRA
Lean | INFRA-REQ | 53 | 2031-03-01 | 0.4715 | 33.7653 | 15.9203 | 0 | 0 | INFRA
Lean | INFRA-REQ | 54 | 2031-04-01 | 0.48786 | 33.7653 | 16.4728 | 0 | 0 | INFRA
Lean | INFRA-REQ | 55 | 2031-05-01 | 0.50398 | 33.7653 | 17.0171 | 0 | 0 | INFRA
Lean | INFRA-REQ | 56 | 2031-06-01 | 0.51986 | 33.7653 | 17.5532 | 0 | 0 | INFRA
Lean | INFRA-REQ | 57 | 2031-07-01 | 0.5355 | 33.7653 | 18.0813 | 0 | 0 | INFRA
Lean | INFRA-REQ | 58 | 2031-08-01 | 0.5509 | 33.7653 | 18.6015 | 0 | 0 | INFRA
Lean | INFRA-REQ | 59 | 2031-09-01 | 0.56608 | 33.7653 | 19.1138 | 0 | 0 | INFRA
Lean | INFRA-REQ | 60 | 2031-10-01 | 0.58103 | 33.7653 | 19.6185 | 0 | 0 | INFRA
Lean | TOOLS-GH | 1 | 2026-11-01 | 2 | 4 | 8 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 2 | 2026-12-01 | 3 | 4 | 12 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 3 | 2027-01-01 | 3 | 4 | 12 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 4 | 2027-02-01 | 3 | 4 | 12 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 5 | 2027-03-01 | 3 | 4 | 12 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 6 | 2027-04-01 | 3 | 4 | 12 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 7 | 2027-05-01 | 4 | 4 | 16 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 8 | 2027-06-01 | 4 | 4 | 16 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 9 | 2027-07-01 | 4 | 4 | 16 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 10 | 2027-08-01 | 4 | 4 | 16 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 11 | 2027-09-01 | 4 | 4 | 16 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 12 | 2027-10-01 | 5 | 4 | 20 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 13 | 2027-11-01 | 5 | 4.12 | 20.6 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 14 | 2027-12-01 | 5 | 4.12 | 20.6 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 15 | 2028-01-01 | 5 | 4.12 | 20.6 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 16 | 2028-02-01 | 6 | 4.12 | 24.72 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 17 | 2028-03-01 | 6 | 4.12 | 24.72 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 18 | 2028-04-01 | 6 | 4.12 | 24.72 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 19 | 2028-05-01 | 6 | 4.12 | 24.72 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 20 | 2028-06-01 | 6 | 4.12 | 24.72 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 21 | 2028-07-01 | 6 | 4.12 | 24.72 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 22 | 2028-08-01 | 6 | 4.12 | 24.72 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 23 | 2028-09-01 | 6 | 4.12 | 24.72 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 24 | 2028-10-01 | 6 | 4.12 | 24.72 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 25 | 2028-11-01 | 6 | 4.2436 | 25.4616 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 26 | 2028-12-01 | 6 | 4.2436 | 25.4616 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 27 | 2029-01-01 | 6 | 4.2436 | 25.4616 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 28 | 2029-02-01 | 6 | 4.2436 | 25.4616 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 29 | 2029-03-01 | 6 | 4.2436 | 25.4616 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 30 | 2029-04-01 | 6 | 4.2436 | 25.4616 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 31 | 2029-05-01 | 7 | 4.2436 | 29.7052 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 32 | 2029-06-01 | 7 | 4.2436 | 29.7052 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 33 | 2029-07-01 | 7 | 4.2436 | 29.7052 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 34 | 2029-08-01 | 7 | 4.2436 | 29.7052 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 35 | 2029-09-01 | 7 | 4.2436 | 29.7052 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 36 | 2029-10-01 | 7 | 4.2436 | 29.7052 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 37 | 2029-11-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 38 | 2029-12-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 39 | 2030-01-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 40 | 2030-02-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 41 | 2030-03-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 42 | 2030-04-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 43 | 2030-05-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 44 | 2030-06-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 45 | 2030-07-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 46 | 2030-08-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 47 | 2030-09-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 48 | 2030-10-01 | 7 | 4.3709 | 30.5964 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 49 | 2030-11-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 50 | 2030-12-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 51 | 2031-01-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 52 | 2031-02-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 53 | 2031-03-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 54 | 2031-04-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 55 | 2031-05-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 56 | 2031-06-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 57 | 2031-07-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 58 | 2031-08-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 59 | 2031-09-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-GH | 60 | 2031-10-01 | 7 | 4.502 | 31.5142 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 1 | 2026-11-01 | 2 | 45 | 90 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 2 | 2026-12-01 | 3 | 45 | 135 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 3 | 2027-01-01 | 3 | 45 | 135 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 4 | 2027-02-01 | 3 | 45 | 135 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 5 | 2027-03-01 | 3 | 45 | 135 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 6 | 2027-04-01 | 3 | 45 | 135 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 7 | 2027-05-01 | 4 | 45 | 180 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 8 | 2027-06-01 | 4 | 45 | 180 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 9 | 2027-07-01 | 4 | 45 | 180 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 10 | 2027-08-01 | 4 | 45 | 180 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 11 | 2027-09-01 | 4 | 45 | 180 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 12 | 2027-10-01 | 5 | 45 | 225 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 13 | 2027-11-01 | 5 | 46.35 | 231.75 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 14 | 2027-12-01 | 5 | 46.35 | 231.75 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 15 | 2028-01-01 | 5 | 46.35 | 231.75 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 16 | 2028-02-01 | 6 | 46.35 | 278.1 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 17 | 2028-03-01 | 6 | 46.35 | 278.1 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 18 | 2028-04-01 | 6 | 46.35 | 278.1 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 19 | 2028-05-01 | 6 | 46.35 | 278.1 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 20 | 2028-06-01 | 6 | 46.35 | 278.1 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 21 | 2028-07-01 | 6 | 46.35 | 278.1 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 22 | 2028-08-01 | 6 | 46.35 | 278.1 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 23 | 2028-09-01 | 6 | 46.35 | 278.1 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 24 | 2028-10-01 | 6 | 46.35 | 278.1 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 25 | 2028-11-01 | 6 | 47.7405 | 286.443 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 26 | 2028-12-01 | 6 | 47.7405 | 286.443 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 27 | 2029-01-01 | 6 | 47.7405 | 286.443 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 28 | 2029-02-01 | 6 | 47.7405 | 286.443 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 29 | 2029-03-01 | 6 | 47.7405 | 286.443 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 30 | 2029-04-01 | 6 | 47.7405 | 286.443 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 31 | 2029-05-01 | 7 | 47.7405 | 334.1835 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 32 | 2029-06-01 | 7 | 47.7405 | 334.1835 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 33 | 2029-07-01 | 7 | 47.7405 | 334.1835 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 34 | 2029-08-01 | 7 | 47.7405 | 334.1835 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 35 | 2029-09-01 | 7 | 47.7405 | 334.1835 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 36 | 2029-10-01 | 7 | 47.7405 | 334.1835 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 37 | 2029-11-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 38 | 2029-12-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 39 | 2030-01-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 40 | 2030-02-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 41 | 2030-03-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 42 | 2030-04-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 43 | 2030-05-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 44 | 2030-06-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 45 | 2030-07-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 46 | 2030-08-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 47 | 2030-09-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 48 | 2030-10-01 | 7 | 49.1727 | 344.209 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 49 | 2030-11-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 50 | 2030-12-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 51 | 2031-01-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 52 | 2031-02-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 53 | 2031-03-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 54 | 2031-04-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 55 | 2031-05-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 56 | 2031-06-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 57 | 2031-07-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 58 | 2031-08-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 59 | 2031-09-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | TOOLS-CI | 60 | 2031-10-01 | 7 | 50.6479 | 354.5353 | 0 | 0 | TOOLS
Lean | LEGAL-SETUP | 1 | 2026-11-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 2 | 2026-12-01 | 1 | 20000 | 20000 | 20000 | 0 | LEGAL
Lean | LEGAL-SETUP | 3 | 2027-01-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 4 | 2027-02-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 5 | 2027-03-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 6 | 2027-04-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 7 | 2027-05-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 8 | 2027-06-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 9 | 2027-07-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 10 | 2027-08-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 11 | 2027-09-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 12 | 2027-10-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 13 | 2027-11-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 14 | 2027-12-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 15 | 2028-01-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 16 | 2028-02-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 17 | 2028-03-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 18 | 2028-04-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 19 | 2028-05-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 20 | 2028-06-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 21 | 2028-07-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 22 | 2028-08-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 23 | 2028-09-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 24 | 2028-10-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 25 | 2028-11-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 26 | 2028-12-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 27 | 2029-01-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 28 | 2029-02-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 29 | 2029-03-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 30 | 2029-04-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 31 | 2029-05-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 32 | 2029-06-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 33 | 2029-07-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 34 | 2029-08-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 35 | 2029-09-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 36 | 2029-10-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 37 | 2029-11-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 38 | 2029-12-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 39 | 2030-01-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 40 | 2030-02-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 41 | 2030-03-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 42 | 2030-04-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 43 | 2030-05-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 44 | 2030-06-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 45 | 2030-07-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 46 | 2030-08-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 47 | 2030-09-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 48 | 2030-10-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 49 | 2030-11-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 50 | 2030-12-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 51 | 2031-01-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 52 | 2031-02-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 53 | 2031-03-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 54 | 2031-04-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 55 | 2031-05-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 56 | 2031-06-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 57 | 2031-07-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 58 | 2031-08-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 59 | 2031-09-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-SETUP | 60 | 2031-10-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 1 | 2026-11-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 2 | 2026-12-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 3 | 2027-01-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 4 | 2027-02-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 5 | 2027-03-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 6 | 2027-04-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 7 | 2027-05-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 8 | 2027-06-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 9 | 2027-07-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 10 | 2027-08-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 11 | 2027-09-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 12 | 2027-10-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 13 | 2027-11-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 14 | 2027-12-01 | 1 | 12360 | 12360 | 12360 | 0 | LEGAL
Lean | LEGAL-RENEW | 15 | 2028-01-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 16 | 2028-02-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 17 | 2028-03-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 18 | 2028-04-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 19 | 2028-05-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 20 | 2028-06-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 21 | 2028-07-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 22 | 2028-08-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 23 | 2028-09-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 24 | 2028-10-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 25 | 2028-11-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 26 | 2028-12-01 | 1 | 12730.8 | 12730.8 | 12730.8 | 0 | LEGAL
Lean | LEGAL-RENEW | 27 | 2029-01-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 28 | 2029-02-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 29 | 2029-03-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 30 | 2029-04-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 31 | 2029-05-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 32 | 2029-06-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 33 | 2029-07-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 34 | 2029-08-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 35 | 2029-09-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 36 | 2029-10-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 37 | 2029-11-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 38 | 2029-12-01 | 1 | 13112.724 | 13112.724 | 13112.724 | 0 | LEGAL
Lean | LEGAL-RENEW | 39 | 2030-01-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 40 | 2030-02-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 41 | 2030-03-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 42 | 2030-04-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 43 | 2030-05-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 44 | 2030-06-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 45 | 2030-07-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 46 | 2030-08-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 47 | 2030-09-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 48 | 2030-10-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 49 | 2030-11-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 50 | 2030-12-01 | 1 | 13506.1057 | 13506.1057 | 13506.1057 | 0 | LEGAL
Lean | LEGAL-RENEW | 51 | 2031-01-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 52 | 2031-02-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 53 | 2031-03-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 54 | 2031-04-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 55 | 2031-05-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 56 | 2031-06-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 57 | 2031-07-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 58 | 2031-08-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 59 | 2031-09-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | LEGAL-RENEW | 60 | 2031-10-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Lean | SECURITY-TEST | 1 | 2026-11-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 2 | 2026-12-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 3 | 2027-01-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 4 | 2027-02-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 5 | 2027-03-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 6 | 2027-04-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 7 | 2027-05-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 8 | 2027-06-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 9 | 2027-07-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 10 | 2027-08-01 | 1 | 18000 | 18000 | 18000 | 0 | SECURITY
Lean | SECURITY-TEST | 11 | 2027-09-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 12 | 2027-10-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 13 | 2027-11-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 14 | 2027-12-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 15 | 2028-01-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 16 | 2028-02-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 17 | 2028-03-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 18 | 2028-04-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 19 | 2028-05-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 20 | 2028-06-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 21 | 2028-07-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 22 | 2028-08-01 | 1 | 18540 | 18540 | 18540 | 0 | SECURITY
Lean | SECURITY-TEST | 23 | 2028-09-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 24 | 2028-10-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 25 | 2028-11-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 26 | 2028-12-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 27 | 2029-01-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 28 | 2029-02-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 29 | 2029-03-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 30 | 2029-04-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 31 | 2029-05-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 32 | 2029-06-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 33 | 2029-07-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 34 | 2029-08-01 | 1 | 19096.2 | 19096.2 | 19096.2 | 0 | SECURITY
Lean | SECURITY-TEST | 35 | 2029-09-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 36 | 2029-10-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 37 | 2029-11-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 38 | 2029-12-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 39 | 2030-01-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 40 | 2030-02-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 41 | 2030-03-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 42 | 2030-04-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 43 | 2030-05-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 44 | 2030-06-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 45 | 2030-07-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 46 | 2030-08-01 | 1 | 19669.086 | 19669.086 | 19669.086 | 0 | SECURITY
Lean | SECURITY-TEST | 47 | 2030-09-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 48 | 2030-10-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 49 | 2030-11-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 50 | 2030-12-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 51 | 2031-01-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 52 | 2031-02-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 53 | 2031-03-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 54 | 2031-04-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 55 | 2031-05-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 56 | 2031-06-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 57 | 2031-07-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 58 | 2031-08-01 | 1 | 20259.1586 | 20259.1586 | 20259.1586 | 0 | SECURITY
Lean | SECURITY-TEST | 59 | 2031-09-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | SECURITY-TEST | 60 | 2031-10-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Lean | COMPLIANCE-EXT | 1 | 2026-11-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 2 | 2026-12-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 3 | 2027-01-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 4 | 2027-02-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 5 | 2027-03-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 6 | 2027-04-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 7 | 2027-05-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 8 | 2027-06-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 9 | 2027-07-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 10 | 2027-08-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 11 | 2027-09-01 | 1 | 15000 | 15000 | 15000 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 12 | 2027-10-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 13 | 2027-11-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 14 | 2027-12-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 15 | 2028-01-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 16 | 2028-02-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 17 | 2028-03-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 18 | 2028-04-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 19 | 2028-05-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 20 | 2028-06-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 21 | 2028-07-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 22 | 2028-08-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 23 | 2028-09-01 | 1 | 15450 | 15450 | 15450 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 24 | 2028-10-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 25 | 2028-11-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 26 | 2028-12-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 27 | 2029-01-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 28 | 2029-02-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 29 | 2029-03-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 30 | 2029-04-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 31 | 2029-05-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 32 | 2029-06-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 33 | 2029-07-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 34 | 2029-08-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 35 | 2029-09-01 | 1 | 15913.5 | 15913.5 | 15913.5 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 36 | 2029-10-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 37 | 2029-11-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 38 | 2029-12-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 39 | 2030-01-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 40 | 2030-02-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 41 | 2030-03-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 42 | 2030-04-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 43 | 2030-05-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 44 | 2030-06-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 45 | 2030-07-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 46 | 2030-08-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 47 | 2030-09-01 | 1 | 16390.905 | 16390.905 | 16390.905 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 48 | 2030-10-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 49 | 2030-11-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 50 | 2030-12-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 51 | 2031-01-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 52 | 2031-02-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 53 | 2031-03-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 54 | 2031-04-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 55 | 2031-05-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 56 | 2031-06-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 57 | 2031-07-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 58 | 2031-08-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 59 | 2031-09-01 | 1 | 16882.6322 | 16882.6322 | 16882.6322 | 0 | COMPLIANCE
Lean | COMPLIANCE-EXT | 60 | 2031-10-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Lean | INSURANCE | 1 | 2026-11-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 2 | 2026-12-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 3 | 2027-01-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 4 | 2027-02-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 5 | 2027-03-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 6 | 2027-04-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 7 | 2027-05-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 8 | 2027-06-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 9 | 2027-07-01 | 1 | 12000 | 12000 | 12000 | 0 | INSURANCE
Lean | INSURANCE | 10 | 2027-08-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 11 | 2027-09-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 12 | 2027-10-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 13 | 2027-11-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 14 | 2027-12-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 15 | 2028-01-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 16 | 2028-02-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 17 | 2028-03-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 18 | 2028-04-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 19 | 2028-05-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 20 | 2028-06-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 21 | 2028-07-01 | 1 | 12360 | 12360 | 12360 | 0 | INSURANCE
Lean | INSURANCE | 22 | 2028-08-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 23 | 2028-09-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 24 | 2028-10-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 25 | 2028-11-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 26 | 2028-12-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 27 | 2029-01-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 28 | 2029-02-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 29 | 2029-03-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 30 | 2029-04-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 31 | 2029-05-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 32 | 2029-06-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 33 | 2029-07-01 | 1 | 12730.8 | 12730.8 | 12730.8 | 0 | INSURANCE
Lean | INSURANCE | 34 | 2029-08-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 35 | 2029-09-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 36 | 2029-10-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 37 | 2029-11-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 38 | 2029-12-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 39 | 2030-01-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 40 | 2030-02-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 41 | 2030-03-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 42 | 2030-04-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 43 | 2030-05-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 44 | 2030-06-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 45 | 2030-07-01 | 1 | 13112.724 | 13112.724 | 13112.724 | 0 | INSURANCE
Lean | INSURANCE | 46 | 2030-08-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 47 | 2030-09-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 48 | 2030-10-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 49 | 2030-11-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 50 | 2030-12-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 51 | 2031-01-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 52 | 2031-02-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 53 | 2031-03-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 54 | 2031-04-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 55 | 2031-05-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 56 | 2031-06-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 57 | 2031-07-01 | 1 | 13506.1057 | 13506.1057 | 13506.1057 | 0 | INSURANCE
Lean | INSURANCE | 58 | 2031-08-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 59 | 2031-09-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | INSURANCE | 60 | 2031-10-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Lean | ACCOUNTING | 1 | 2026-11-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 2 | 2026-12-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 3 | 2027-01-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 4 | 2027-02-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 5 | 2027-03-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 6 | 2027-04-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 7 | 2027-05-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 8 | 2027-06-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 9 | 2027-07-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 10 | 2027-08-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 11 | 2027-09-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 12 | 2027-10-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Lean | ACCOUNTING | 13 | 2027-11-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 14 | 2027-12-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 15 | 2028-01-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 16 | 2028-02-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 17 | 2028-03-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 18 | 2028-04-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 19 | 2028-05-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 20 | 2028-06-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 21 | 2028-07-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 22 | 2028-08-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 23 | 2028-09-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 24 | 2028-10-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Lean | ACCOUNTING | 25 | 2028-11-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 26 | 2028-12-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 27 | 2029-01-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 28 | 2029-02-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 29 | 2029-03-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 30 | 2029-04-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 31 | 2029-05-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 32 | 2029-06-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 33 | 2029-07-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 34 | 2029-08-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 35 | 2029-09-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 36 | 2029-10-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Lean | ACCOUNTING | 37 | 2029-11-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 38 | 2029-12-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 39 | 2030-01-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 40 | 2030-02-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 41 | 2030-03-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 42 | 2030-04-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 43 | 2030-05-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 44 | 2030-06-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 45 | 2030-07-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 46 | 2030-08-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 47 | 2030-09-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 48 | 2030-10-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Lean | ACCOUNTING | 49 | 2030-11-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 50 | 2030-12-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 51 | 2031-01-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 52 | 2031-02-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 53 | 2031-03-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 54 | 2031-04-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 55 | 2031-05-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 56 | 2031-06-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 57 | 2031-07-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 58 | 2031-08-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 59 | 2031-09-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | ACCOUNTING | 60 | 2031-10-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Lean | SUPPORT | 1 | 2026-11-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Lean | SUPPORT | 2 | 2026-12-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Lean | SUPPORT | 3 | 2027-01-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Lean | SUPPORT | 4 | 2027-02-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Lean | SUPPORT | 5 | 2027-03-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Lean | SUPPORT | 6 | 2027-04-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Lean | SUPPORT | 7 | 2027-05-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Lean | SUPPORT | 8 | 2027-06-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Lean | SUPPORT | 9 | 2027-07-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Lean | SUPPORT | 10 | 2027-08-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Lean | SUPPORT | 11 | 2027-09-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Lean | SUPPORT | 12 | 2027-10-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Lean | SUPPORT | 13 | 2027-11-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 14 | 2027-12-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 15 | 2028-01-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 16 | 2028-02-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 17 | 2028-03-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 18 | 2028-04-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 19 | 2028-05-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 20 | 2028-06-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 21 | 2028-07-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 22 | 2028-08-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 23 | 2028-09-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 24 | 2028-10-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Lean | SUPPORT | 25 | 2028-11-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 26 | 2028-12-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 27 | 2029-01-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 28 | 2029-02-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 29 | 2029-03-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 30 | 2029-04-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 31 | 2029-05-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 32 | 2029-06-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 33 | 2029-07-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 34 | 2029-08-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 35 | 2029-09-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 36 | 2029-10-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Lean | SUPPORT | 37 | 2029-11-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 38 | 2029-12-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 39 | 2030-01-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 40 | 2030-02-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 41 | 2030-03-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 42 | 2030-04-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 43 | 2030-05-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 44 | 2030-06-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 45 | 2030-07-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 46 | 2030-08-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 47 | 2030-09-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 48 | 2030-10-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Lean | SUPPORT | 49 | 2030-11-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 50 | 2030-12-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 51 | 2031-01-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 52 | 2031-02-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 53 | 2031-03-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 54 | 2031-04-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 55 | 2031-05-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 56 | 2031-06-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 57 | 2031-07-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 58 | 2031-08-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 59 | 2031-09-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | SUPPORT | 60 | 2031-10-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Lean | MARKETING | 1 | 2026-11-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 2 | 2026-12-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 3 | 2027-01-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 4 | 2027-02-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 5 | 2027-03-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 6 | 2027-04-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 7 | 2027-05-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 8 | 2027-06-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 9 | 2027-07-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 10 | 2027-08-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 11 | 2027-09-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 12 | 2027-10-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 13 | 2027-11-01 | 0 | 77.25 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 14 | 2027-12-01 | 0 | 77.25 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 15 | 2028-01-01 | 0 | 77.25 | 0 | 0 | 0 | MARKETING
Lean | MARKETING | 16 | 2028-02-01 | 0.5 | 77.25 | 38.625 | 0 | 0 | MARKETING
Lean | MARKETING | 17 | 2028-03-01 | 0.9925 | 77.25 | 76.6706 | 0 | 0 | MARKETING
Lean | MARKETING | 18 | 2028-04-01 | 1.4776 | 77.25 | 114.1456 | 0 | 0 | MARKETING
Lean | MARKETING | 19 | 2028-05-01 | 1.9554 | 77.25 | 151.0584 | 0 | 0 | MARKETING
Lean | MARKETING | 20 | 2028-06-01 | 2.4261 | 77.25 | 187.4175 | 0 | 0 | MARKETING
Lean | MARKETING | 21 | 2028-07-01 | 2.8897 | 77.25 | 223.2312 | 0 | 0 | MARKETING
Lean | MARKETING | 22 | 2028-08-01 | 3.3464 | 77.25 | 258.5078 | 0 | 0 | MARKETING
Lean | MARKETING | 23 | 2028-09-01 | 3.7962 | 77.25 | 293.2552 | 0 | 0 | MARKETING
Lean | MARKETING | 24 | 2028-10-01 | 4.2392 | 77.25 | 327.4813 | 0 | 0 | MARKETING
Lean | MARKETING | 25 | 2028-11-01 | 4.6757 | 79.5675 | 372.0299 | 0 | 0 | MARKETING
Lean | MARKETING | 26 | 2028-12-01 | 5.1055 | 79.5675 | 406.2332 | 0 | 0 | MARKETING
Lean | MARKETING | 27 | 2029-01-01 | 5.5289 | 79.5675 | 439.9235 | 0 | 0 | MARKETING
Lean | MARKETING | 28 | 2029-02-01 | 6.071 | 79.5675 | 483.0543 | 0 | 0 | MARKETING
Lean | MARKETING | 29 | 2029-03-01 | 6.6049 | 79.5675 | 525.5382 | 0 | 0 | MARKETING
Lean | MARKETING | 30 | 2029-04-01 | 7.1309 | 79.5675 | 567.3848 | 0 | 0 | MARKETING
Lean | MARKETING | 31 | 2029-05-01 | 7.6489 | 79.5675 | 608.6037 | 0 | 0 | MARKETING
Lean | MARKETING | 32 | 2029-06-01 | 8.1592 | 79.5675 | 649.2044 | 0 | 0 | MARKETING
Lean | MARKETING | 33 | 2029-07-01 | 8.6618 | 79.5675 | 689.196 | 0 | 0 | MARKETING
Lean | MARKETING | 34 | 2029-08-01 | 9.1569 | 79.5675 | 728.5877 | 0 | 0 | MARKETING
Lean | MARKETING | 35 | 2029-09-01 | 9.6445 | 79.5675 | 767.3886 | 0 | 0 | MARKETING
Lean | MARKETING | 36 | 2029-10-01 | 10.1248 | 79.5675 | 805.6075 | 0 | 0 | MARKETING
Lean | MARKETING | 37 | 2029-11-01 | 10.598 | 81.9545 | 868.5506 | 0 | 0 | MARKETING
Lean | MARKETING | 38 | 2029-12-01 | 11.064 | 81.9545 | 906.7439 | 0 | 0 | MARKETING
Lean | MARKETING | 39 | 2030-01-01 | 11.523 | 81.9545 | 944.3644 | 0 | 0 | MARKETING
Lean | MARKETING | 40 | 2030-02-01 | 12.1314 | 81.9545 | 994.2259 | 0 | 0 | MARKETING
Lean | MARKETING | 41 | 2030-03-01 | 12.7307 | 81.9545 | 1043.3395 | 0 | 0 | MARKETING
Lean | MARKETING | 42 | 2030-04-01 | 13.321 | 81.9545 | 1091.7163 | 0 | 0 | MARKETING
Lean | MARKETING | 43 | 2030-05-01 | 13.9024 | 81.9545 | 1139.3676 | 0 | 0 | MARKETING
Lean | MARKETING | 44 | 2030-06-01 | 14.4751 | 81.9545 | 1186.304 | 0 | 0 | MARKETING
Lean | MARKETING | 45 | 2030-07-01 | 15.0393 | 81.9545 | 1232.5364 | 0 | 0 | MARKETING
Lean | MARKETING | 46 | 2030-08-01 | 15.5949 | 81.9545 | 1278.0754 | 0 | 0 | MARKETING
Lean | MARKETING | 47 | 2030-09-01 | 16.1423 | 81.9545 | 1322.9312 | 0 | 0 | MARKETING
Lean | MARKETING | 48 | 2030-10-01 | 16.6814 | 81.9545 | 1367.1142 | 0 | 0 | MARKETING
Lean | MARKETING | 49 | 2030-11-01 | 17.2124 | 84.4132 | 1452.9535 | 0 | 0 | MARKETING
Lean | MARKETING | 50 | 2030-12-01 | 17.7355 | 84.4132 | 1497.107 | 0 | 0 | MARKETING
Lean | MARKETING | 51 | 2031-01-01 | 18.2507 | 84.4132 | 1540.5982 | 0 | 0 | MARKETING
Lean | MARKETING | 52 | 2031-02-01 | 18.9535 | 84.4132 | 1599.9239 | 0 | 0 | MARKETING
Lean | MARKETING | 53 | 2031-03-01 | 19.6457 | 84.4132 | 1658.3598 | 0 | 0 | MARKETING
Lean | MARKETING | 54 | 2031-04-01 | 20.3276 | 84.4132 | 1715.9191 | 0 | 0 | MARKETING
Lean | MARKETING | 55 | 2031-05-01 | 20.9993 | 84.4132 | 1772.6151 | 0 | 0 | MARKETING
Lean | MARKETING | 56 | 2031-06-01 | 21.6608 | 84.4132 | 1828.4606 | 0 | 0 | MARKETING
Lean | MARKETING | 57 | 2031-07-01 | 22.3125 | 84.4132 | 1883.4684 | 0 | 0 | MARKETING
Lean | MARKETING | 58 | 2031-08-01 | 22.9544 | 84.4132 | 1937.6511 | 0 | 0 | MARKETING
Lean | MARKETING | 59 | 2031-09-01 | 23.5866 | 84.4132 | 1991.021 | 0 | 0 | MARKETING
Lean | MARKETING | 60 | 2031-10-01 | 24.2094 | 84.4132 | 2043.5904 | 0 | 0 | MARKETING
Lean | ONBOARD | 1 | 2026-11-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 2 | 2026-12-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 3 | 2027-01-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 4 | 2027-02-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 5 | 2027-03-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 6 | 2027-04-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 7 | 2027-05-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 8 | 2027-06-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 9 | 2027-07-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 10 | 2027-08-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 11 | 2027-09-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 12 | 2027-10-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 13 | 2027-11-01 | 0 | 309 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 14 | 2027-12-01 | 0 | 309 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 15 | 2028-01-01 | 0 | 309 | 0 | 0 | 0 | ONBOARD
Lean | ONBOARD | 16 | 2028-02-01 | 0.5 | 309 | 154.5 | 0 | 0 | ONBOARD
Lean | ONBOARD | 17 | 2028-03-01 | 0.5 | 309 | 154.5 | 0 | 0 | ONBOARD
Lean | ONBOARD | 18 | 2028-04-01 | 0.5 | 309 | 154.5 | 0 | 0 | ONBOARD
Lean | ONBOARD | 19 | 2028-05-01 | 0.5 | 309 | 154.5 | 0 | 0 | ONBOARD
Lean | ONBOARD | 20 | 2028-06-01 | 0.5 | 309 | 154.5 | 0 | 0 | ONBOARD
Lean | ONBOARD | 21 | 2028-07-01 | 0.5 | 309 | 154.5 | 0 | 0 | ONBOARD
Lean | ONBOARD | 22 | 2028-08-01 | 0.5 | 309 | 154.5 | 0 | 0 | ONBOARD
Lean | ONBOARD | 23 | 2028-09-01 | 0.5 | 309 | 154.5 | 0 | 0 | ONBOARD
Lean | ONBOARD | 24 | 2028-10-01 | 0.5 | 309 | 154.5 | 0 | 0 | ONBOARD
Lean | ONBOARD | 25 | 2028-11-01 | 0.5 | 318.27 | 159.135 | 0 | 0 | ONBOARD
Lean | ONBOARD | 26 | 2028-12-01 | 0.5 | 318.27 | 159.135 | 0 | 0 | ONBOARD
Lean | ONBOARD | 27 | 2029-01-01 | 0.5 | 318.27 | 159.135 | 0 | 0 | ONBOARD
Lean | ONBOARD | 28 | 2029-02-01 | 0.625 | 318.27 | 198.9187 | 0 | 0 | ONBOARD
Lean | ONBOARD | 29 | 2029-03-01 | 0.625 | 318.27 | 198.9187 | 0 | 0 | ONBOARD
Lean | ONBOARD | 30 | 2029-04-01 | 0.625 | 318.27 | 198.9187 | 0 | 0 | ONBOARD
Lean | ONBOARD | 31 | 2029-05-01 | 0.625 | 318.27 | 198.9187 | 0 | 0 | ONBOARD
Lean | ONBOARD | 32 | 2029-06-01 | 0.625 | 318.27 | 198.9187 | 0 | 0 | ONBOARD
Lean | ONBOARD | 33 | 2029-07-01 | 0.625 | 318.27 | 198.9187 | 0 | 0 | ONBOARD
Lean | ONBOARD | 34 | 2029-08-01 | 0.625 | 318.27 | 198.9187 | 0 | 0 | ONBOARD
Lean | ONBOARD | 35 | 2029-09-01 | 0.625 | 318.27 | 198.9187 | 0 | 0 | ONBOARD
Lean | ONBOARD | 36 | 2029-10-01 | 0.625 | 318.27 | 198.9187 | 0 | 0 | ONBOARD
Lean | ONBOARD | 37 | 2029-11-01 | 0.625 | 327.8181 | 204.8863 | 0 | 0 | ONBOARD
Lean | ONBOARD | 38 | 2029-12-01 | 0.625 | 327.8181 | 204.8863 | 0 | 0 | ONBOARD
Lean | ONBOARD | 39 | 2030-01-01 | 0.625 | 327.8181 | 204.8863 | 0 | 0 | ONBOARD
Lean | ONBOARD | 40 | 2030-02-01 | 0.78125 | 327.8181 | 256.1079 | 0 | 0 | ONBOARD
Lean | ONBOARD | 41 | 2030-03-01 | 0.78125 | 327.8181 | 256.1079 | 0 | 0 | ONBOARD
Lean | ONBOARD | 42 | 2030-04-01 | 0.78125 | 327.8181 | 256.1079 | 0 | 0 | ONBOARD
Lean | ONBOARD | 43 | 2030-05-01 | 0.78125 | 327.8181 | 256.1079 | 0 | 0 | ONBOARD
Lean | ONBOARD | 44 | 2030-06-01 | 0.78125 | 327.8181 | 256.1079 | 0 | 0 | ONBOARD
Lean | ONBOARD | 45 | 2030-07-01 | 0.78125 | 327.8181 | 256.1079 | 0 | 0 | ONBOARD
Lean | ONBOARD | 46 | 2030-08-01 | 0.78125 | 327.8181 | 256.1079 | 0 | 0 | ONBOARD
Lean | ONBOARD | 47 | 2030-09-01 | 0.78125 | 327.8181 | 256.1079 | 0 | 0 | ONBOARD
Lean | ONBOARD | 48 | 2030-10-01 | 0.78125 | 327.8181 | 256.1079 | 0 | 0 | ONBOARD
Lean | ONBOARD | 49 | 2030-11-01 | 0.78125 | 337.6526 | 263.7911 | 0 | 0 | ONBOARD
Lean | ONBOARD | 50 | 2030-12-01 | 0.78125 | 337.6526 | 263.7911 | 0 | 0 | ONBOARD
Lean | ONBOARD | 51 | 2031-01-01 | 0.78125 | 337.6526 | 263.7911 | 0 | 0 | ONBOARD
Lean | ONBOARD | 52 | 2031-02-01 | 0.97656 | 337.6526 | 329.7389 | 0 | 0 | ONBOARD
Lean | ONBOARD | 53 | 2031-03-01 | 0.97656 | 337.6526 | 329.7389 | 0 | 0 | ONBOARD
Lean | ONBOARD | 54 | 2031-04-01 | 0.97656 | 337.6526 | 329.7389 | 0 | 0 | ONBOARD
Lean | ONBOARD | 55 | 2031-05-01 | 0.97656 | 337.6526 | 329.7389 | 0 | 0 | ONBOARD
Lean | ONBOARD | 56 | 2031-06-01 | 0.97656 | 337.6526 | 329.7389 | 0 | 0 | ONBOARD
Lean | ONBOARD | 57 | 2031-07-01 | 0.97656 | 337.6526 | 329.7389 | 0 | 0 | ONBOARD
Lean | ONBOARD | 58 | 2031-08-01 | 0.97656 | 337.6526 | 329.7389 | 0 | 0 | ONBOARD
Lean | ONBOARD | 59 | 2031-09-01 | 0.97656 | 337.6526 | 329.7389 | 0 | 0 | ONBOARD
Lean | ONBOARD | 60 | 2031-10-01 | 0.97656 | 337.6526 | 329.7389 | 0 | 0 | ONBOARD
Lean | AI-IN | 1 | 2026-11-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 2 | 2026-12-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 3 | 2027-01-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 4 | 2027-02-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 5 | 2027-03-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 6 | 2027-04-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 7 | 2027-05-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 8 | 2027-06-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 9 | 2027-07-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 10 | 2027-08-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 11 | 2027-09-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 12 | 2027-10-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Lean | AI-IN | 13 | 2027-11-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 14 | 2027-12-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 15 | 2028-01-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 16 | 2028-02-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 17 | 2028-03-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 18 | 2028-04-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 19 | 2028-05-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 20 | 2028-06-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 21 | 2028-07-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 22 | 2028-08-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 23 | 2028-09-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 24 | 2028-10-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Lean | AI-IN | 25 | 2028-11-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 26 | 2028-12-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 27 | 2029-01-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 28 | 2029-02-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 29 | 2029-03-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 30 | 2029-04-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 31 | 2029-05-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 32 | 2029-06-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 33 | 2029-07-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 34 | 2029-08-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 35 | 2029-09-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 36 | 2029-10-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Lean | AI-IN | 37 | 2029-11-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 38 | 2029-12-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 39 | 2030-01-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 40 | 2030-02-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 41 | 2030-03-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 42 | 2030-04-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 43 | 2030-05-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 44 | 2030-06-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 45 | 2030-07-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 46 | 2030-08-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 47 | 2030-09-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 48 | 2030-10-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Lean | AI-IN | 49 | 2030-11-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 50 | 2030-12-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 51 | 2031-01-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 52 | 2031-02-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 53 | 2031-03-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 54 | 2031-04-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 55 | 2031-05-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 56 | 2031-06-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 57 | 2031-07-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 58 | 2031-08-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 59 | 2031-09-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-IN | 60 | 2031-10-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Lean | AI-OUT | 1 | 2026-11-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 2 | 2026-12-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 3 | 2027-01-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 4 | 2027-02-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 5 | 2027-03-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 6 | 2027-04-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 7 | 2027-05-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 8 | 2027-06-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 9 | 2027-07-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 10 | 2027-08-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 11 | 2027-09-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 12 | 2027-10-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Lean | AI-OUT | 13 | 2027-11-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 14 | 2027-12-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 15 | 2028-01-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 16 | 2028-02-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 17 | 2028-03-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 18 | 2028-04-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 19 | 2028-05-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 20 | 2028-06-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 21 | 2028-07-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 22 | 2028-08-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 23 | 2028-09-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 24 | 2028-10-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Lean | AI-OUT | 25 | 2028-11-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 26 | 2028-12-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 27 | 2029-01-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 28 | 2029-02-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 29 | 2029-03-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 30 | 2029-04-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 31 | 2029-05-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 32 | 2029-06-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 33 | 2029-07-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 34 | 2029-08-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 35 | 2029-09-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 36 | 2029-10-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Lean | AI-OUT | 37 | 2029-11-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 38 | 2029-12-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 39 | 2030-01-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 40 | 2030-02-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 41 | 2030-03-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 42 | 2030-04-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 43 | 2030-05-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 44 | 2030-06-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 45 | 2030-07-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 46 | 2030-08-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 47 | 2030-09-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 48 | 2030-10-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Lean | AI-OUT | 49 | 2030-11-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 50 | 2030-12-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 51 | 2031-01-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 52 | 2031-02-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 53 | 2031-03-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 54 | 2031-04-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 55 | 2031-05-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 56 | 2031-06-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 57 | 2031-07-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 58 | 2031-08-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 59 | 2031-09-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-OUT | 60 | 2031-10-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 1 | 2026-11-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 2 | 2026-12-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 3 | 2027-01-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 4 | 2027-02-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 5 | 2027-03-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 6 | 2027-04-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 7 | 2027-05-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 8 | 2027-06-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 9 | 2027-07-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 10 | 2027-08-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 11 | 2027-09-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 12 | 2027-10-01 | 0 | 15000 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 13 | 2027-11-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 14 | 2027-12-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 15 | 2028-01-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 16 | 2028-02-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 17 | 2028-03-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 18 | 2028-04-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 19 | 2028-05-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 20 | 2028-06-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 21 | 2028-07-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 22 | 2028-08-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 23 | 2028-09-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 24 | 2028-10-01 | 0 | 15450 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 25 | 2028-11-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 26 | 2028-12-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 27 | 2029-01-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 28 | 2029-02-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 29 | 2029-03-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 30 | 2029-04-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 31 | 2029-05-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 32 | 2029-06-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 33 | 2029-07-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 34 | 2029-08-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 35 | 2029-09-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 36 | 2029-10-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 37 | 2029-11-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 38 | 2029-12-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 39 | 2030-01-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 40 | 2030-02-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 41 | 2030-03-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 42 | 2030-04-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 43 | 2030-05-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 44 | 2030-06-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 45 | 2030-07-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 46 | 2030-08-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 47 | 2030-09-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 48 | 2030-10-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 49 | 2030-11-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 50 | 2030-12-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 51 | 2031-01-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 52 | 2031-02-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 53 | 2031-03-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 54 | 2031-04-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 55 | 2031-05-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 56 | 2031-06-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 57 | 2031-07-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 58 | 2031-08-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 59 | 2031-09-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | AI-EVAL | 60 | 2031-10-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Lean | CTMS-EXT | 1 | 2026-11-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 2 | 2026-12-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 3 | 2027-01-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 4 | 2027-02-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 5 | 2027-03-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 6 | 2027-04-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 7 | 2027-05-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 8 | 2027-06-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 9 | 2027-07-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 10 | 2027-08-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 11 | 2027-09-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 12 | 2027-10-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 13 | 2027-11-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 14 | 2027-12-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 15 | 2028-01-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 16 | 2028-02-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 17 | 2028-03-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 18 | 2028-04-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 19 | 2028-05-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 20 | 2028-06-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 21 | 2028-07-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 22 | 2028-08-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 23 | 2028-09-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 24 | 2028-10-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 25 | 2028-11-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 26 | 2028-12-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 27 | 2029-01-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 28 | 2029-02-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 29 | 2029-03-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 30 | 2029-04-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 31 | 2029-05-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 32 | 2029-06-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 33 | 2029-07-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 34 | 2029-08-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 35 | 2029-09-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 36 | 2029-10-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 37 | 2029-11-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 38 | 2029-12-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 39 | 2030-01-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 40 | 2030-02-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 41 | 2030-03-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 42 | 2030-04-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 43 | 2030-05-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 44 | 2030-06-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 45 | 2030-07-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 46 | 2030-08-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 47 | 2030-09-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 48 | 2030-10-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 49 | 2030-11-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 50 | 2030-12-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 51 | 2031-01-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 52 | 2031-02-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 53 | 2031-03-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 54 | 2031-04-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 55 | 2031-05-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 56 | 2031-06-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 57 | 2031-07-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 58 | 2031-08-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 59 | 2031-09-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Lean | CTMS-EXT | 60 | 2031-10-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | INFRA-APP | 1 | 2026-11-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 2 | 2026-12-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 3 | 2027-01-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 4 | 2027-02-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 5 | 2027-03-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 6 | 2027-04-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 7 | 2027-05-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 8 | 2027-06-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 9 | 2027-07-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 10 | 2027-08-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 11 | 2027-09-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 12 | 2027-10-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Base | INFRA-APP | 13 | 2027-11-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 14 | 2027-12-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 15 | 2028-01-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 16 | 2028-02-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 17 | 2028-03-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 18 | 2028-04-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 19 | 2028-05-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 20 | 2028-06-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 21 | 2028-07-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 22 | 2028-08-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 23 | 2028-09-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 24 | 2028-10-01 | 1 | 412 | 412 | 412 | 0 | INFRA
Base | INFRA-APP | 25 | 2028-11-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 26 | 2028-12-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 27 | 2029-01-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 28 | 2029-02-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 29 | 2029-03-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 30 | 2029-04-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 31 | 2029-05-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 32 | 2029-06-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 33 | 2029-07-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 34 | 2029-08-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 35 | 2029-09-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 36 | 2029-10-01 | 1 | 424.36 | 424.36 | 424.36 | 0 | INFRA
Base | INFRA-APP | 37 | 2029-11-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 38 | 2029-12-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 39 | 2030-01-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 40 | 2030-02-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 41 | 2030-03-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 42 | 2030-04-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 43 | 2030-05-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 44 | 2030-06-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 45 | 2030-07-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 46 | 2030-08-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 47 | 2030-09-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 48 | 2030-10-01 | 1 | 437.0908 | 437.0908 | 437.0908 | 0 | INFRA
Base | INFRA-APP | 49 | 2030-11-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 50 | 2030-12-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 51 | 2031-01-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 52 | 2031-02-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 53 | 2031-03-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 54 | 2031-04-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 55 | 2031-05-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 56 | 2031-06-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 57 | 2031-07-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 58 | 2031-08-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 59 | 2031-09-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-APP | 60 | 2031-10-01 | 1 | 450.2035 | 450.2035 | 450.2035 | 0 | INFRA
Base | INFRA-DB | 1 | 2026-11-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 2 | 2026-12-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 3 | 2027-01-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 4 | 2027-02-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 5 | 2027-03-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 6 | 2027-04-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 7 | 2027-05-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 8 | 2027-06-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 9 | 2027-07-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 10 | 2027-08-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 11 | 2027-09-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 12 | 2027-10-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Base | INFRA-DB | 13 | 2027-11-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 14 | 2027-12-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 15 | 2028-01-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 16 | 2028-02-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 17 | 2028-03-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 18 | 2028-04-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 19 | 2028-05-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 20 | 2028-06-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 21 | 2028-07-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 22 | 2028-08-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 23 | 2028-09-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 24 | 2028-10-01 | 1 | 618 | 618 | 618 | 0 | INFRA
Base | INFRA-DB | 25 | 2028-11-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 26 | 2028-12-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 27 | 2029-01-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 28 | 2029-02-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 29 | 2029-03-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 30 | 2029-04-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 31 | 2029-05-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 32 | 2029-06-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 33 | 2029-07-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 34 | 2029-08-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 35 | 2029-09-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 36 | 2029-10-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | INFRA
Base | INFRA-DB | 37 | 2029-11-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 38 | 2029-12-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 39 | 2030-01-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 40 | 2030-02-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 41 | 2030-03-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 42 | 2030-04-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 43 | 2030-05-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 44 | 2030-06-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 45 | 2030-07-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 46 | 2030-08-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 47 | 2030-09-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 48 | 2030-10-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | INFRA
Base | INFRA-DB | 49 | 2030-11-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 50 | 2030-12-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 51 | 2031-01-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 52 | 2031-02-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 53 | 2031-03-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 54 | 2031-04-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 55 | 2031-05-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 56 | 2031-06-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 57 | 2031-07-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 58 | 2031-08-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 59 | 2031-09-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-DB | 60 | 2031-10-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | INFRA
Base | INFRA-AWS | 1 | 2026-11-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 2 | 2026-12-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 3 | 2027-01-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 4 | 2027-02-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 5 | 2027-03-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 6 | 2027-04-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 7 | 2027-05-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 8 | 2027-06-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 9 | 2027-07-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 10 | 2027-08-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 11 | 2027-09-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 12 | 2027-10-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 13 | 2027-11-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 14 | 2027-12-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 15 | 2028-01-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 16 | 2028-02-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 17 | 2028-03-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 18 | 2028-04-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 19 | 2028-05-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 20 | 2028-06-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 21 | 2028-07-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 22 | 2028-08-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 23 | 2028-09-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 24 | 2028-10-01 | 0 | 1133 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 25 | 2028-11-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 26 | 2028-12-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 27 | 2029-01-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 28 | 2029-02-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 29 | 2029-03-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 30 | 2029-04-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 31 | 2029-05-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 32 | 2029-06-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 33 | 2029-07-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 34 | 2029-08-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 35 | 2029-09-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 36 | 2029-10-01 | 0 | 1166.99 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 37 | 2029-11-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 38 | 2029-12-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 39 | 2030-01-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 40 | 2030-02-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 41 | 2030-03-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 42 | 2030-04-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 43 | 2030-05-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 44 | 2030-06-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 45 | 2030-07-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 46 | 2030-08-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 47 | 2030-09-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 48 | 2030-10-01 | 0 | 1201.9997 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 49 | 2030-11-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 50 | 2030-12-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 51 | 2031-01-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 52 | 2031-02-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 53 | 2031-03-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 54 | 2031-04-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 55 | 2031-05-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 56 | 2031-06-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 57 | 2031-07-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 58 | 2031-08-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 59 | 2031-09-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-AWS | 60 | 2031-10-01 | 0 | 1238.0597 | 0 | 0 | 0 | INFRA
Base | INFRA-EDGE | 1 | 2026-11-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 2 | 2026-12-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 3 | 2027-01-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 4 | 2027-02-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 5 | 2027-03-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 6 | 2027-04-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 7 | 2027-05-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 8 | 2027-06-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 9 | 2027-07-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 10 | 2027-08-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 11 | 2027-09-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 12 | 2027-10-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Base | INFRA-EDGE | 13 | 2027-11-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 14 | 2027-12-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 15 | 2028-01-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 16 | 2028-02-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 17 | 2028-03-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 18 | 2028-04-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 19 | 2028-05-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 20 | 2028-06-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 21 | 2028-07-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 22 | 2028-08-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 23 | 2028-09-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 24 | 2028-10-01 | 1 | 257.5 | 257.5 | 257.5 | 0 | INFRA
Base | INFRA-EDGE | 25 | 2028-11-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 26 | 2028-12-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 27 | 2029-01-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 28 | 2029-02-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 29 | 2029-03-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 30 | 2029-04-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 31 | 2029-05-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 32 | 2029-06-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 33 | 2029-07-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 34 | 2029-08-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 35 | 2029-09-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 36 | 2029-10-01 | 1 | 265.225 | 265.225 | 265.225 | 0 | INFRA
Base | INFRA-EDGE | 37 | 2029-11-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 38 | 2029-12-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 39 | 2030-01-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 40 | 2030-02-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 41 | 2030-03-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 42 | 2030-04-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 43 | 2030-05-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 44 | 2030-06-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 45 | 2030-07-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 46 | 2030-08-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 47 | 2030-09-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 48 | 2030-10-01 | 1 | 273.1818 | 273.1818 | 273.1818 | 0 | INFRA
Base | INFRA-EDGE | 49 | 2030-11-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 50 | 2030-12-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 51 | 2031-01-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 52 | 2031-02-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 53 | 2031-03-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 54 | 2031-04-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 55 | 2031-05-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 56 | 2031-06-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 57 | 2031-07-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 58 | 2031-08-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 59 | 2031-09-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-EDGE | 60 | 2031-10-01 | 1 | 281.3772 | 281.3772 | 281.3772 | 0 | INFRA
Base | INFRA-STORE | 1 | 2026-11-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 2 | 2026-12-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 3 | 2027-01-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 4 | 2027-02-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 5 | 2027-03-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 6 | 2027-04-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 7 | 2027-05-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 8 | 2027-06-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 9 | 2027-07-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 10 | 2027-08-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 11 | 2027-09-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 12 | 2027-10-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Base | INFRA-STORE | 13 | 2027-11-01 | 5 | 0.1545 | 0.7725 | 0 | 0 | INFRA
Base | INFRA-STORE | 14 | 2027-12-01 | 9.95 | 0.1545 | 1.5373 | 0 | 0 | INFRA
Base | INFRA-STORE | 15 | 2028-01-01 | 14.8505 | 0.1545 | 2.2944 | 0 | 0 | INFRA
Base | INFRA-STORE | 16 | 2028-02-01 | 19.702 | 0.1545 | 3.044 | 0 | 0 | INFRA
Base | INFRA-STORE | 17 | 2028-03-01 | 24.505 | 0.1545 | 3.786 | 0 | 0 | INFRA
Base | INFRA-STORE | 18 | 2028-04-01 | 29.2599 | 0.1545 | 4.5207 | 0 | 0 | INFRA
Base | INFRA-STORE | 19 | 2028-05-01 | 33.9673 | 0.1545 | 5.248 | 0 | 0 | INFRA
Base | INFRA-STORE | 20 | 2028-06-01 | 38.6277 | 0.1545 | 5.968 | 0 | 0 | INFRA
Base | INFRA-STORE | 21 | 2028-07-01 | 43.2414 | 0.1545 | 6.6808 | 0 | 0 | INFRA
Base | INFRA-STORE | 22 | 2028-08-01 | 47.809 | 0.1545 | 7.3865 | 0 | 0 | INFRA
Base | INFRA-STORE | 23 | 2028-09-01 | 52.3309 | 0.1545 | 8.0851 | 0 | 0 | INFRA
Base | INFRA-STORE | 24 | 2028-10-01 | 56.8076 | 0.1545 | 8.7768 | 0 | 0 | INFRA
Base | INFRA-STORE | 25 | 2028-11-01 | 63.7395 | 0.15913 | 10.1432 | 0 | 0 | INFRA
Base | INFRA-STORE | 26 | 2028-12-01 | 70.6021 | 0.15913 | 11.2353 | 0 | 0 | INFRA
Base | INFRA-STORE | 27 | 2029-01-01 | 77.3961 | 0.15913 | 12.3164 | 0 | 0 | INFRA
Base | INFRA-STORE | 28 | 2029-02-01 | 84.1221 | 0.15913 | 13.3868 | 0 | 0 | INFRA
Base | INFRA-STORE | 29 | 2029-03-01 | 90.7809 | 0.15913 | 14.4464 | 0 | 0 | INFRA
Base | INFRA-STORE | 30 | 2029-04-01 | 97.3731 | 0.15913 | 15.4955 | 0 | 0 | INFRA
Base | INFRA-STORE | 31 | 2029-05-01 | 103.8994 | 0.15913 | 16.534 | 0 | 0 | INFRA
Base | INFRA-STORE | 32 | 2029-06-01 | 110.3604 | 0.15913 | 17.5622 | 0 | 0 | INFRA
Base | INFRA-STORE | 33 | 2029-07-01 | 116.7568 | 0.15913 | 18.5801 | 0 | 0 | INFRA
Base | INFRA-STORE | 34 | 2029-08-01 | 123.0892 | 0.15913 | 19.5878 | 0 | 0 | INFRA
Base | INFRA-STORE | 35 | 2029-09-01 | 129.3583 | 0.15913 | 20.5854 | 0 | 0 | INFRA
Base | INFRA-STORE | 36 | 2029-10-01 | 135.5647 | 0.15913 | 21.5731 | 0 | 0 | INFRA
Base | INFRA-STORE | 37 | 2029-11-01 | 145.4591 | 0.16391 | 23.8421 | 0 | 0 | INFRA
Base | INFRA-STORE | 38 | 2029-12-01 | 155.2545 | 0.16391 | 25.4476 | 0 | 0 | INFRA
Base | INFRA-STORE | 39 | 2030-01-01 | 164.9519 | 0.16391 | 27.0371 | 0 | 0 | INFRA
Base | INFRA-STORE | 40 | 2030-02-01 | 174.5524 | 0.16391 | 28.6107 | 0 | 0 | INFRA
Base | INFRA-STORE | 41 | 2030-03-01 | 184.0569 | 0.16391 | 30.1686 | 0 | 0 | INFRA
Base | INFRA-STORE | 42 | 2030-04-01 | 193.4663 | 0.16391 | 31.7109 | 0 | 0 | INFRA
Base | INFRA-STORE | 43 | 2030-05-01 | 202.7817 | 0.16391 | 33.2377 | 0 | 0 | INFRA
Base | INFRA-STORE | 44 | 2030-06-01 | 212.0038 | 0.16391 | 34.7493 | 0 | 0 | INFRA
Base | INFRA-STORE | 45 | 2030-07-01 | 221.1338 | 0.16391 | 36.2458 | 0 | 0 | INFRA
Base | INFRA-STORE | 46 | 2030-08-01 | 230.1725 | 0.16391 | 37.7273 | 0 | 0 | INFRA
Base | INFRA-STORE | 47 | 2030-09-01 | 239.1207 | 0.16391 | 39.1941 | 0 | 0 | INFRA
Base | INFRA-STORE | 48 | 2030-10-01 | 247.9795 | 0.16391 | 40.6461 | 0 | 0 | INFRA
Base | INFRA-STORE | 49 | 2030-11-01 | 262.3747 | 0.16883 | 44.2958 | 0 | 0 | INFRA
Base | INFRA-STORE | 50 | 2030-12-01 | 276.626 | 0.16883 | 46.7017 | 0 | 0 | INFRA
Base | INFRA-STORE | 51 | 2031-01-01 | 290.7347 | 0.16883 | 49.0837 | 0 | 0 | INFRA
Base | INFRA-STORE | 52 | 2031-02-01 | 304.7024 | 0.16883 | 51.4418 | 0 | 0 | INFRA
Base | INFRA-STORE | 53 | 2031-03-01 | 318.5304 | 0.16883 | 53.7763 | 0 | 0 | INFRA
Base | INFRA-STORE | 54 | 2031-04-01 | 332.2201 | 0.16883 | 56.0875 | 0 | 0 | INFRA
Base | INFRA-STORE | 55 | 2031-05-01 | 345.7729 | 0.16883 | 58.3756 | 0 | 0 | INFRA
Base | INFRA-STORE | 56 | 2031-06-01 | 359.1901 | 0.16883 | 60.6407 | 0 | 0 | INFRA
Base | INFRA-STORE | 57 | 2031-07-01 | 372.4732 | 0.16883 | 62.8833 | 0 | 0 | INFRA
Base | INFRA-STORE | 58 | 2031-08-01 | 385.6235 | 0.16883 | 65.1034 | 0 | 0 | INFRA
Base | INFRA-STORE | 59 | 2031-09-01 | 398.6423 | 0.16883 | 67.3013 | 0 | 0 | INFRA
Base | INFRA-STORE | 60 | 2031-10-01 | 411.5308 | 0.16883 | 69.4772 | 0 | 0 | INFRA
Base | INFRA-LOG | 1 | 2026-11-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 2 | 2026-12-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 3 | 2027-01-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 4 | 2027-02-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 5 | 2027-03-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 6 | 2027-04-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 7 | 2027-05-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 8 | 2027-06-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 9 | 2027-07-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 10 | 2027-08-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 11 | 2027-09-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 12 | 2027-10-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Base | INFRA-LOG | 13 | 2027-11-01 | 1 | 5.15 | 5.15 | 0 | 0 | INFRA
Base | INFRA-LOG | 14 | 2027-12-01 | 1.99 | 5.15 | 10.2485 | 0 | 0 | INFRA
Base | INFRA-LOG | 15 | 2028-01-01 | 2.9701 | 5.15 | 15.296 | 0 | 0 | INFRA
Base | INFRA-LOG | 16 | 2028-02-01 | 3.9404 | 5.15 | 20.2931 | 0 | 0 | INFRA
Base | INFRA-LOG | 17 | 2028-03-01 | 4.901 | 5.15 | 25.2401 | 0 | 0 | INFRA
Base | INFRA-LOG | 18 | 2028-04-01 | 5.852 | 5.15 | 30.1377 | 0 | 0 | INFRA
Base | INFRA-LOG | 19 | 2028-05-01 | 6.7935 | 5.15 | 34.9863 | 0 | 0 | INFRA
Base | INFRA-LOG | 20 | 2028-06-01 | 7.7255 | 5.15 | 39.7865 | 0 | 0 | INFRA
Base | INFRA-LOG | 21 | 2028-07-01 | 8.6483 | 5.15 | 44.5386 | 0 | 0 | INFRA
Base | INFRA-LOG | 22 | 2028-08-01 | 9.5618 | 5.15 | 49.2432 | 0 | 0 | INFRA
Base | INFRA-LOG | 23 | 2028-09-01 | 10.4662 | 5.15 | 53.9008 | 0 | 0 | INFRA
Base | INFRA-LOG | 24 | 2028-10-01 | 11.3615 | 5.15 | 58.5118 | 0 | 0 | INFRA
Base | INFRA-LOG | 25 | 2028-11-01 | 12.7479 | 5.3045 | 67.6212 | 0 | 0 | INFRA
Base | INFRA-LOG | 26 | 2028-12-01 | 14.1204 | 5.3045 | 74.9018 | 0 | 0 | INFRA
Base | INFRA-LOG | 27 | 2029-01-01 | 15.4792 | 5.3045 | 82.1095 | 0 | 0 | INFRA
Base | INFRA-LOG | 28 | 2029-02-01 | 16.8244 | 5.3045 | 89.2451 | 0 | 0 | INFRA
Base | INFRA-LOG | 29 | 2029-03-01 | 18.1562 | 5.3045 | 96.3094 | 0 | 0 | INFRA
Base | INFRA-LOG | 30 | 2029-04-01 | 19.4746 | 5.3045 | 103.3031 | 0 | 0 | INFRA
Base | INFRA-LOG | 31 | 2029-05-01 | 20.7799 | 5.3045 | 110.2268 | 0 | 0 | INFRA
Base | INFRA-LOG | 32 | 2029-06-01 | 22.0721 | 5.3045 | 117.0813 | 0 | 0 | INFRA
Base | INFRA-LOG | 33 | 2029-07-01 | 23.3514 | 5.3045 | 123.8672 | 0 | 0 | INFRA
Base | INFRA-LOG | 34 | 2029-08-01 | 24.6178 | 5.3045 | 130.5853 | 0 | 0 | INFRA
Base | INFRA-LOG | 35 | 2029-09-01 | 25.8717 | 5.3045 | 137.2362 | 0 | 0 | INFRA
Base | INFRA-LOG | 36 | 2029-10-01 | 27.1129 | 5.3045 | 143.8206 | 0 | 0 | INFRA
Base | INFRA-LOG | 37 | 2029-11-01 | 29.0918 | 5.4636 | 158.947 | 0 | 0 | INFRA
Base | INFRA-LOG | 38 | 2029-12-01 | 31.0509 | 5.4636 | 169.6508 | 0 | 0 | INFRA
Base | INFRA-LOG | 39 | 2030-01-01 | 32.9904 | 5.4636 | 180.2474 | 0 | 0 | INFRA
Base | INFRA-LOG | 40 | 2030-02-01 | 34.9105 | 5.4636 | 190.7381 | 0 | 0 | INFRA
Base | INFRA-LOG | 41 | 2030-03-01 | 36.8114 | 5.4636 | 201.1239 | 0 | 0 | INFRA
Base | INFRA-LOG | 42 | 2030-04-01 | 38.6933 | 5.4636 | 211.4059 | 0 | 0 | INFRA
Base | INFRA-LOG | 43 | 2030-05-01 | 40.5563 | 5.4636 | 221.585 | 0 | 0 | INFRA
Base | INFRA-LOG | 44 | 2030-06-01 | 42.4008 | 5.4636 | 231.6623 | 0 | 0 | INFRA
Base | INFRA-LOG | 45 | 2030-07-01 | 44.2268 | 5.4636 | 241.6389 | 0 | 0 | INFRA
Base | INFRA-LOG | 46 | 2030-08-01 | 46.0345 | 5.4636 | 251.5157 | 0 | 0 | INFRA
Base | INFRA-LOG | 47 | 2030-09-01 | 47.8241 | 5.4636 | 261.2937 | 0 | 0 | INFRA
Base | INFRA-LOG | 48 | 2030-10-01 | 49.5959 | 5.4636 | 270.9739 | 0 | 0 | INFRA
Base | INFRA-LOG | 49 | 2030-11-01 | 52.4749 | 5.6275 | 295.3051 | 0 | 0 | INFRA
Base | INFRA-LOG | 50 | 2030-12-01 | 55.3252 | 5.6275 | 311.345 | 0 | 0 | INFRA
Base | INFRA-LOG | 51 | 2031-01-01 | 58.1469 | 5.6275 | 327.2245 | 0 | 0 | INFRA
Base | INFRA-LOG | 52 | 2031-02-01 | 60.9405 | 5.6275 | 342.9452 | 0 | 0 | INFRA
Base | INFRA-LOG | 53 | 2031-03-01 | 63.7061 | 5.6275 | 358.5087 | 0 | 0 | INFRA
Base | INFRA-LOG | 54 | 2031-04-01 | 66.444 | 5.6275 | 373.9166 | 0 | 0 | INFRA
Base | INFRA-LOG | 55 | 2031-05-01 | 69.1546 | 5.6275 | 389.1704 | 0 | 0 | INFRA
Base | INFRA-LOG | 56 | 2031-06-01 | 71.838 | 5.6275 | 404.2716 | 0 | 0 | INFRA
Base | INFRA-LOG | 57 | 2031-07-01 | 74.4946 | 5.6275 | 419.2219 | 0 | 0 | INFRA
Base | INFRA-LOG | 58 | 2031-08-01 | 77.1247 | 5.6275 | 434.0226 | 0 | 0 | INFRA
Base | INFRA-LOG | 59 | 2031-09-01 | 79.7285 | 5.6275 | 448.6754 | 0 | 0 | INFRA
Base | INFRA-LOG | 60 | 2031-10-01 | 82.3062 | 5.6275 | 463.1816 | 0 | 0 | INFRA
Base | INFRA-REQ | 1 | 2026-11-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 2 | 2026-12-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 3 | 2027-01-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 4 | 2027-02-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 5 | 2027-03-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 6 | 2027-04-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 7 | 2027-05-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 8 | 2027-06-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 9 | 2027-07-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 10 | 2027-08-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 11 | 2027-09-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 12 | 2027-10-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Base | INFRA-REQ | 13 | 2027-11-01 | 0.0675 | 30.9 | 2.0857 | 0 | 0 | INFRA
Base | INFRA-REQ | 14 | 2027-12-01 | 0.13432 | 30.9 | 4.1506 | 0 | 0 | INFRA
Base | INFRA-REQ | 15 | 2028-01-01 | 0.20048 | 30.9 | 6.1949 | 0 | 0 | INFRA
Base | INFRA-REQ | 16 | 2028-02-01 | 0.26598 | 30.9 | 8.2187 | 0 | 0 | INFRA
Base | INFRA-REQ | 17 | 2028-03-01 | 0.33082 | 30.9 | 10.2223 | 0 | 0 | INFRA
Base | INFRA-REQ | 18 | 2028-04-01 | 0.39501 | 30.9 | 12.2058 | 0 | 0 | INFRA
Base | INFRA-REQ | 19 | 2028-05-01 | 0.45856 | 30.9 | 14.1695 | 0 | 0 | INFRA
Base | INFRA-REQ | 20 | 2028-06-01 | 0.52147 | 30.9 | 16.1135 | 0 | 0 | INFRA
Base | INFRA-REQ | 21 | 2028-07-01 | 0.58376 | 30.9 | 18.0381 | 0 | 0 | INFRA
Base | INFRA-REQ | 22 | 2028-08-01 | 0.64542 | 30.9 | 19.9435 | 0 | 0 | INFRA
Base | INFRA-REQ | 23 | 2028-09-01 | 0.70647 | 30.9 | 21.8298 | 0 | 0 | INFRA
Base | INFRA-REQ | 24 | 2028-10-01 | 0.7669 | 30.9 | 23.6973 | 0 | 0 | INFRA
Base | INFRA-REQ | 25 | 2028-11-01 | 0.86048 | 31.827 | 27.3866 | 0 | 0 | INFRA
Base | INFRA-REQ | 26 | 2028-12-01 | 0.95313 | 31.827 | 30.3352 | 0 | 0 | INFRA
Base | INFRA-REQ | 27 | 2029-01-01 | 1.0448 | 31.827 | 33.2543 | 0 | 0 | INFRA
Base | INFRA-REQ | 28 | 2029-02-01 | 1.1356 | 31.827 | 36.1443 | 0 | 0 | INFRA
Base | INFRA-REQ | 29 | 2029-03-01 | 1.2255 | 31.827 | 39.0053 | 0 | 0 | INFRA
Base | INFRA-REQ | 30 | 2029-04-01 | 1.3145 | 31.827 | 41.8378 | 0 | 0 | INFRA
Base | INFRA-REQ | 31 | 2029-05-01 | 1.4026 | 31.827 | 44.6419 | 0 | 0 | INFRA
Base | INFRA-REQ | 32 | 2029-06-01 | 1.4899 | 31.827 | 47.4179 | 0 | 0 | INFRA
Base | INFRA-REQ | 33 | 2029-07-01 | 1.5762 | 31.827 | 50.1662 | 0 | 0 | INFRA
Base | INFRA-REQ | 34 | 2029-08-01 | 1.6617 | 31.827 | 52.8871 | 0 | 0 | INFRA
Base | INFRA-REQ | 35 | 2029-09-01 | 1.7463 | 31.827 | 55.5807 | 0 | 0 | INFRA
Base | INFRA-REQ | 36 | 2029-10-01 | 1.8301 | 31.827 | 58.2473 | 0 | 0 | INFRA
Base | INFRA-REQ | 37 | 2029-11-01 | 1.9637 | 32.7818 | 64.3736 | 0 | 0 | INFRA
Base | INFRA-REQ | 38 | 2029-12-01 | 2.0959 | 32.7818 | 68.7086 | 0 | 0 | INFRA
Base | INFRA-REQ | 39 | 2030-01-01 | 2.2269 | 32.7818 | 73.0002 | 0 | 0 | INFRA
Base | INFRA-REQ | 40 | 2030-02-01 | 2.3565 | 32.7818 | 77.2489 | 0 | 0 | INFRA
Base | INFRA-REQ | 41 | 2030-03-01 | 2.4848 | 32.7818 | 81.4552 | 0 | 0 | INFRA
Base | INFRA-REQ | 42 | 2030-04-01 | 2.6118 | 32.7818 | 85.6194 | 0 | 0 | INFRA
Base | INFRA-REQ | 43 | 2030-05-01 | 2.7376 | 32.7818 | 89.7419 | 0 | 0 | INFRA
Base | INFRA-REQ | 44 | 2030-06-01 | 2.8621 | 32.7818 | 93.8232 | 0 | 0 | INFRA
Base | INFRA-REQ | 45 | 2030-07-01 | 2.9853 | 32.7818 | 97.8637 | 0 | 0 | INFRA
Base | INFRA-REQ | 46 | 2030-08-01 | 3.1073 | 32.7818 | 101.8638 | 0 | 0 | INFRA
Base | INFRA-REQ | 47 | 2030-09-01 | 3.2281 | 32.7818 | 105.8239 | 0 | 0 | INFRA
Base | INFRA-REQ | 48 | 2030-10-01 | 3.3477 | 32.7818 | 109.7444 | 0 | 0 | INFRA
Base | INFRA-REQ | 49 | 2030-11-01 | 3.5421 | 33.7653 | 119.5986 | 0 | 0 | INFRA
Base | INFRA-REQ | 50 | 2030-12-01 | 3.7345 | 33.7653 | 126.0947 | 0 | 0 | INFRA
Base | INFRA-REQ | 51 | 2031-01-01 | 3.9249 | 33.7653 | 132.5259 | 0 | 0 | INFRA
Base | INFRA-REQ | 52 | 2031-02-01 | 4.1135 | 33.7653 | 138.8928 | 0 | 0 | INFRA
Base | INFRA-REQ | 53 | 2031-03-01 | 4.3002 | 33.7653 | 145.196 | 0 | 0 | INFRA
Base | INFRA-REQ | 54 | 2031-04-01 | 4.485 | 33.7653 | 151.4362 | 0 | 0 | INFRA
Base | INFRA-REQ | 55 | 2031-05-01 | 4.6679 | 33.7653 | 157.614 | 0 | 0 | INFRA
Base | INFRA-REQ | 56 | 2031-06-01 | 4.8491 | 33.7653 | 163.73 | 0 | 0 | INFRA
Base | INFRA-REQ | 57 | 2031-07-01 | 5.0284 | 33.7653 | 169.7849 | 0 | 0 | INFRA
Base | INFRA-REQ | 58 | 2031-08-01 | 5.2059 | 33.7653 | 175.7792 | 0 | 0 | INFRA
Base | INFRA-REQ | 59 | 2031-09-01 | 5.3817 | 33.7653 | 181.7135 | 0 | 0 | INFRA
Base | INFRA-REQ | 60 | 2031-10-01 | 5.5557 | 33.7653 | 187.5885 | 0 | 0 | INFRA
Base | TOOLS-GH | 1 | 2026-11-01 | 2 | 4 | 8 | 0 | 0 | TOOLS
Base | TOOLS-GH | 2 | 2026-12-01 | 3 | 4 | 12 | 0 | 0 | TOOLS
Base | TOOLS-GH | 3 | 2027-01-01 | 4 | 4 | 16 | 0 | 0 | TOOLS
Base | TOOLS-GH | 4 | 2027-02-01 | 5 | 4 | 20 | 0 | 0 | TOOLS
Base | TOOLS-GH | 5 | 2027-03-01 | 5 | 4 | 20 | 0 | 0 | TOOLS
Base | TOOLS-GH | 6 | 2027-04-01 | 5 | 4 | 20 | 0 | 0 | TOOLS
Base | TOOLS-GH | 7 | 2027-05-01 | 6 | 4 | 24 | 0 | 0 | TOOLS
Base | TOOLS-GH | 8 | 2027-06-01 | 6 | 4 | 24 | 0 | 0 | TOOLS
Base | TOOLS-GH | 9 | 2027-07-01 | 6 | 4 | 24 | 0 | 0 | TOOLS
Base | TOOLS-GH | 10 | 2027-08-01 | 7 | 4 | 28 | 0 | 0 | TOOLS
Base | TOOLS-GH | 11 | 2027-09-01 | 7 | 4 | 28 | 0 | 0 | TOOLS
Base | TOOLS-GH | 12 | 2027-10-01 | 7 | 4 | 28 | 0 | 0 | TOOLS
Base | TOOLS-GH | 13 | 2027-11-01 | 7 | 4.12 | 28.84 | 0 | 0 | TOOLS
Base | TOOLS-GH | 14 | 2027-12-01 | 7 | 4.12 | 28.84 | 0 | 0 | TOOLS
Base | TOOLS-GH | 15 | 2028-01-01 | 7 | 4.12 | 28.84 | 0 | 0 | TOOLS
Base | TOOLS-GH | 16 | 2028-02-01 | 9 | 4.12 | 37.08 | 0 | 0 | TOOLS
Base | TOOLS-GH | 17 | 2028-03-01 | 9 | 4.12 | 37.08 | 0 | 0 | TOOLS
Base | TOOLS-GH | 18 | 2028-04-01 | 9 | 4.12 | 37.08 | 0 | 0 | TOOLS
Base | TOOLS-GH | 19 | 2028-05-01 | 9 | 4.12 | 37.08 | 0 | 0 | TOOLS
Base | TOOLS-GH | 20 | 2028-06-01 | 9 | 4.12 | 37.08 | 0 | 0 | TOOLS
Base | TOOLS-GH | 21 | 2028-07-01 | 9 | 4.12 | 37.08 | 0 | 0 | TOOLS
Base | TOOLS-GH | 22 | 2028-08-01 | 9 | 4.12 | 37.08 | 0 | 0 | TOOLS
Base | TOOLS-GH | 23 | 2028-09-01 | 9 | 4.12 | 37.08 | 0 | 0 | TOOLS
Base | TOOLS-GH | 24 | 2028-10-01 | 9 | 4.12 | 37.08 | 0 | 0 | TOOLS
Base | TOOLS-GH | 25 | 2028-11-01 | 9 | 4.2436 | 38.1924 | 0 | 0 | TOOLS
Base | TOOLS-GH | 26 | 2028-12-01 | 9 | 4.2436 | 38.1924 | 0 | 0 | TOOLS
Base | TOOLS-GH | 27 | 2029-01-01 | 9 | 4.2436 | 38.1924 | 0 | 0 | TOOLS
Base | TOOLS-GH | 28 | 2029-02-01 | 9 | 4.2436 | 38.1924 | 0 | 0 | TOOLS
Base | TOOLS-GH | 29 | 2029-03-01 | 9 | 4.2436 | 38.1924 | 0 | 0 | TOOLS
Base | TOOLS-GH | 30 | 2029-04-01 | 9 | 4.2436 | 38.1924 | 0 | 0 | TOOLS
Base | TOOLS-GH | 31 | 2029-05-01 | 13 | 4.2436 | 55.1668 | 0 | 0 | TOOLS
Base | TOOLS-GH | 32 | 2029-06-01 | 13 | 4.2436 | 55.1668 | 0 | 0 | TOOLS
Base | TOOLS-GH | 33 | 2029-07-01 | 13 | 4.2436 | 55.1668 | 0 | 0 | TOOLS
Base | TOOLS-GH | 34 | 2029-08-01 | 13 | 4.2436 | 55.1668 | 0 | 0 | TOOLS
Base | TOOLS-GH | 35 | 2029-09-01 | 13 | 4.2436 | 55.1668 | 0 | 0 | TOOLS
Base | TOOLS-GH | 36 | 2029-10-01 | 13 | 4.2436 | 55.1668 | 0 | 0 | TOOLS
Base | TOOLS-GH | 37 | 2029-11-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 38 | 2029-12-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 39 | 2030-01-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 40 | 2030-02-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 41 | 2030-03-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 42 | 2030-04-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 43 | 2030-05-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 44 | 2030-06-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 45 | 2030-07-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 46 | 2030-08-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 47 | 2030-09-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 48 | 2030-10-01 | 13 | 4.3709 | 56.8218 | 0 | 0 | TOOLS
Base | TOOLS-GH | 49 | 2030-11-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 50 | 2030-12-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 51 | 2031-01-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 52 | 2031-02-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 53 | 2031-03-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 54 | 2031-04-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 55 | 2031-05-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 56 | 2031-06-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 57 | 2031-07-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 58 | 2031-08-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 59 | 2031-09-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-GH | 60 | 2031-10-01 | 13 | 4.502 | 58.5265 | 0 | 0 | TOOLS
Base | TOOLS-CI | 1 | 2026-11-01 | 2 | 45 | 90 | 0 | 0 | TOOLS
Base | TOOLS-CI | 2 | 2026-12-01 | 3 | 45 | 135 | 0 | 0 | TOOLS
Base | TOOLS-CI | 3 | 2027-01-01 | 4 | 45 | 180 | 0 | 0 | TOOLS
Base | TOOLS-CI | 4 | 2027-02-01 | 5 | 45 | 225 | 0 | 0 | TOOLS
Base | TOOLS-CI | 5 | 2027-03-01 | 5 | 45 | 225 | 0 | 0 | TOOLS
Base | TOOLS-CI | 6 | 2027-04-01 | 5 | 45 | 225 | 0 | 0 | TOOLS
Base | TOOLS-CI | 7 | 2027-05-01 | 6 | 45 | 270 | 0 | 0 | TOOLS
Base | TOOLS-CI | 8 | 2027-06-01 | 6 | 45 | 270 | 0 | 0 | TOOLS
Base | TOOLS-CI | 9 | 2027-07-01 | 6 | 45 | 270 | 0 | 0 | TOOLS
Base | TOOLS-CI | 10 | 2027-08-01 | 7 | 45 | 315 | 0 | 0 | TOOLS
Base | TOOLS-CI | 11 | 2027-09-01 | 7 | 45 | 315 | 0 | 0 | TOOLS
Base | TOOLS-CI | 12 | 2027-10-01 | 7 | 45 | 315 | 0 | 0 | TOOLS
Base | TOOLS-CI | 13 | 2027-11-01 | 7 | 46.35 | 324.45 | 0 | 0 | TOOLS
Base | TOOLS-CI | 14 | 2027-12-01 | 7 | 46.35 | 324.45 | 0 | 0 | TOOLS
Base | TOOLS-CI | 15 | 2028-01-01 | 7 | 46.35 | 324.45 | 0 | 0 | TOOLS
Base | TOOLS-CI | 16 | 2028-02-01 | 9 | 46.35 | 417.15 | 0 | 0 | TOOLS
Base | TOOLS-CI | 17 | 2028-03-01 | 9 | 46.35 | 417.15 | 0 | 0 | TOOLS
Base | TOOLS-CI | 18 | 2028-04-01 | 9 | 46.35 | 417.15 | 0 | 0 | TOOLS
Base | TOOLS-CI | 19 | 2028-05-01 | 9 | 46.35 | 417.15 | 0 | 0 | TOOLS
Base | TOOLS-CI | 20 | 2028-06-01 | 9 | 46.35 | 417.15 | 0 | 0 | TOOLS
Base | TOOLS-CI | 21 | 2028-07-01 | 9 | 46.35 | 417.15 | 0 | 0 | TOOLS
Base | TOOLS-CI | 22 | 2028-08-01 | 9 | 46.35 | 417.15 | 0 | 0 | TOOLS
Base | TOOLS-CI | 23 | 2028-09-01 | 9 | 46.35 | 417.15 | 0 | 0 | TOOLS
Base | TOOLS-CI | 24 | 2028-10-01 | 9 | 46.35 | 417.15 | 0 | 0 | TOOLS
Base | TOOLS-CI | 25 | 2028-11-01 | 9 | 47.7405 | 429.6645 | 0 | 0 | TOOLS
Base | TOOLS-CI | 26 | 2028-12-01 | 9 | 47.7405 | 429.6645 | 0 | 0 | TOOLS
Base | TOOLS-CI | 27 | 2029-01-01 | 9 | 47.7405 | 429.6645 | 0 | 0 | TOOLS
Base | TOOLS-CI | 28 | 2029-02-01 | 9 | 47.7405 | 429.6645 | 0 | 0 | TOOLS
Base | TOOLS-CI | 29 | 2029-03-01 | 9 | 47.7405 | 429.6645 | 0 | 0 | TOOLS
Base | TOOLS-CI | 30 | 2029-04-01 | 9 | 47.7405 | 429.6645 | 0 | 0 | TOOLS
Base | TOOLS-CI | 31 | 2029-05-01 | 13 | 47.7405 | 620.6265 | 0 | 0 | TOOLS
Base | TOOLS-CI | 32 | 2029-06-01 | 13 | 47.7405 | 620.6265 | 0 | 0 | TOOLS
Base | TOOLS-CI | 33 | 2029-07-01 | 13 | 47.7405 | 620.6265 | 0 | 0 | TOOLS
Base | TOOLS-CI | 34 | 2029-08-01 | 13 | 47.7405 | 620.6265 | 0 | 0 | TOOLS
Base | TOOLS-CI | 35 | 2029-09-01 | 13 | 47.7405 | 620.6265 | 0 | 0 | TOOLS
Base | TOOLS-CI | 36 | 2029-10-01 | 13 | 47.7405 | 620.6265 | 0 | 0 | TOOLS
Base | TOOLS-CI | 37 | 2029-11-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 38 | 2029-12-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 39 | 2030-01-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 40 | 2030-02-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 41 | 2030-03-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 42 | 2030-04-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 43 | 2030-05-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 44 | 2030-06-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 45 | 2030-07-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 46 | 2030-08-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 47 | 2030-09-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 48 | 2030-10-01 | 13 | 49.1727 | 639.2453 | 0 | 0 | TOOLS
Base | TOOLS-CI | 49 | 2030-11-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 50 | 2030-12-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 51 | 2031-01-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 52 | 2031-02-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 53 | 2031-03-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 54 | 2031-04-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 55 | 2031-05-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 56 | 2031-06-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 57 | 2031-07-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 58 | 2031-08-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 59 | 2031-09-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | TOOLS-CI | 60 | 2031-10-01 | 13 | 50.6479 | 658.4227 | 0 | 0 | TOOLS
Base | LEGAL-SETUP | 1 | 2026-11-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 2 | 2026-12-01 | 1 | 20000 | 20000 | 20000 | 0 | LEGAL
Base | LEGAL-SETUP | 3 | 2027-01-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 4 | 2027-02-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 5 | 2027-03-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 6 | 2027-04-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 7 | 2027-05-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 8 | 2027-06-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 9 | 2027-07-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 10 | 2027-08-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 11 | 2027-09-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 12 | 2027-10-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 13 | 2027-11-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 14 | 2027-12-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 15 | 2028-01-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 16 | 2028-02-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 17 | 2028-03-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 18 | 2028-04-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 19 | 2028-05-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 20 | 2028-06-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 21 | 2028-07-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 22 | 2028-08-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 23 | 2028-09-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 24 | 2028-10-01 | 0 | 20600 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 25 | 2028-11-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 26 | 2028-12-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 27 | 2029-01-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 28 | 2029-02-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 29 | 2029-03-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 30 | 2029-04-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 31 | 2029-05-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 32 | 2029-06-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 33 | 2029-07-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 34 | 2029-08-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 35 | 2029-09-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 36 | 2029-10-01 | 0 | 21218 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 37 | 2029-11-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 38 | 2029-12-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 39 | 2030-01-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 40 | 2030-02-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 41 | 2030-03-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 42 | 2030-04-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 43 | 2030-05-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 44 | 2030-06-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 45 | 2030-07-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 46 | 2030-08-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 47 | 2030-09-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 48 | 2030-10-01 | 0 | 21854.54 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 49 | 2030-11-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 50 | 2030-12-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 51 | 2031-01-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 52 | 2031-02-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 53 | 2031-03-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 54 | 2031-04-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 55 | 2031-05-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 56 | 2031-06-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 57 | 2031-07-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 58 | 2031-08-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 59 | 2031-09-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-SETUP | 60 | 2031-10-01 | 0 | 22510.1762 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 1 | 2026-11-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 2 | 2026-12-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 3 | 2027-01-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 4 | 2027-02-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 5 | 2027-03-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 6 | 2027-04-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 7 | 2027-05-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 8 | 2027-06-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 9 | 2027-07-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 10 | 2027-08-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 11 | 2027-09-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 12 | 2027-10-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 13 | 2027-11-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 14 | 2027-12-01 | 1 | 12360 | 12360 | 12360 | 0 | LEGAL
Base | LEGAL-RENEW | 15 | 2028-01-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 16 | 2028-02-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 17 | 2028-03-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 18 | 2028-04-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 19 | 2028-05-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 20 | 2028-06-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 21 | 2028-07-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 22 | 2028-08-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 23 | 2028-09-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 24 | 2028-10-01 | 0 | 12360 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 25 | 2028-11-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 26 | 2028-12-01 | 1 | 12730.8 | 12730.8 | 12730.8 | 0 | LEGAL
Base | LEGAL-RENEW | 27 | 2029-01-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 28 | 2029-02-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 29 | 2029-03-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 30 | 2029-04-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 31 | 2029-05-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 32 | 2029-06-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 33 | 2029-07-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 34 | 2029-08-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 35 | 2029-09-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 36 | 2029-10-01 | 0 | 12730.8 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 37 | 2029-11-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 38 | 2029-12-01 | 1 | 13112.724 | 13112.724 | 13112.724 | 0 | LEGAL
Base | LEGAL-RENEW | 39 | 2030-01-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 40 | 2030-02-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 41 | 2030-03-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 42 | 2030-04-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 43 | 2030-05-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 44 | 2030-06-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 45 | 2030-07-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 46 | 2030-08-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 47 | 2030-09-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 48 | 2030-10-01 | 0 | 13112.724 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 49 | 2030-11-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 50 | 2030-12-01 | 1 | 13506.1057 | 13506.1057 | 13506.1057 | 0 | LEGAL
Base | LEGAL-RENEW | 51 | 2031-01-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 52 | 2031-02-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 53 | 2031-03-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 54 | 2031-04-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 55 | 2031-05-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 56 | 2031-06-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 57 | 2031-07-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 58 | 2031-08-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 59 | 2031-09-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | LEGAL-RENEW | 60 | 2031-10-01 | 0 | 13506.1057 | 0 | 0 | 0 | LEGAL
Base | SECURITY-TEST | 1 | 2026-11-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 2 | 2026-12-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 3 | 2027-01-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 4 | 2027-02-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 5 | 2027-03-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 6 | 2027-04-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 7 | 2027-05-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 8 | 2027-06-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 9 | 2027-07-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 10 | 2027-08-01 | 1 | 18000 | 18000 | 18000 | 0 | SECURITY
Base | SECURITY-TEST | 11 | 2027-09-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 12 | 2027-10-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 13 | 2027-11-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 14 | 2027-12-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 15 | 2028-01-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 16 | 2028-02-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 17 | 2028-03-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 18 | 2028-04-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 19 | 2028-05-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 20 | 2028-06-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 21 | 2028-07-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 22 | 2028-08-01 | 1 | 18540 | 18540 | 18540 | 0 | SECURITY
Base | SECURITY-TEST | 23 | 2028-09-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 24 | 2028-10-01 | 0 | 18540 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 25 | 2028-11-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 26 | 2028-12-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 27 | 2029-01-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 28 | 2029-02-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 29 | 2029-03-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 30 | 2029-04-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 31 | 2029-05-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 32 | 2029-06-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 33 | 2029-07-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 34 | 2029-08-01 | 1 | 19096.2 | 19096.2 | 19096.2 | 0 | SECURITY
Base | SECURITY-TEST | 35 | 2029-09-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 36 | 2029-10-01 | 0 | 19096.2 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 37 | 2029-11-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 38 | 2029-12-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 39 | 2030-01-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 40 | 2030-02-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 41 | 2030-03-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 42 | 2030-04-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 43 | 2030-05-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 44 | 2030-06-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 45 | 2030-07-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 46 | 2030-08-01 | 1 | 19669.086 | 19669.086 | 19669.086 | 0 | SECURITY
Base | SECURITY-TEST | 47 | 2030-09-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 48 | 2030-10-01 | 0 | 19669.086 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 49 | 2030-11-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 50 | 2030-12-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 51 | 2031-01-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 52 | 2031-02-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 53 | 2031-03-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 54 | 2031-04-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 55 | 2031-05-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 56 | 2031-06-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 57 | 2031-07-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 58 | 2031-08-01 | 1 | 20259.1586 | 20259.1586 | 20259.1586 | 0 | SECURITY
Base | SECURITY-TEST | 59 | 2031-09-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | SECURITY-TEST | 60 | 2031-10-01 | 0 | 20259.1586 | 0 | 0 | 0 | SECURITY
Base | COMPLIANCE-EXT | 1 | 2026-11-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 2 | 2026-12-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 3 | 2027-01-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 4 | 2027-02-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 5 | 2027-03-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 6 | 2027-04-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 7 | 2027-05-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 8 | 2027-06-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 9 | 2027-07-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 10 | 2027-08-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 11 | 2027-09-01 | 1 | 15000 | 15000 | 15000 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 12 | 2027-10-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 13 | 2027-11-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 14 | 2027-12-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 15 | 2028-01-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 16 | 2028-02-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 17 | 2028-03-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 18 | 2028-04-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 19 | 2028-05-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 20 | 2028-06-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 21 | 2028-07-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 22 | 2028-08-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 23 | 2028-09-01 | 1 | 15450 | 15450 | 15450 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 24 | 2028-10-01 | 0 | 15450 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 25 | 2028-11-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 26 | 2028-12-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 27 | 2029-01-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 28 | 2029-02-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 29 | 2029-03-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 30 | 2029-04-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 31 | 2029-05-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 32 | 2029-06-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 33 | 2029-07-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 34 | 2029-08-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 35 | 2029-09-01 | 1 | 15913.5 | 15913.5 | 15913.5 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 36 | 2029-10-01 | 0 | 15913.5 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 37 | 2029-11-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 38 | 2029-12-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 39 | 2030-01-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 40 | 2030-02-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 41 | 2030-03-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 42 | 2030-04-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 43 | 2030-05-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 44 | 2030-06-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 45 | 2030-07-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 46 | 2030-08-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 47 | 2030-09-01 | 1 | 16390.905 | 16390.905 | 16390.905 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 48 | 2030-10-01 | 0 | 16390.905 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 49 | 2030-11-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 50 | 2030-12-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 51 | 2031-01-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 52 | 2031-02-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 53 | 2031-03-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 54 | 2031-04-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 55 | 2031-05-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 56 | 2031-06-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 57 | 2031-07-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 58 | 2031-08-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 59 | 2031-09-01 | 1 | 16882.6322 | 16882.6322 | 16882.6322 | 0 | COMPLIANCE
Base | COMPLIANCE-EXT | 60 | 2031-10-01 | 0 | 16882.6322 | 0 | 0 | 0 | COMPLIANCE
Base | INSURANCE | 1 | 2026-11-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 2 | 2026-12-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 3 | 2027-01-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 4 | 2027-02-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 5 | 2027-03-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 6 | 2027-04-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 7 | 2027-05-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 8 | 2027-06-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 9 | 2027-07-01 | 1 | 12000 | 12000 | 12000 | 0 | INSURANCE
Base | INSURANCE | 10 | 2027-08-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 11 | 2027-09-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 12 | 2027-10-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 13 | 2027-11-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 14 | 2027-12-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 15 | 2028-01-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 16 | 2028-02-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 17 | 2028-03-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 18 | 2028-04-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 19 | 2028-05-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 20 | 2028-06-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 21 | 2028-07-01 | 1 | 12360 | 12360 | 12360 | 0 | INSURANCE
Base | INSURANCE | 22 | 2028-08-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 23 | 2028-09-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 24 | 2028-10-01 | 0 | 12360 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 25 | 2028-11-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 26 | 2028-12-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 27 | 2029-01-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 28 | 2029-02-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 29 | 2029-03-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 30 | 2029-04-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 31 | 2029-05-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 32 | 2029-06-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 33 | 2029-07-01 | 1 | 12730.8 | 12730.8 | 12730.8 | 0 | INSURANCE
Base | INSURANCE | 34 | 2029-08-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 35 | 2029-09-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 36 | 2029-10-01 | 0 | 12730.8 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 37 | 2029-11-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 38 | 2029-12-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 39 | 2030-01-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 40 | 2030-02-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 41 | 2030-03-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 42 | 2030-04-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 43 | 2030-05-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 44 | 2030-06-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 45 | 2030-07-01 | 1 | 13112.724 | 13112.724 | 13112.724 | 0 | INSURANCE
Base | INSURANCE | 46 | 2030-08-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 47 | 2030-09-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 48 | 2030-10-01 | 0 | 13112.724 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 49 | 2030-11-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 50 | 2030-12-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 51 | 2031-01-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 52 | 2031-02-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 53 | 2031-03-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 54 | 2031-04-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 55 | 2031-05-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 56 | 2031-06-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 57 | 2031-07-01 | 1 | 13506.1057 | 13506.1057 | 13506.1057 | 0 | INSURANCE
Base | INSURANCE | 58 | 2031-08-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 59 | 2031-09-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | INSURANCE | 60 | 2031-10-01 | 0 | 13506.1057 | 0 | 0 | 0 | INSURANCE
Base | ACCOUNTING | 1 | 2026-11-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 2 | 2026-12-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 3 | 2027-01-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 4 | 2027-02-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 5 | 2027-03-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 6 | 2027-04-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 7 | 2027-05-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 8 | 2027-06-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 9 | 2027-07-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 10 | 2027-08-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 11 | 2027-09-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 12 | 2027-10-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Base | ACCOUNTING | 13 | 2027-11-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 14 | 2027-12-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 15 | 2028-01-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 16 | 2028-02-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 17 | 2028-03-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 18 | 2028-04-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 19 | 2028-05-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 20 | 2028-06-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 21 | 2028-07-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 22 | 2028-08-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 23 | 2028-09-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 24 | 2028-10-01 | 1 | 618 | 618 | 618 | 0 | ACCOUNTING
Base | ACCOUNTING | 25 | 2028-11-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 26 | 2028-12-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 27 | 2029-01-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 28 | 2029-02-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 29 | 2029-03-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 30 | 2029-04-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 31 | 2029-05-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 32 | 2029-06-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 33 | 2029-07-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 34 | 2029-08-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 35 | 2029-09-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 36 | 2029-10-01 | 1 | 636.54 | 636.54 | 636.54 | 0 | ACCOUNTING
Base | ACCOUNTING | 37 | 2029-11-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 38 | 2029-12-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 39 | 2030-01-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 40 | 2030-02-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 41 | 2030-03-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 42 | 2030-04-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 43 | 2030-05-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 44 | 2030-06-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 45 | 2030-07-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 46 | 2030-08-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 47 | 2030-09-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 48 | 2030-10-01 | 1 | 655.6362 | 655.6362 | 655.6362 | 0 | ACCOUNTING
Base | ACCOUNTING | 49 | 2030-11-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 50 | 2030-12-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 51 | 2031-01-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 52 | 2031-02-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 53 | 2031-03-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 54 | 2031-04-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 55 | 2031-05-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 56 | 2031-06-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 57 | 2031-07-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 58 | 2031-08-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 59 | 2031-09-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | ACCOUNTING | 60 | 2031-10-01 | 1 | 675.3053 | 675.3053 | 675.3053 | 0 | ACCOUNTING
Base | SUPPORT | 1 | 2026-11-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Base | SUPPORT | 2 | 2026-12-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Base | SUPPORT | 3 | 2027-01-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Base | SUPPORT | 4 | 2027-02-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Base | SUPPORT | 5 | 2027-03-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Base | SUPPORT | 6 | 2027-04-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Base | SUPPORT | 7 | 2027-05-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Base | SUPPORT | 8 | 2027-06-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Base | SUPPORT | 9 | 2027-07-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Base | SUPPORT | 10 | 2027-08-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Base | SUPPORT | 11 | 2027-09-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Base | SUPPORT | 12 | 2027-10-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Base | SUPPORT | 13 | 2027-11-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 14 | 2027-12-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 15 | 2028-01-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 16 | 2028-02-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 17 | 2028-03-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 18 | 2028-04-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 19 | 2028-05-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 20 | 2028-06-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 21 | 2028-07-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 22 | 2028-08-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 23 | 2028-09-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 24 | 2028-10-01 | 1 | 103 | 103 | 0 | 0 | SUPPORT
Base | SUPPORT | 25 | 2028-11-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 26 | 2028-12-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 27 | 2029-01-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 28 | 2029-02-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 29 | 2029-03-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 30 | 2029-04-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 31 | 2029-05-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 32 | 2029-06-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 33 | 2029-07-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 34 | 2029-08-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 35 | 2029-09-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 36 | 2029-10-01 | 1 | 106.09 | 106.09 | 0 | 0 | SUPPORT
Base | SUPPORT | 37 | 2029-11-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 38 | 2029-12-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 39 | 2030-01-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 40 | 2030-02-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 41 | 2030-03-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 42 | 2030-04-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 43 | 2030-05-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 44 | 2030-06-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 45 | 2030-07-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 46 | 2030-08-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 47 | 2030-09-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 48 | 2030-10-01 | 1 | 109.2727 | 109.2727 | 0 | 0 | SUPPORT
Base | SUPPORT | 49 | 2030-11-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 50 | 2030-12-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 51 | 2031-01-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 52 | 2031-02-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 53 | 2031-03-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 54 | 2031-04-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 55 | 2031-05-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 56 | 2031-06-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 57 | 2031-07-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 58 | 2031-08-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 59 | 2031-09-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | SUPPORT | 60 | 2031-10-01 | 1 | 112.5509 | 112.5509 | 0 | 0 | SUPPORT
Base | MARKETING | 1 | 2026-11-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 2 | 2026-12-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 3 | 2027-01-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 4 | 2027-02-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 5 | 2027-03-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 6 | 2027-04-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 7 | 2027-05-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 8 | 2027-06-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 9 | 2027-07-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 10 | 2027-08-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 11 | 2027-09-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 12 | 2027-10-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Base | MARKETING | 13 | 2027-11-01 | 1 | 77.25 | 77.25 | 0 | 0 | MARKETING
Base | MARKETING | 14 | 2027-12-01 | 1.99 | 77.25 | 153.7275 | 0 | 0 | MARKETING
Base | MARKETING | 15 | 2028-01-01 | 2.9701 | 77.25 | 229.4402 | 0 | 0 | MARKETING
Base | MARKETING | 16 | 2028-02-01 | 3.9404 | 77.25 | 304.3958 | 0 | 0 | MARKETING
Base | MARKETING | 17 | 2028-03-01 | 4.901 | 77.25 | 378.6019 | 0 | 0 | MARKETING
Base | MARKETING | 18 | 2028-04-01 | 5.852 | 77.25 | 452.0658 | 0 | 0 | MARKETING
Base | MARKETING | 19 | 2028-05-01 | 6.7935 | 77.25 | 524.7952 | 0 | 0 | MARKETING
Base | MARKETING | 20 | 2028-06-01 | 7.7255 | 77.25 | 596.7972 | 0 | 0 | MARKETING
Base | MARKETING | 21 | 2028-07-01 | 8.6483 | 77.25 | 668.0793 | 0 | 0 | MARKETING
Base | MARKETING | 22 | 2028-08-01 | 9.5618 | 77.25 | 738.6485 | 0 | 0 | MARKETING
Base | MARKETING | 23 | 2028-09-01 | 10.4662 | 77.25 | 808.512 | 0 | 0 | MARKETING
Base | MARKETING | 24 | 2028-10-01 | 11.3615 | 77.25 | 877.6769 | 0 | 0 | MARKETING
Base | MARKETING | 25 | 2028-11-01 | 12.7479 | 79.5675 | 1014.3184 | 0 | 0 | MARKETING
Base | MARKETING | 26 | 2028-12-01 | 14.1204 | 79.5675 | 1123.5264 | 0 | 0 | MARKETING
Base | MARKETING | 27 | 2029-01-01 | 15.4792 | 79.5675 | 1231.6424 | 0 | 0 | MARKETING
Base | MARKETING | 28 | 2029-02-01 | 16.8244 | 79.5675 | 1338.6772 | 0 | 0 | MARKETING
Base | MARKETING | 29 | 2029-03-01 | 18.1562 | 79.5675 | 1444.6417 | 0 | 0 | MARKETING
Base | MARKETING | 30 | 2029-04-01 | 19.4746 | 79.5675 | 1549.5465 | 0 | 0 | MARKETING
Base | MARKETING | 31 | 2029-05-01 | 20.7799 | 79.5675 | 1653.4023 | 0 | 0 | MARKETING
Base | MARKETING | 32 | 2029-06-01 | 22.0721 | 79.5675 | 1756.2196 | 0 | 0 | MARKETING
Base | MARKETING | 33 | 2029-07-01 | 23.3514 | 79.5675 | 1858.0086 | 0 | 0 | MARKETING
Base | MARKETING | 34 | 2029-08-01 | 24.6178 | 79.5675 | 1958.7798 | 0 | 0 | MARKETING
Base | MARKETING | 35 | 2029-09-01 | 25.8717 | 79.5675 | 2058.5432 | 0 | 0 | MARKETING
Base | MARKETING | 36 | 2029-10-01 | 27.1129 | 79.5675 | 2157.309 | 0 | 0 | MARKETING
Base | MARKETING | 37 | 2029-11-01 | 29.0918 | 81.9545 | 2384.2057 | 0 | 0 | MARKETING
Base | MARKETING | 38 | 2029-12-01 | 31.0509 | 81.9545 | 2544.7613 | 0 | 0 | MARKETING
Base | MARKETING | 39 | 2030-01-01 | 32.9904 | 81.9545 | 2703.7114 | 0 | 0 | MARKETING
Base | MARKETING | 40 | 2030-02-01 | 34.9105 | 81.9545 | 2861.072 | 0 | 0 | MARKETING
Base | MARKETING | 41 | 2030-03-01 | 36.8114 | 81.9545 | 3016.8589 | 0 | 0 | MARKETING
Base | MARKETING | 42 | 2030-04-01 | 38.6933 | 81.9545 | 3171.088 | 0 | 0 | MARKETING
Base | MARKETING | 43 | 2030-05-01 | 40.5563 | 81.9545 | 3323.7748 | 0 | 0 | MARKETING
Base | MARKETING | 44 | 2030-06-01 | 42.4008 | 81.9545 | 3474.9348 | 0 | 0 | MARKETING
Base | MARKETING | 45 | 2030-07-01 | 44.2268 | 81.9545 | 3624.5831 | 0 | 0 | MARKETING
Base | MARKETING | 46 | 2030-08-01 | 46.0345 | 81.9545 | 3772.7349 | 0 | 0 | MARKETING
Base | MARKETING | 47 | 2030-09-01 | 47.8241 | 81.9545 | 3919.4053 | 0 | 0 | MARKETING
Base | MARKETING | 48 | 2030-10-01 | 49.5959 | 81.9545 | 4064.6089 | 0 | 0 | MARKETING
Base | MARKETING | 49 | 2030-11-01 | 52.4749 | 84.4132 | 4429.5761 | 0 | 0 | MARKETING
Base | MARKETING | 50 | 2030-12-01 | 55.3252 | 84.4132 | 4670.1748 | 0 | 0 | MARKETING
Base | MARKETING | 51 | 2031-01-01 | 58.1469 | 84.4132 | 4908.3674 | 0 | 0 | MARKETING
Base | MARKETING | 52 | 2031-02-01 | 60.9405 | 84.4132 | 5144.1782 | 0 | 0 | MARKETING
Base | MARKETING | 53 | 2031-03-01 | 63.7061 | 84.4132 | 5377.6308 | 0 | 0 | MARKETING
Base | MARKETING | 54 | 2031-04-01 | 66.444 | 84.4132 | 5608.7489 | 0 | 0 | MARKETING
Base | MARKETING | 55 | 2031-05-01 | 69.1546 | 84.4132 | 5837.5559 | 0 | 0 | MARKETING
Base | MARKETING | 56 | 2031-06-01 | 71.838 | 84.4132 | 6064.0747 | 0 | 0 | MARKETING
Base | MARKETING | 57 | 2031-07-01 | 74.4946 | 84.4132 | 6288.3284 | 0 | 0 | MARKETING
Base | MARKETING | 58 | 2031-08-01 | 77.1247 | 84.4132 | 6510.3395 | 0 | 0 | MARKETING
Base | MARKETING | 59 | 2031-09-01 | 79.7285 | 84.4132 | 6730.1305 | 0 | 0 | MARKETING
Base | MARKETING | 60 | 2031-10-01 | 82.3062 | 84.4132 | 6947.7237 | 0 | 0 | MARKETING
Base | ONBOARD | 1 | 2026-11-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 2 | 2026-12-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 3 | 2027-01-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 4 | 2027-02-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 5 | 2027-03-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 6 | 2027-04-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 7 | 2027-05-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 8 | 2027-06-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 9 | 2027-07-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 10 | 2027-08-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 11 | 2027-09-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 12 | 2027-10-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Base | ONBOARD | 13 | 2027-11-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 14 | 2027-12-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 15 | 2028-01-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 16 | 2028-02-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 17 | 2028-03-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 18 | 2028-04-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 19 | 2028-05-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 20 | 2028-06-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 21 | 2028-07-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 22 | 2028-08-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 23 | 2028-09-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 24 | 2028-10-01 | 1 | 309 | 309 | 0 | 0 | ONBOARD
Base | ONBOARD | 25 | 2028-11-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 26 | 2028-12-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 27 | 2029-01-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 28 | 2029-02-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 29 | 2029-03-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 30 | 2029-04-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 31 | 2029-05-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 32 | 2029-06-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 33 | 2029-07-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 34 | 2029-08-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 35 | 2029-09-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 36 | 2029-10-01 | 1.5 | 318.27 | 477.405 | 0 | 0 | ONBOARD
Base | ONBOARD | 37 | 2029-11-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 38 | 2029-12-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 39 | 2030-01-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 40 | 2030-02-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 41 | 2030-03-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 42 | 2030-04-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 43 | 2030-05-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 44 | 2030-06-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 45 | 2030-07-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 46 | 2030-08-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 47 | 2030-09-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 48 | 2030-10-01 | 2.25 | 327.8181 | 737.5907 | 0 | 0 | ONBOARD
Base | ONBOARD | 49 | 2030-11-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 50 | 2030-12-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 51 | 2031-01-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 52 | 2031-02-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 53 | 2031-03-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 54 | 2031-04-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 55 | 2031-05-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 56 | 2031-06-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 57 | 2031-07-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 58 | 2031-08-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 59 | 2031-09-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | ONBOARD | 60 | 2031-10-01 | 3.375 | 337.6526 | 1139.5777 | 0 | 0 | ONBOARD
Base | AI-IN | 1 | 2026-11-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 2 | 2026-12-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 3 | 2027-01-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 4 | 2027-02-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 5 | 2027-03-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 6 | 2027-04-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 7 | 2027-05-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 8 | 2027-06-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 9 | 2027-07-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 10 | 2027-08-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 11 | 2027-09-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 12 | 2027-10-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Base | AI-IN | 13 | 2027-11-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 14 | 2027-12-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 15 | 2028-01-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 16 | 2028-02-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 17 | 2028-03-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 18 | 2028-04-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 19 | 2028-05-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 20 | 2028-06-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 21 | 2028-07-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 22 | 2028-08-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 23 | 2028-09-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 24 | 2028-10-01 | 0 | 0.412 | 0 | 0 | 0 | AI
Base | AI-IN | 25 | 2028-11-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 26 | 2028-12-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 27 | 2029-01-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 28 | 2029-02-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 29 | 2029-03-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 30 | 2029-04-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 31 | 2029-05-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 32 | 2029-06-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 33 | 2029-07-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 34 | 2029-08-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 35 | 2029-09-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 36 | 2029-10-01 | 0 | 0.42436 | 0 | 0 | 0 | AI
Base | AI-IN | 37 | 2029-11-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 38 | 2029-12-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 39 | 2030-01-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 40 | 2030-02-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 41 | 2030-03-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 42 | 2030-04-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 43 | 2030-05-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 44 | 2030-06-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 45 | 2030-07-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 46 | 2030-08-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 47 | 2030-09-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 48 | 2030-10-01 | 0 | 0.43709 | 0 | 0 | 0 | AI
Base | AI-IN | 49 | 2030-11-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 50 | 2030-12-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 51 | 2031-01-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 52 | 2031-02-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 53 | 2031-03-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 54 | 2031-04-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 55 | 2031-05-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 56 | 2031-06-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 57 | 2031-07-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 58 | 2031-08-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 59 | 2031-09-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-IN | 60 | 2031-10-01 | 0 | 0.4502 | 0 | 0 | 0 | AI
Base | AI-OUT | 1 | 2026-11-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 2 | 2026-12-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 3 | 2027-01-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 4 | 2027-02-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 5 | 2027-03-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 6 | 2027-04-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 7 | 2027-05-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 8 | 2027-06-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 9 | 2027-07-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 10 | 2027-08-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 11 | 2027-09-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 12 | 2027-10-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Base | AI-OUT | 13 | 2027-11-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 14 | 2027-12-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 15 | 2028-01-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 16 | 2028-02-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 17 | 2028-03-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 18 | 2028-04-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 19 | 2028-05-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 20 | 2028-06-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 21 | 2028-07-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 22 | 2028-08-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 23 | 2028-09-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 24 | 2028-10-01 | 0 | 1.648 | 0 | 0 | 0 | AI
Base | AI-OUT | 25 | 2028-11-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 26 | 2028-12-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 27 | 2029-01-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 28 | 2029-02-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 29 | 2029-03-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 30 | 2029-04-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 31 | 2029-05-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 32 | 2029-06-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 33 | 2029-07-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 34 | 2029-08-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 35 | 2029-09-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 36 | 2029-10-01 | 0 | 1.6974 | 0 | 0 | 0 | AI
Base | AI-OUT | 37 | 2029-11-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 38 | 2029-12-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 39 | 2030-01-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 40 | 2030-02-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 41 | 2030-03-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 42 | 2030-04-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 43 | 2030-05-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 44 | 2030-06-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 45 | 2030-07-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 46 | 2030-08-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 47 | 2030-09-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 48 | 2030-10-01 | 0 | 1.7484 | 0 | 0 | 0 | AI
Base | AI-OUT | 49 | 2030-11-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 50 | 2030-12-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 51 | 2031-01-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 52 | 2031-02-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 53 | 2031-03-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 54 | 2031-04-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 55 | 2031-05-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 56 | 2031-06-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 57 | 2031-07-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 58 | 2031-08-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 59 | 2031-09-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-OUT | 60 | 2031-10-01 | 0 | 1.8008 | 0 | 0 | 0 | AI
Base | AI-EVAL | 1 | 2026-11-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 2 | 2026-12-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 3 | 2027-01-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 4 | 2027-02-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 5 | 2027-03-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 6 | 2027-04-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 7 | 2027-05-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 8 | 2027-06-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 9 | 2027-07-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 10 | 2027-08-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 11 | 2027-09-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 12 | 2027-10-01 | 0 | 15000 | 0 | 0 | 0 | AI
Base | AI-EVAL | 13 | 2027-11-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 14 | 2027-12-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 15 | 2028-01-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 16 | 2028-02-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 17 | 2028-03-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 18 | 2028-04-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 19 | 2028-05-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 20 | 2028-06-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 21 | 2028-07-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 22 | 2028-08-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 23 | 2028-09-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 24 | 2028-10-01 | 0 | 15450 | 0 | 0 | 0 | AI
Base | AI-EVAL | 25 | 2028-11-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 26 | 2028-12-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 27 | 2029-01-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 28 | 2029-02-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 29 | 2029-03-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 30 | 2029-04-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 31 | 2029-05-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 32 | 2029-06-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 33 | 2029-07-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 34 | 2029-08-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 35 | 2029-09-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 36 | 2029-10-01 | 0 | 15913.5 | 0 | 0 | 0 | AI
Base | AI-EVAL | 37 | 2029-11-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 38 | 2029-12-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 39 | 2030-01-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 40 | 2030-02-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 41 | 2030-03-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 42 | 2030-04-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 43 | 2030-05-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 44 | 2030-06-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 45 | 2030-07-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 46 | 2030-08-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 47 | 2030-09-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 48 | 2030-10-01 | 0 | 16390.905 | 0 | 0 | 0 | AI
Base | AI-EVAL | 49 | 2030-11-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 50 | 2030-12-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 51 | 2031-01-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 52 | 2031-02-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 53 | 2031-03-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 54 | 2031-04-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 55 | 2031-05-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 56 | 2031-06-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 57 | 2031-07-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 58 | 2031-08-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 59 | 2031-09-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | AI-EVAL | 60 | 2031-10-01 | 0 | 16882.6322 | 0 | 0 | 0 | AI
Base | CTMS-EXT | 1 | 2026-11-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 2 | 2026-12-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 3 | 2027-01-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 4 | 2027-02-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 5 | 2027-03-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 6 | 2027-04-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 7 | 2027-05-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 8 | 2027-06-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 9 | 2027-07-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 10 | 2027-08-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 11 | 2027-09-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 12 | 2027-10-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 13 | 2027-11-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 14 | 2027-12-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 15 | 2028-01-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 16 | 2028-02-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 17 | 2028-03-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 18 | 2028-04-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 19 | 2028-05-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 20 | 2028-06-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 21 | 2028-07-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 22 | 2028-08-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 23 | 2028-09-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 24 | 2028-10-01 | 0 | 41200 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 25 | 2028-11-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 26 | 2028-12-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 27 | 2029-01-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 28 | 2029-02-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 29 | 2029-03-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 30 | 2029-04-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 31 | 2029-05-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 32 | 2029-06-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 33 | 2029-07-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 34 | 2029-08-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 35 | 2029-09-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 36 | 2029-10-01 | 0 | 42436 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 37 | 2029-11-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 38 | 2029-12-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 39 | 2030-01-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 40 | 2030-02-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 41 | 2030-03-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 42 | 2030-04-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 43 | 2030-05-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 44 | 2030-06-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 45 | 2030-07-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 46 | 2030-08-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 47 | 2030-09-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 48 | 2030-10-01 | 0 | 43709.08 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 49 | 2030-11-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 50 | 2030-12-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 51 | 2031-01-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 52 | 2031-02-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 53 | 2031-03-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 54 | 2031-04-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 55 | 2031-05-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 56 | 2031-06-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 57 | 2031-07-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 58 | 2031-08-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 59 | 2031-09-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Base | CTMS-EXT | 60 | 2031-10-01 | 0 | 45020.3524 | 0 | 0 | 0 | CTMS
Growth | INFRA-APP | 1 | 2026-11-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 2 | 2026-12-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 3 | 2027-01-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 4 | 2027-02-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 5 | 2027-03-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 6 | 2027-04-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 7 | 2027-05-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 8 | 2027-06-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 9 | 2027-07-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 10 | 2027-08-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 11 | 2027-09-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 12 | 2027-10-01 | 1 | 400 | 400 | 400 | 0 | INFRA
Growth | INFRA-APP | 13 | 2027-11-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 14 | 2027-12-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 15 | 2028-01-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 16 | 2028-02-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 17 | 2028-03-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 18 | 2028-04-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 19 | 2028-05-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 20 | 2028-06-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 21 | 2028-07-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 22 | 2028-08-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 23 | 2028-09-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 24 | 2028-10-01 | 1 | 416 | 416 | 416 | 0 | INFRA
Growth | INFRA-APP | 25 | 2028-11-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 26 | 2028-12-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 27 | 2029-01-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 28 | 2029-02-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 29 | 2029-03-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 30 | 2029-04-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 31 | 2029-05-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 32 | 2029-06-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 33 | 2029-07-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 34 | 2029-08-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 35 | 2029-09-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 36 | 2029-10-01 | 1 | 432.64 | 432.64 | 432.64 | 0 | INFRA
Growth | INFRA-APP | 37 | 2029-11-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 38 | 2029-12-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 39 | 2030-01-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 40 | 2030-02-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 41 | 2030-03-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 42 | 2030-04-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 43 | 2030-05-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 44 | 2030-06-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 45 | 2030-07-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 46 | 2030-08-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 47 | 2030-09-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 48 | 2030-10-01 | 1 | 449.9456 | 449.9456 | 449.9456 | 0 | INFRA
Growth | INFRA-APP | 49 | 2030-11-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 50 | 2030-12-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 51 | 2031-01-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 52 | 2031-02-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 53 | 2031-03-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 54 | 2031-04-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 55 | 2031-05-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 56 | 2031-06-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 57 | 2031-07-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 58 | 2031-08-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 59 | 2031-09-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-APP | 60 | 2031-10-01 | 1 | 467.9434 | 467.9434 | 467.9434 | 0 | INFRA
Growth | INFRA-DB | 1 | 2026-11-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 2 | 2026-12-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 3 | 2027-01-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 4 | 2027-02-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 5 | 2027-03-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 6 | 2027-04-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 7 | 2027-05-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 8 | 2027-06-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 9 | 2027-07-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 10 | 2027-08-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 11 | 2027-09-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 12 | 2027-10-01 | 1 | 600 | 600 | 600 | 0 | INFRA
Growth | INFRA-DB | 13 | 2027-11-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 14 | 2027-12-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 15 | 2028-01-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 16 | 2028-02-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 17 | 2028-03-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 18 | 2028-04-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 19 | 2028-05-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 20 | 2028-06-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 21 | 2028-07-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 22 | 2028-08-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 23 | 2028-09-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 24 | 2028-10-01 | 1 | 624 | 624 | 624 | 0 | INFRA
Growth | INFRA-DB | 25 | 2028-11-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 26 | 2028-12-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 27 | 2029-01-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 28 | 2029-02-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 29 | 2029-03-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 30 | 2029-04-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 31 | 2029-05-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 32 | 2029-06-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 33 | 2029-07-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 34 | 2029-08-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 35 | 2029-09-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 36 | 2029-10-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | INFRA
Growth | INFRA-DB | 37 | 2029-11-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 38 | 2029-12-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 39 | 2030-01-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 40 | 2030-02-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 41 | 2030-03-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 42 | 2030-04-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 43 | 2030-05-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 44 | 2030-06-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 45 | 2030-07-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 46 | 2030-08-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 47 | 2030-09-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 48 | 2030-10-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | INFRA
Growth | INFRA-DB | 49 | 2030-11-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 50 | 2030-12-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 51 | 2031-01-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 52 | 2031-02-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 53 | 2031-03-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 54 | 2031-04-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 55 | 2031-05-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 56 | 2031-06-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 57 | 2031-07-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 58 | 2031-08-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 59 | 2031-09-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-DB | 60 | 2031-10-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | INFRA
Growth | INFRA-AWS | 1 | 2026-11-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 2 | 2026-12-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 3 | 2027-01-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 4 | 2027-02-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 5 | 2027-03-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 6 | 2027-04-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 7 | 2027-05-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 8 | 2027-06-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 9 | 2027-07-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 10 | 2027-08-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 11 | 2027-09-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 12 | 2027-10-01 | 0 | 1100 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 13 | 2027-11-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 14 | 2027-12-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 15 | 2028-01-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 16 | 2028-02-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 17 | 2028-03-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 18 | 2028-04-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 19 | 2028-05-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 20 | 2028-06-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 21 | 2028-07-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 22 | 2028-08-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 23 | 2028-09-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 24 | 2028-10-01 | 0 | 1144 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 25 | 2028-11-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 26 | 2028-12-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 27 | 2029-01-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 28 | 2029-02-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 29 | 2029-03-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 30 | 2029-04-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 31 | 2029-05-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 32 | 2029-06-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 33 | 2029-07-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 34 | 2029-08-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 35 | 2029-09-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 36 | 2029-10-01 | 0 | 1189.76 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 37 | 2029-11-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 38 | 2029-12-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 39 | 2030-01-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 40 | 2030-02-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 41 | 2030-03-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 42 | 2030-04-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 43 | 2030-05-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 44 | 2030-06-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 45 | 2030-07-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 46 | 2030-08-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 47 | 2030-09-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 48 | 2030-10-01 | 0 | 1237.3504 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 49 | 2030-11-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 50 | 2030-12-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 51 | 2031-01-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 52 | 2031-02-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 53 | 2031-03-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 54 | 2031-04-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 55 | 2031-05-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 56 | 2031-06-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 57 | 2031-07-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 58 | 2031-08-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 59 | 2031-09-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-AWS | 60 | 2031-10-01 | 0 | 1286.8444 | 0 | 0 | 0 | INFRA
Growth | INFRA-EDGE | 1 | 2026-11-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 2 | 2026-12-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 3 | 2027-01-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 4 | 2027-02-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 5 | 2027-03-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 6 | 2027-04-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 7 | 2027-05-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 8 | 2027-06-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 9 | 2027-07-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 10 | 2027-08-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 11 | 2027-09-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 12 | 2027-10-01 | 1 | 250 | 250 | 250 | 0 | INFRA
Growth | INFRA-EDGE | 13 | 2027-11-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 14 | 2027-12-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 15 | 2028-01-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 16 | 2028-02-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 17 | 2028-03-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 18 | 2028-04-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 19 | 2028-05-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 20 | 2028-06-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 21 | 2028-07-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 22 | 2028-08-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 23 | 2028-09-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 24 | 2028-10-01 | 1 | 260 | 260 | 260 | 0 | INFRA
Growth | INFRA-EDGE | 25 | 2028-11-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 26 | 2028-12-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 27 | 2029-01-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 28 | 2029-02-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 29 | 2029-03-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 30 | 2029-04-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 31 | 2029-05-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 32 | 2029-06-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 33 | 2029-07-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 34 | 2029-08-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 35 | 2029-09-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 36 | 2029-10-01 | 1 | 270.4 | 270.4 | 270.4 | 0 | INFRA
Growth | INFRA-EDGE | 37 | 2029-11-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 38 | 2029-12-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 39 | 2030-01-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 40 | 2030-02-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 41 | 2030-03-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 42 | 2030-04-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 43 | 2030-05-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 44 | 2030-06-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 45 | 2030-07-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 46 | 2030-08-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 47 | 2030-09-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 48 | 2030-10-01 | 1 | 281.216 | 281.216 | 281.216 | 0 | INFRA
Growth | INFRA-EDGE | 49 | 2030-11-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 50 | 2030-12-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 51 | 2031-01-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 52 | 2031-02-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 53 | 2031-03-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 54 | 2031-04-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 55 | 2031-05-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 56 | 2031-06-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 57 | 2031-07-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 58 | 2031-08-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 59 | 2031-09-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-EDGE | 60 | 2031-10-01 | 1 | 292.4646 | 292.4646 | 292.4646 | 0 | INFRA
Growth | INFRA-STORE | 1 | 2026-11-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 2 | 2026-12-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 3 | 2027-01-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 4 | 2027-02-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 5 | 2027-03-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 6 | 2027-04-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 7 | 2027-05-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 8 | 2027-06-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 9 | 2027-07-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 10 | 2027-08-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 11 | 2027-09-01 | 0 | 0.15 | 0 | 0 | 0 | INFRA
Growth | INFRA-STORE | 12 | 2027-10-01 | 20 | 0.15 | 3 | 0 | 0 | INFRA
Growth | INFRA-STORE | 13 | 2027-11-01 | 39.8 | 0.156 | 6.2088 | 0 | 0 | INFRA
Growth | INFRA-STORE | 14 | 2027-12-01 | 59.402 | 0.156 | 9.2667 | 0 | 0 | INFRA
Growth | INFRA-STORE | 15 | 2028-01-01 | 78.808 | 0.156 | 12.294 | 0 | 0 | INFRA
Growth | INFRA-STORE | 16 | 2028-02-01 | 98.0199 | 0.156 | 15.2911 | 0 | 0 | INFRA
Growth | INFRA-STORE | 17 | 2028-03-01 | 117.0397 | 0.156 | 18.2582 | 0 | 0 | INFRA
Growth | INFRA-STORE | 18 | 2028-04-01 | 135.8693 | 0.156 | 21.1956 | 0 | 0 | INFRA
Growth | INFRA-STORE | 19 | 2028-05-01 | 154.5106 | 0.156 | 24.1037 | 0 | 0 | INFRA
Growth | INFRA-STORE | 20 | 2028-06-01 | 172.9655 | 0.156 | 26.9826 | 0 | 0 | INFRA
Growth | INFRA-STORE | 21 | 2028-07-01 | 191.2358 | 0.156 | 29.8328 | 0 | 0 | INFRA
Growth | INFRA-STORE | 22 | 2028-08-01 | 209.3235 | 0.156 | 32.6545 | 0 | 0 | INFRA
Growth | INFRA-STORE | 23 | 2028-09-01 | 227.2303 | 0.156 | 35.4479 | 0 | 0 | INFRA
Growth | INFRA-STORE | 24 | 2028-10-01 | 258.958 | 0.156 | 40.3974 | 0 | 0 | INFRA
Growth | INFRA-STORE | 25 | 2028-11-01 | 290.3684 | 0.16224 | 47.1094 | 0 | 0 | INFRA
Growth | INFRA-STORE | 26 | 2028-12-01 | 321.4647 | 0.16224 | 52.1544 | 0 | 0 | INFRA
Growth | INFRA-STORE | 27 | 2029-01-01 | 352.25 | 0.16224 | 57.149 | 0 | 0 | INFRA
Growth | INFRA-STORE | 28 | 2029-02-01 | 382.7275 | 0.16224 | 62.0937 | 0 | 0 | INFRA
Growth | INFRA-STORE | 29 | 2029-03-01 | 412.9003 | 0.16224 | 66.9889 | 0 | 0 | INFRA
Growth | INFRA-STORE | 30 | 2029-04-01 | 442.7713 | 0.16224 | 71.8352 | 0 | 0 | INFRA
Growth | INFRA-STORE | 31 | 2029-05-01 | 472.3436 | 0.16224 | 76.633 | 0 | 0 | INFRA
Growth | INFRA-STORE | 32 | 2029-06-01 | 501.6201 | 0.16224 | 81.3828 | 0 | 0 | INFRA
Growth | INFRA-STORE | 33 | 2029-07-01 | 530.6039 | 0.16224 | 86.0852 | 0 | 0 | INFRA
Growth | INFRA-STORE | 34 | 2029-08-01 | 559.2979 | 0.16224 | 90.7405 | 0 | 0 | INFRA
Growth | INFRA-STORE | 35 | 2029-09-01 | 587.7049 | 0.16224 | 95.3492 | 0 | 0 | INFRA
Growth | INFRA-STORE | 36 | 2029-10-01 | 639.6278 | 0.16224 | 103.7732 | 0 | 0 | INFRA
Growth | INFRA-STORE | 37 | 2029-11-01 | 691.0316 | 0.16873 | 116.5975 | 0 | 0 | INFRA
Growth | INFRA-STORE | 38 | 2029-12-01 | 741.9213 | 0.16873 | 125.1841 | 0 | 0 | INFRA
Growth | INFRA-STORE | 39 | 2030-01-01 | 792.302 | 0.16873 | 133.6848 | 0 | 0 | INFRA
Growth | INFRA-STORE | 40 | 2030-02-01 | 842.179 | 0.16873 | 142.1005 | 0 | 0 | INFRA
Growth | INFRA-STORE | 41 | 2030-03-01 | 891.5572 | 0.16873 | 150.4321 | 0 | 0 | INFRA
Growth | INFRA-STORE | 42 | 2030-04-01 | 940.4417 | 0.16873 | 158.6803 | 0 | 0 | INFRA
Growth | INFRA-STORE | 43 | 2030-05-01 | 988.8372 | 0.16873 | 166.8461 | 0 | 0 | INFRA
Growth | INFRA-STORE | 44 | 2030-06-01 | 1036.7489 | 0.16873 | 174.9302 | 0 | 0 | INFRA
Growth | INFRA-STORE | 45 | 2030-07-01 | 1084.1814 | 0.16873 | 182.9335 | 0 | 0 | INFRA
Growth | INFRA-STORE | 46 | 2030-08-01 | 1131.1396 | 0.16873 | 190.8567 | 0 | 0 | INFRA
Growth | INFRA-STORE | 47 | 2030-09-01 | 1177.6282 | 0.16873 | 198.7007 | 0 | 0 | INFRA
Growth | INFRA-STORE | 48 | 2030-10-01 | 1264.1119 | 0.16873 | 213.2931 | 0 | 0 | INFRA
Growth | INFRA-STORE | 49 | 2030-11-01 | 1349.7308 | 0.17548 | 236.8491 | 0 | 0 | INFRA
Growth | INFRA-STORE | 50 | 2030-12-01 | 1434.4935 | 0.17548 | 251.7232 | 0 | 0 | INFRA
Growth | INFRA-STORE | 51 | 2031-01-01 | 1518.4085 | 0.17548 | 266.4485 | 0 | 0 | INFRA
Growth | INFRA-STORE | 52 | 2031-02-01 | 1601.4844 | 0.17548 | 281.0265 | 0 | 0 | INFRA
Growth | INFRA-STORE | 53 | 2031-03-01 | 1683.7296 | 0.17548 | 295.4588 | 0 | 0 | INFRA
Growth | INFRA-STORE | 54 | 2031-04-01 | 1765.1523 | 0.17548 | 309.7468 | 0 | 0 | INFRA
Growth | INFRA-STORE | 55 | 2031-05-01 | 1845.7608 | 0.17548 | 323.8919 | 0 | 0 | INFRA
Growth | INFRA-STORE | 56 | 2031-06-01 | 1925.5632 | 0.17548 | 337.8955 | 0 | 0 | INFRA
Growth | INFRA-STORE | 57 | 2031-07-01 | 2004.5675 | 0.17548 | 351.7591 | 0 | 0 | INFRA
Growth | INFRA-STORE | 58 | 2031-08-01 | 2082.7819 | 0.17548 | 365.484 | 0 | 0 | INFRA
Growth | INFRA-STORE | 59 | 2031-09-01 | 2160.214 | 0.17548 | 379.0717 | 0 | 0 | INFRA
Growth | INFRA-STORE | 60 | 2031-10-01 | 2305.6539 | 0.17548 | 404.5933 | 0 | 0 | INFRA
Growth | INFRA-LOG | 1 | 2026-11-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 2 | 2026-12-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 3 | 2027-01-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 4 | 2027-02-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 5 | 2027-03-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 6 | 2027-04-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 7 | 2027-05-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 8 | 2027-06-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 9 | 2027-07-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 10 | 2027-08-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 11 | 2027-09-01 | 0 | 5 | 0 | 0 | 0 | INFRA
Growth | INFRA-LOG | 12 | 2027-10-01 | 4 | 5 | 20 | 0 | 0 | INFRA
Growth | INFRA-LOG | 13 | 2027-11-01 | 7.96 | 5.2 | 41.392 | 0 | 0 | INFRA
Growth | INFRA-LOG | 14 | 2027-12-01 | 11.8804 | 5.2 | 61.7781 | 0 | 0 | INFRA
Growth | INFRA-LOG | 15 | 2028-01-01 | 15.7616 | 5.2 | 81.9603 | 0 | 0 | INFRA
Growth | INFRA-LOG | 16 | 2028-02-01 | 19.604 | 5.2 | 101.9407 | 0 | 0 | INFRA
Growth | INFRA-LOG | 17 | 2028-03-01 | 23.4079 | 5.2 | 121.7213 | 0 | 0 | INFRA
Growth | INFRA-LOG | 18 | 2028-04-01 | 27.1739 | 5.2 | 141.3041 | 0 | 0 | INFRA
Growth | INFRA-LOG | 19 | 2028-05-01 | 30.9021 | 5.2 | 160.691 | 0 | 0 | INFRA
Growth | INFRA-LOG | 20 | 2028-06-01 | 34.5931 | 5.2 | 179.8841 | 0 | 0 | INFRA
Growth | INFRA-LOG | 21 | 2028-07-01 | 38.2472 | 5.2 | 198.8853 | 0 | 0 | INFRA
Growth | INFRA-LOG | 22 | 2028-08-01 | 41.8647 | 5.2 | 217.6964 | 0 | 0 | INFRA
Growth | INFRA-LOG | 23 | 2028-09-01 | 45.4461 | 5.2 | 236.3195 | 0 | 0 | INFRA
Growth | INFRA-LOG | 24 | 2028-10-01 | 51.7916 | 5.2 | 269.3163 | 0 | 0 | INFRA
Growth | INFRA-LOG | 25 | 2028-11-01 | 58.0737 | 5.408 | 314.0624 | 0 | 0 | INFRA
Growth | INFRA-LOG | 26 | 2028-12-01 | 64.2929 | 5.408 | 347.6962 | 0 | 0 | INFRA
Growth | INFRA-LOG | 27 | 2029-01-01 | 70.45 | 5.408 | 380.9936 | 0 | 0 | INFRA
Growth | INFRA-LOG | 28 | 2029-02-01 | 76.5455 | 5.408 | 413.9581 | 0 | 0 | INFRA
Growth | INFRA-LOG | 29 | 2029-03-01 | 82.5801 | 5.408 | 446.5929 | 0 | 0 | INFRA
Growth | INFRA-LOG | 30 | 2029-04-01 | 88.5543 | 5.408 | 478.9014 | 0 | 0 | INFRA
Growth | INFRA-LOG | 31 | 2029-05-01 | 94.4687 | 5.408 | 510.8868 | 0 | 0 | INFRA
Growth | INFRA-LOG | 32 | 2029-06-01 | 100.324 | 5.408 | 542.5523 | 0 | 0 | INFRA
Growth | INFRA-LOG | 33 | 2029-07-01 | 106.1208 | 5.408 | 573.9012 | 0 | 0 | INFRA
Growth | INFRA-LOG | 34 | 2029-08-01 | 111.8596 | 5.408 | 604.9366 | 0 | 0 | INFRA
Growth | INFRA-LOG | 35 | 2029-09-01 | 117.541 | 5.408 | 635.6616 | 0 | 0 | INFRA
Growth | INFRA-LOG | 36 | 2029-10-01 | 127.9256 | 5.408 | 691.8215 | 0 | 0 | INFRA
Growth | INFRA-LOG | 37 | 2029-11-01 | 138.2063 | 5.6243 | 777.3165 | 0 | 0 | INFRA
Growth | INFRA-LOG | 38 | 2029-12-01 | 148.3843 | 5.6243 | 834.5605 | 0 | 0 | INFRA
Growth | INFRA-LOG | 39 | 2030-01-01 | 158.4604 | 5.6243 | 891.232 | 0 | 0 | INFRA
Growth | INFRA-LOG | 40 | 2030-02-01 | 168.4358 | 5.6243 | 947.3369 | 0 | 0 | INFRA
Growth | INFRA-LOG | 41 | 2030-03-01 | 178.3114 | 5.6243 | 1002.8806 | 0 | 0 | INFRA
Growth | INFRA-LOG | 42 | 2030-04-01 | 188.0883 | 5.6243 | 1057.869 | 0 | 0 | INFRA
Growth | INFRA-LOG | 43 | 2030-05-01 | 197.7674 | 5.6243 | 1112.3074 | 0 | 0 | INFRA
Growth | INFRA-LOG | 44 | 2030-06-01 | 207.3498 | 5.6243 | 1166.2015 | 0 | 0 | INFRA
Growth | INFRA-LOG | 45 | 2030-07-01 | 216.8363 | 5.6243 | 1219.5566 | 0 | 0 | INFRA
Growth | INFRA-LOG | 46 | 2030-08-01 | 226.2279 | 5.6243 | 1272.3782 | 0 | 0 | INFRA
Growth | INFRA-LOG | 47 | 2030-09-01 | 235.5256 | 5.6243 | 1324.6715 | 0 | 0 | INFRA
Growth | INFRA-LOG | 48 | 2030-10-01 | 252.8224 | 5.6243 | 1421.954 | 0 | 0 | INFRA
Growth | INFRA-LOG | 49 | 2030-11-01 | 269.9462 | 5.8493 | 1578.9941 | 0 | 0 | INFRA
Growth | INFRA-LOG | 50 | 2030-12-01 | 286.8987 | 5.8493 | 1678.1545 | 0 | 0 | INFRA
Growth | INFRA-LOG | 51 | 2031-01-01 | 303.6817 | 5.8493 | 1776.3232 | 0 | 0 | INFRA
Growth | INFRA-LOG | 52 | 2031-02-01 | 320.2969 | 5.8493 | 1873.5103 | 0 | 0 | INFRA
Growth | INFRA-LOG | 53 | 2031-03-01 | 336.7459 | 5.8493 | 1969.7255 | 0 | 0 | INFRA
Growth | INFRA-LOG | 54 | 2031-04-01 | 353.0305 | 5.8493 | 2064.9785 | 0 | 0 | INFRA
Growth | INFRA-LOG | 55 | 2031-05-01 | 369.1522 | 5.8493 | 2159.279 | 0 | 0 | INFRA
Growth | INFRA-LOG | 56 | 2031-06-01 | 385.1126 | 5.8493 | 2252.6366 | 0 | 0 | INFRA
Growth | INFRA-LOG | 57 | 2031-07-01 | 400.9135 | 5.8493 | 2345.0605 | 0 | 0 | INFRA
Growth | INFRA-LOG | 58 | 2031-08-01 | 416.5564 | 5.8493 | 2436.5602 | 0 | 0 | INFRA
Growth | INFRA-LOG | 59 | 2031-09-01 | 432.0428 | 5.8493 | 2527.1449 | 0 | 0 | INFRA
Growth | INFRA-LOG | 60 | 2031-10-01 | 461.1308 | 5.8493 | 2697.289 | 0 | 0 | INFRA
Growth | INFRA-REQ | 1 | 2026-11-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 2 | 2026-12-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 3 | 2027-01-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 4 | 2027-02-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 5 | 2027-03-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 6 | 2027-04-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 7 | 2027-05-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 8 | 2027-06-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 9 | 2027-07-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 10 | 2027-08-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 11 | 2027-09-01 | 0 | 30 | 0 | 0 | 0 | INFRA
Growth | INFRA-REQ | 12 | 2027-10-01 | 0.375 | 30 | 11.25 | 0 | 0 | INFRA
Growth | INFRA-REQ | 13 | 2027-11-01 | 0.74625 | 31.2 | 23.283 | 0 | 0 | INFRA
Growth | INFRA-REQ | 14 | 2027-12-01 | 1.1138 | 31.2 | 34.7502 | 0 | 0 | INFRA
Growth | INFRA-REQ | 15 | 2028-01-01 | 1.4776 | 31.2 | 46.1027 | 0 | 0 | INFRA
Growth | INFRA-REQ | 16 | 2028-02-01 | 1.8379 | 31.2 | 57.3416 | 0 | 0 | INFRA
Growth | INFRA-REQ | 17 | 2028-03-01 | 2.1945 | 31.2 | 68.4682 | 0 | 0 | INFRA
Growth | INFRA-REQ | 18 | 2028-04-01 | 2.5475 | 31.2 | 79.4835 | 0 | 0 | INFRA
Growth | INFRA-REQ | 19 | 2028-05-01 | 2.8971 | 31.2 | 90.3887 | 0 | 0 | INFRA
Growth | INFRA-REQ | 20 | 2028-06-01 | 3.2431 | 31.2 | 101.1848 | 0 | 0 | INFRA
Growth | INFRA-REQ | 21 | 2028-07-01 | 3.5857 | 31.2 | 111.873 | 0 | 0 | INFRA
Growth | INFRA-REQ | 22 | 2028-08-01 | 3.9248 | 31.2 | 122.4542 | 0 | 0 | INFRA
Growth | INFRA-REQ | 23 | 2028-09-01 | 4.2606 | 31.2 | 132.9297 | 0 | 0 | INFRA
Growth | INFRA-REQ | 24 | 2028-10-01 | 4.8555 | 31.2 | 151.4904 | 0 | 0 | INFRA
Growth | INFRA-REQ | 25 | 2028-11-01 | 5.4444 | 32.448 | 176.6601 | 0 | 0 | INFRA
Growth | INFRA-REQ | 26 | 2028-12-01 | 6.0275 | 32.448 | 195.5791 | 0 | 0 | INFRA
Growth | INFRA-REQ | 27 | 2029-01-01 | 6.6047 | 32.448 | 214.3089 | 0 | 0 | INFRA
Growth | INFRA-REQ | 28 | 2029-02-01 | 7.1761 | 32.448 | 232.8514 | 0 | 0 | INFRA
Growth | INFRA-REQ | 29 | 2029-03-01 | 7.7419 | 32.448 | 251.2085 | 0 | 0 | INFRA
Growth | INFRA-REQ | 30 | 2029-04-01 | 8.302 | 32.448 | 269.382 | 0 | 0 | INFRA
Growth | INFRA-REQ | 31 | 2029-05-01 | 8.8564 | 32.448 | 287.3738 | 0 | 0 | INFRA
Growth | INFRA-REQ | 32 | 2029-06-01 | 9.4054 | 32.448 | 305.1857 | 0 | 0 | INFRA
Growth | INFRA-REQ | 33 | 2029-07-01 | 9.9488 | 32.448 | 322.8194 | 0 | 0 | INFRA
Growth | INFRA-REQ | 34 | 2029-08-01 | 10.4868 | 32.448 | 340.2768 | 0 | 0 | INFRA
Growth | INFRA-REQ | 35 | 2029-09-01 | 11.0195 | 32.448 | 357.5597 | 0 | 0 | INFRA
Growth | INFRA-REQ | 36 | 2029-10-01 | 11.993 | 32.448 | 389.1496 | 0 | 0 | INFRA
Growth | INFRA-REQ | 37 | 2029-11-01 | 12.9568 | 33.7459 | 437.2406 | 0 | 0 | INFRA
Growth | INFRA-REQ | 38 | 2029-12-01 | 13.911 | 33.7459 | 469.4403 | 0 | 0 | INFRA
Growth | INFRA-REQ | 39 | 2030-01-01 | 14.8557 | 33.7459 | 501.318 | 0 | 0 | INFRA
Growth | INFRA-REQ | 40 | 2030-02-01 | 15.7909 | 33.7459 | 532.877 | 0 | 0 | INFRA
Growth | INFRA-REQ | 41 | 2030-03-01 | 16.7167 | 33.7459 | 564.1204 | 0 | 0 | INFRA
Growth | INFRA-REQ | 42 | 2030-04-01 | 17.6333 | 33.7459 | 595.0513 | 0 | 0 | INFRA
Growth | INFRA-REQ | 43 | 2030-05-01 | 18.5407 | 33.7459 | 625.6729 | 0 | 0 | INFRA
Growth | INFRA-REQ | 44 | 2030-06-01 | 19.439 | 33.7459 | 655.9883 | 0 | 0 | INFRA
Growth | INFRA-REQ | 45 | 2030-07-01 | 20.3284 | 33.7459 | 686.0006 | 0 | 0 | INFRA
Growth | INFRA-REQ | 46 | 2030-08-01 | 21.2089 | 33.7459 | 715.7127 | 0 | 0 | INFRA
Growth | INFRA-REQ | 47 | 2030-09-01 | 22.0805 | 33.7459 | 745.1277 | 0 | 0 | INFRA
Growth | INFRA-REQ | 48 | 2030-10-01 | 23.7021 | 33.7459 | 799.8491 | 0 | 0 | INFRA
Growth | INFRA-REQ | 49 | 2030-11-01 | 25.3075 | 35.0958 | 888.1842 | 0 | 0 | INFRA
Growth | INFRA-REQ | 50 | 2030-12-01 | 26.8968 | 35.0958 | 943.9619 | 0 | 0 | INFRA
Growth | INFRA-REQ | 51 | 2031-01-01 | 28.4702 | 35.0958 | 999.1818 | 0 | 0 | INFRA
Growth | INFRA-REQ | 52 | 2031-02-01 | 30.0278 | 35.0958 | 1053.8495 | 0 | 0 | INFRA
Growth | INFRA-REQ | 53 | 2031-03-01 | 31.5699 | 35.0958 | 1107.9706 | 0 | 0 | INFRA
Growth | INFRA-REQ | 54 | 2031-04-01 | 33.0966 | 35.0958 | 1161.5504 | 0 | 0 | INFRA
Growth | INFRA-REQ | 55 | 2031-05-01 | 34.608 | 35.0958 | 1214.5945 | 0 | 0 | INFRA
Growth | INFRA-REQ | 56 | 2031-06-01 | 36.1043 | 35.0958 | 1267.1081 | 0 | 0 | INFRA
Growth | INFRA-REQ | 57 | 2031-07-01 | 37.5856 | 35.0958 | 1319.0965 | 0 | 0 | INFRA
Growth | INFRA-REQ | 58 | 2031-08-01 | 39.0522 | 35.0958 | 1370.5651 | 0 | 0 | INFRA
Growth | INFRA-REQ | 59 | 2031-09-01 | 40.504 | 35.0958 | 1421.519 | 0 | 0 | INFRA
Growth | INFRA-REQ | 60 | 2031-10-01 | 43.231 | 35.0958 | 1517.225 | 0 | 0 | INFRA
Growth | TOOLS-GH | 1 | 2026-11-01 | 2 | 4 | 8 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 2 | 2026-12-01 | 5 | 4 | 20 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 3 | 2027-01-01 | 6 | 4 | 24 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 4 | 2027-02-01 | 6 | 4 | 24 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 5 | 2027-03-01 | 6 | 4 | 24 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 6 | 2027-04-01 | 6 | 4 | 24 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 7 | 2027-05-01 | 8 | 4 | 32 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 8 | 2027-06-01 | 8 | 4 | 32 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 9 | 2027-07-01 | 9 | 4 | 36 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 10 | 2027-08-01 | 9 | 4 | 36 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 11 | 2027-09-01 | 9 | 4 | 36 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 12 | 2027-10-01 | 9 | 4 | 36 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 13 | 2027-11-01 | 9 | 4.16 | 37.44 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 14 | 2027-12-01 | 9 | 4.16 | 37.44 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 15 | 2028-01-01 | 9 | 4.16 | 37.44 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 16 | 2028-02-01 | 15 | 4.16 | 62.4 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 17 | 2028-03-01 | 15 | 4.16 | 62.4 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 18 | 2028-04-01 | 15 | 4.16 | 62.4 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 19 | 2028-05-01 | 15 | 4.16 | 62.4 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 20 | 2028-06-01 | 15 | 4.16 | 62.4 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 21 | 2028-07-01 | 15 | 4.16 | 62.4 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 22 | 2028-08-01 | 15 | 4.16 | 62.4 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 23 | 2028-09-01 | 15 | 4.16 | 62.4 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 24 | 2028-10-01 | 15 | 4.16 | 62.4 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 25 | 2028-11-01 | 15 | 4.3264 | 64.896 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 26 | 2028-12-01 | 15 | 4.3264 | 64.896 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 27 | 2029-01-01 | 15 | 4.3264 | 64.896 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 28 | 2029-02-01 | 15 | 4.3264 | 64.896 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 29 | 2029-03-01 | 15 | 4.3264 | 64.896 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 30 | 2029-04-01 | 15 | 4.3264 | 64.896 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 31 | 2029-05-01 | 23 | 4.3264 | 99.5072 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 32 | 2029-06-01 | 23 | 4.3264 | 99.5072 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 33 | 2029-07-01 | 23 | 4.3264 | 99.5072 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 34 | 2029-08-01 | 23 | 4.3264 | 99.5072 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 35 | 2029-09-01 | 23 | 4.3264 | 99.5072 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 36 | 2029-10-01 | 23 | 4.3264 | 99.5072 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 37 | 2029-11-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 38 | 2029-12-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 39 | 2030-01-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 40 | 2030-02-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 41 | 2030-03-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 42 | 2030-04-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 43 | 2030-05-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 44 | 2030-06-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 45 | 2030-07-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 46 | 2030-08-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 47 | 2030-09-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 48 | 2030-10-01 | 23 | 4.4995 | 103.4875 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 49 | 2030-11-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 50 | 2030-12-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 51 | 2031-01-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 52 | 2031-02-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 53 | 2031-03-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 54 | 2031-04-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 55 | 2031-05-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 56 | 2031-06-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 57 | 2031-07-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 58 | 2031-08-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 59 | 2031-09-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-GH | 60 | 2031-10-01 | 23 | 4.6794 | 107.627 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 1 | 2026-11-01 | 2 | 45 | 90 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 2 | 2026-12-01 | 5 | 45 | 225 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 3 | 2027-01-01 | 6 | 45 | 270 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 4 | 2027-02-01 | 6 | 45 | 270 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 5 | 2027-03-01 | 6 | 45 | 270 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 6 | 2027-04-01 | 6 | 45 | 270 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 7 | 2027-05-01 | 8 | 45 | 360 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 8 | 2027-06-01 | 8 | 45 | 360 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 9 | 2027-07-01 | 9 | 45 | 405 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 10 | 2027-08-01 | 9 | 45 | 405 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 11 | 2027-09-01 | 9 | 45 | 405 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 12 | 2027-10-01 | 9 | 45 | 405 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 13 | 2027-11-01 | 9 | 46.8 | 421.2 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 14 | 2027-12-01 | 9 | 46.8 | 421.2 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 15 | 2028-01-01 | 9 | 46.8 | 421.2 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 16 | 2028-02-01 | 15 | 46.8 | 702 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 17 | 2028-03-01 | 15 | 46.8 | 702 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 18 | 2028-04-01 | 15 | 46.8 | 702 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 19 | 2028-05-01 | 15 | 46.8 | 702 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 20 | 2028-06-01 | 15 | 46.8 | 702 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 21 | 2028-07-01 | 15 | 46.8 | 702 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 22 | 2028-08-01 | 15 | 46.8 | 702 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 23 | 2028-09-01 | 15 | 46.8 | 702 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 24 | 2028-10-01 | 15 | 46.8 | 702 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 25 | 2028-11-01 | 15 | 48.672 | 730.08 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 26 | 2028-12-01 | 15 | 48.672 | 730.08 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 27 | 2029-01-01 | 15 | 48.672 | 730.08 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 28 | 2029-02-01 | 15 | 48.672 | 730.08 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 29 | 2029-03-01 | 15 | 48.672 | 730.08 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 30 | 2029-04-01 | 15 | 48.672 | 730.08 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 31 | 2029-05-01 | 23 | 48.672 | 1119.456 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 32 | 2029-06-01 | 23 | 48.672 | 1119.456 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 33 | 2029-07-01 | 23 | 48.672 | 1119.456 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 34 | 2029-08-01 | 23 | 48.672 | 1119.456 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 35 | 2029-09-01 | 23 | 48.672 | 1119.456 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 36 | 2029-10-01 | 23 | 48.672 | 1119.456 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 37 | 2029-11-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 38 | 2029-12-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 39 | 2030-01-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 40 | 2030-02-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 41 | 2030-03-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 42 | 2030-04-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 43 | 2030-05-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 44 | 2030-06-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 45 | 2030-07-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 46 | 2030-08-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 47 | 2030-09-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 48 | 2030-10-01 | 23 | 50.6189 | 1164.2342 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 49 | 2030-11-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 50 | 2030-12-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 51 | 2031-01-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 52 | 2031-02-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 53 | 2031-03-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 54 | 2031-04-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 55 | 2031-05-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 56 | 2031-06-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 57 | 2031-07-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 58 | 2031-08-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 59 | 2031-09-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | TOOLS-CI | 60 | 2031-10-01 | 23 | 52.6436 | 1210.8036 | 0 | 0 | TOOLS
Growth | LEGAL-SETUP | 1 | 2026-11-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 2 | 2026-12-01 | 1 | 20000 | 20000 | 20000 | 0 | LEGAL
Growth | LEGAL-SETUP | 3 | 2027-01-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 4 | 2027-02-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 5 | 2027-03-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 6 | 2027-04-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 7 | 2027-05-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 8 | 2027-06-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 9 | 2027-07-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 10 | 2027-08-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 11 | 2027-09-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 12 | 2027-10-01 | 0 | 20000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 13 | 2027-11-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 14 | 2027-12-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 15 | 2028-01-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 16 | 2028-02-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 17 | 2028-03-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 18 | 2028-04-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 19 | 2028-05-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 20 | 2028-06-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 21 | 2028-07-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 22 | 2028-08-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 23 | 2028-09-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 24 | 2028-10-01 | 0 | 20800 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 25 | 2028-11-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 26 | 2028-12-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 27 | 2029-01-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 28 | 2029-02-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 29 | 2029-03-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 30 | 2029-04-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 31 | 2029-05-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 32 | 2029-06-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 33 | 2029-07-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 34 | 2029-08-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 35 | 2029-09-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 36 | 2029-10-01 | 0 | 21632 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 37 | 2029-11-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 38 | 2029-12-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 39 | 2030-01-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 40 | 2030-02-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 41 | 2030-03-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 42 | 2030-04-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 43 | 2030-05-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 44 | 2030-06-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 45 | 2030-07-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 46 | 2030-08-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 47 | 2030-09-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 48 | 2030-10-01 | 0 | 22497.28 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 49 | 2030-11-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 50 | 2030-12-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 51 | 2031-01-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 52 | 2031-02-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 53 | 2031-03-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 54 | 2031-04-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 55 | 2031-05-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 56 | 2031-06-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 57 | 2031-07-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 58 | 2031-08-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 59 | 2031-09-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-SETUP | 60 | 2031-10-01 | 0 | 23397.1712 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 1 | 2026-11-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 2 | 2026-12-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 3 | 2027-01-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 4 | 2027-02-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 5 | 2027-03-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 6 | 2027-04-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 7 | 2027-05-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 8 | 2027-06-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 9 | 2027-07-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 10 | 2027-08-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 11 | 2027-09-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 12 | 2027-10-01 | 0 | 12000 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 13 | 2027-11-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 14 | 2027-12-01 | 1 | 12480 | 12480 | 12480 | 0 | LEGAL
Growth | LEGAL-RENEW | 15 | 2028-01-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 16 | 2028-02-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 17 | 2028-03-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 18 | 2028-04-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 19 | 2028-05-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 20 | 2028-06-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 21 | 2028-07-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 22 | 2028-08-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 23 | 2028-09-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 24 | 2028-10-01 | 0 | 12480 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 25 | 2028-11-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 26 | 2028-12-01 | 1 | 12979.2 | 12979.2 | 12979.2 | 0 | LEGAL
Growth | LEGAL-RENEW | 27 | 2029-01-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 28 | 2029-02-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 29 | 2029-03-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 30 | 2029-04-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 31 | 2029-05-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 32 | 2029-06-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 33 | 2029-07-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 34 | 2029-08-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 35 | 2029-09-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 36 | 2029-10-01 | 0 | 12979.2 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 37 | 2029-11-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 38 | 2029-12-01 | 1 | 13498.368 | 13498.368 | 13498.368 | 0 | LEGAL
Growth | LEGAL-RENEW | 39 | 2030-01-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 40 | 2030-02-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 41 | 2030-03-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 42 | 2030-04-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 43 | 2030-05-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 44 | 2030-06-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 45 | 2030-07-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 46 | 2030-08-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 47 | 2030-09-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 48 | 2030-10-01 | 0 | 13498.368 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 49 | 2030-11-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 50 | 2030-12-01 | 1 | 14038.3027 | 14038.3027 | 14038.3027 | 0 | LEGAL
Growth | LEGAL-RENEW | 51 | 2031-01-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 52 | 2031-02-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 53 | 2031-03-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 54 | 2031-04-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 55 | 2031-05-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 56 | 2031-06-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 57 | 2031-07-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 58 | 2031-08-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 59 | 2031-09-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | LEGAL-RENEW | 60 | 2031-10-01 | 0 | 14038.3027 | 0 | 0 | 0 | LEGAL
Growth | SECURITY-TEST | 1 | 2026-11-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 2 | 2026-12-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 3 | 2027-01-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 4 | 2027-02-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 5 | 2027-03-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 6 | 2027-04-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 7 | 2027-05-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 8 | 2027-06-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 9 | 2027-07-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 10 | 2027-08-01 | 1 | 18000 | 18000 | 18000 | 0 | SECURITY
Growth | SECURITY-TEST | 11 | 2027-09-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 12 | 2027-10-01 | 0 | 18000 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 13 | 2027-11-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 14 | 2027-12-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 15 | 2028-01-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 16 | 2028-02-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 17 | 2028-03-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 18 | 2028-04-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 19 | 2028-05-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 20 | 2028-06-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 21 | 2028-07-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 22 | 2028-08-01 | 1 | 18720 | 18720 | 18720 | 0 | SECURITY
Growth | SECURITY-TEST | 23 | 2028-09-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 24 | 2028-10-01 | 0 | 18720 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 25 | 2028-11-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 26 | 2028-12-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 27 | 2029-01-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 28 | 2029-02-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 29 | 2029-03-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 30 | 2029-04-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 31 | 2029-05-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 32 | 2029-06-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 33 | 2029-07-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 34 | 2029-08-01 | 1 | 19468.8 | 19468.8 | 19468.8 | 0 | SECURITY
Growth | SECURITY-TEST | 35 | 2029-09-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 36 | 2029-10-01 | 0 | 19468.8 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 37 | 2029-11-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 38 | 2029-12-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 39 | 2030-01-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 40 | 2030-02-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 41 | 2030-03-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 42 | 2030-04-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 43 | 2030-05-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 44 | 2030-06-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 45 | 2030-07-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 46 | 2030-08-01 | 1 | 20247.552 | 20247.552 | 20247.552 | 0 | SECURITY
Growth | SECURITY-TEST | 47 | 2030-09-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 48 | 2030-10-01 | 0 | 20247.552 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 49 | 2030-11-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 50 | 2030-12-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 51 | 2031-01-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 52 | 2031-02-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 53 | 2031-03-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 54 | 2031-04-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 55 | 2031-05-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 56 | 2031-06-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 57 | 2031-07-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 58 | 2031-08-01 | 1 | 21057.4541 | 21057.4541 | 21057.4541 | 0 | SECURITY
Growth | SECURITY-TEST | 59 | 2031-09-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | SECURITY-TEST | 60 | 2031-10-01 | 0 | 21057.4541 | 0 | 0 | 0 | SECURITY
Growth | COMPLIANCE-EXT | 1 | 2026-11-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 2 | 2026-12-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 3 | 2027-01-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 4 | 2027-02-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 5 | 2027-03-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 6 | 2027-04-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 7 | 2027-05-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 8 | 2027-06-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 9 | 2027-07-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 10 | 2027-08-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 11 | 2027-09-01 | 1 | 15000 | 15000 | 15000 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 12 | 2027-10-01 | 0 | 15000 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 13 | 2027-11-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 14 | 2027-12-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 15 | 2028-01-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 16 | 2028-02-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 17 | 2028-03-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 18 | 2028-04-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 19 | 2028-05-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 20 | 2028-06-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 21 | 2028-07-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 22 | 2028-08-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 23 | 2028-09-01 | 1 | 15600 | 15600 | 15600 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 24 | 2028-10-01 | 0 | 15600 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 25 | 2028-11-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 26 | 2028-12-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 27 | 2029-01-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 28 | 2029-02-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 29 | 2029-03-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 30 | 2029-04-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 31 | 2029-05-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 32 | 2029-06-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 33 | 2029-07-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 34 | 2029-08-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 35 | 2029-09-01 | 1 | 16224 | 16224 | 16224 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 36 | 2029-10-01 | 0 | 16224 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 37 | 2029-11-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 38 | 2029-12-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 39 | 2030-01-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 40 | 2030-02-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 41 | 2030-03-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 42 | 2030-04-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 43 | 2030-05-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 44 | 2030-06-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 45 | 2030-07-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 46 | 2030-08-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 47 | 2030-09-01 | 1 | 16872.96 | 16872.96 | 16872.96 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 48 | 2030-10-01 | 0 | 16872.96 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 49 | 2030-11-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 50 | 2030-12-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 51 | 2031-01-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 52 | 2031-02-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 53 | 2031-03-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 54 | 2031-04-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 55 | 2031-05-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 56 | 2031-06-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 57 | 2031-07-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 58 | 2031-08-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 59 | 2031-09-01 | 1 | 17547.8784 | 17547.8784 | 17547.8784 | 0 | COMPLIANCE
Growth | COMPLIANCE-EXT | 60 | 2031-10-01 | 0 | 17547.8784 | 0 | 0 | 0 | COMPLIANCE
Growth | INSURANCE | 1 | 2026-11-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 2 | 2026-12-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 3 | 2027-01-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 4 | 2027-02-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 5 | 2027-03-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 6 | 2027-04-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 7 | 2027-05-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 8 | 2027-06-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 9 | 2027-07-01 | 1 | 12000 | 12000 | 12000 | 0 | INSURANCE
Growth | INSURANCE | 10 | 2027-08-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 11 | 2027-09-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 12 | 2027-10-01 | 0 | 12000 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 13 | 2027-11-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 14 | 2027-12-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 15 | 2028-01-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 16 | 2028-02-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 17 | 2028-03-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 18 | 2028-04-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 19 | 2028-05-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 20 | 2028-06-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 21 | 2028-07-01 | 1 | 12480 | 12480 | 12480 | 0 | INSURANCE
Growth | INSURANCE | 22 | 2028-08-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 23 | 2028-09-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 24 | 2028-10-01 | 0 | 12480 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 25 | 2028-11-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 26 | 2028-12-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 27 | 2029-01-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 28 | 2029-02-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 29 | 2029-03-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 30 | 2029-04-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 31 | 2029-05-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 32 | 2029-06-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 33 | 2029-07-01 | 1 | 12979.2 | 12979.2 | 12979.2 | 0 | INSURANCE
Growth | INSURANCE | 34 | 2029-08-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 35 | 2029-09-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 36 | 2029-10-01 | 0 | 12979.2 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 37 | 2029-11-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 38 | 2029-12-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 39 | 2030-01-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 40 | 2030-02-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 41 | 2030-03-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 42 | 2030-04-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 43 | 2030-05-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 44 | 2030-06-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 45 | 2030-07-01 | 1 | 13498.368 | 13498.368 | 13498.368 | 0 | INSURANCE
Growth | INSURANCE | 46 | 2030-08-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 47 | 2030-09-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 48 | 2030-10-01 | 0 | 13498.368 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 49 | 2030-11-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 50 | 2030-12-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 51 | 2031-01-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 52 | 2031-02-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 53 | 2031-03-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 54 | 2031-04-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 55 | 2031-05-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 56 | 2031-06-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 57 | 2031-07-01 | 1 | 14038.3027 | 14038.3027 | 14038.3027 | 0 | INSURANCE
Growth | INSURANCE | 58 | 2031-08-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 59 | 2031-09-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | INSURANCE | 60 | 2031-10-01 | 0 | 14038.3027 | 0 | 0 | 0 | INSURANCE
Growth | ACCOUNTING | 1 | 2026-11-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 2 | 2026-12-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 3 | 2027-01-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 4 | 2027-02-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 5 | 2027-03-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 6 | 2027-04-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 7 | 2027-05-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 8 | 2027-06-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 9 | 2027-07-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 10 | 2027-08-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 11 | 2027-09-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 12 | 2027-10-01 | 1 | 600 | 600 | 600 | 0 | ACCOUNTING
Growth | ACCOUNTING | 13 | 2027-11-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 14 | 2027-12-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 15 | 2028-01-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 16 | 2028-02-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 17 | 2028-03-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 18 | 2028-04-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 19 | 2028-05-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 20 | 2028-06-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 21 | 2028-07-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 22 | 2028-08-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 23 | 2028-09-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 24 | 2028-10-01 | 1 | 624 | 624 | 624 | 0 | ACCOUNTING
Growth | ACCOUNTING | 25 | 2028-11-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 26 | 2028-12-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 27 | 2029-01-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 28 | 2029-02-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 29 | 2029-03-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 30 | 2029-04-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 31 | 2029-05-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 32 | 2029-06-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 33 | 2029-07-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 34 | 2029-08-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 35 | 2029-09-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 36 | 2029-10-01 | 1 | 648.96 | 648.96 | 648.96 | 0 | ACCOUNTING
Growth | ACCOUNTING | 37 | 2029-11-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 38 | 2029-12-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 39 | 2030-01-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 40 | 2030-02-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 41 | 2030-03-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 42 | 2030-04-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 43 | 2030-05-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 44 | 2030-06-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 45 | 2030-07-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 46 | 2030-08-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 47 | 2030-09-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 48 | 2030-10-01 | 1 | 674.9184 | 674.9184 | 674.9184 | 0 | ACCOUNTING
Growth | ACCOUNTING | 49 | 2030-11-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 50 | 2030-12-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 51 | 2031-01-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 52 | 2031-02-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 53 | 2031-03-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 54 | 2031-04-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 55 | 2031-05-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 56 | 2031-06-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 57 | 2031-07-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 58 | 2031-08-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 59 | 2031-09-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | ACCOUNTING | 60 | 2031-10-01 | 1 | 701.9151 | 701.9151 | 701.9151 | 0 | ACCOUNTING
Growth | SUPPORT | 1 | 2026-11-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Growth | SUPPORT | 2 | 2026-12-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Growth | SUPPORT | 3 | 2027-01-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Growth | SUPPORT | 4 | 2027-02-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Growth | SUPPORT | 5 | 2027-03-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Growth | SUPPORT | 6 | 2027-04-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Growth | SUPPORT | 7 | 2027-05-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Growth | SUPPORT | 8 | 2027-06-01 | 0 | 100 | 0 | 0 | 0 | SUPPORT
Growth | SUPPORT | 9 | 2027-07-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Growth | SUPPORT | 10 | 2027-08-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Growth | SUPPORT | 11 | 2027-09-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Growth | SUPPORT | 12 | 2027-10-01 | 1 | 100 | 100 | 0 | 0 | SUPPORT
Growth | SUPPORT | 13 | 2027-11-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 14 | 2027-12-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 15 | 2028-01-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 16 | 2028-02-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 17 | 2028-03-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 18 | 2028-04-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 19 | 2028-05-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 20 | 2028-06-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 21 | 2028-07-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 22 | 2028-08-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 23 | 2028-09-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 24 | 2028-10-01 | 1 | 104 | 104 | 0 | 0 | SUPPORT
Growth | SUPPORT | 25 | 2028-11-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 26 | 2028-12-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 27 | 2029-01-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 28 | 2029-02-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 29 | 2029-03-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 30 | 2029-04-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 31 | 2029-05-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 32 | 2029-06-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 33 | 2029-07-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 34 | 2029-08-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 35 | 2029-09-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 36 | 2029-10-01 | 1 | 108.16 | 108.16 | 0 | 0 | SUPPORT
Growth | SUPPORT | 37 | 2029-11-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 38 | 2029-12-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 39 | 2030-01-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 40 | 2030-02-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 41 | 2030-03-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 42 | 2030-04-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 43 | 2030-05-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 44 | 2030-06-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 45 | 2030-07-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 46 | 2030-08-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 47 | 2030-09-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 48 | 2030-10-01 | 1 | 112.4864 | 112.4864 | 0 | 0 | SUPPORT
Growth | SUPPORT | 49 | 2030-11-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 50 | 2030-12-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 51 | 2031-01-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 52 | 2031-02-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 53 | 2031-03-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 54 | 2031-04-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 55 | 2031-05-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 56 | 2031-06-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 57 | 2031-07-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 58 | 2031-08-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 59 | 2031-09-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | SUPPORT | 60 | 2031-10-01 | 1 | 116.9859 | 116.9859 | 0 | 0 | SUPPORT
Growth | MARKETING | 1 | 2026-11-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 2 | 2026-12-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 3 | 2027-01-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 4 | 2027-02-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 5 | 2027-03-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 6 | 2027-04-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 7 | 2027-05-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 8 | 2027-06-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 9 | 2027-07-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 10 | 2027-08-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 11 | 2027-09-01 | 0 | 75 | 0 | 0 | 0 | MARKETING
Growth | MARKETING | 12 | 2027-10-01 | 2 | 75 | 150 | 0 | 0 | MARKETING
Growth | MARKETING | 13 | 2027-11-01 | 3.98 | 78 | 310.44 | 0 | 0 | MARKETING
Growth | MARKETING | 14 | 2027-12-01 | 5.9402 | 78 | 463.3356 | 0 | 0 | MARKETING
Growth | MARKETING | 15 | 2028-01-01 | 7.8808 | 78 | 614.7022 | 0 | 0 | MARKETING
Growth | MARKETING | 16 | 2028-02-01 | 9.802 | 78 | 764.5552 | 0 | 0 | MARKETING
Growth | MARKETING | 17 | 2028-03-01 | 11.704 | 78 | 912.9097 | 0 | 0 | MARKETING
Growth | MARKETING | 18 | 2028-04-01 | 13.5869 | 78 | 1059.7806 | 0 | 0 | MARKETING
Growth | MARKETING | 19 | 2028-05-01 | 15.4511 | 78 | 1205.1828 | 0 | 0 | MARKETING
Growth | MARKETING | 20 | 2028-06-01 | 17.2966 | 78 | 1349.1309 | 0 | 0 | MARKETING
Growth | MARKETING | 21 | 2028-07-01 | 19.1236 | 78 | 1491.6396 | 0 | 0 | MARKETING
Growth | MARKETING | 22 | 2028-08-01 | 20.9323 | 78 | 1632.7232 | 0 | 0 | MARKETING
Growth | MARKETING | 23 | 2028-09-01 | 22.723 | 78 | 1772.396 | 0 | 0 | MARKETING
Growth | MARKETING | 24 | 2028-10-01 | 25.8958 | 78 | 2019.872 | 0 | 0 | MARKETING
Growth | MARKETING | 25 | 2028-11-01 | 29.0368 | 81.12 | 2355.4683 | 0 | 0 | MARKETING
Growth | MARKETING | 26 | 2028-12-01 | 32.1465 | 81.12 | 2607.7216 | 0 | 0 | MARKETING
Growth | MARKETING | 27 | 2029-01-01 | 35.225 | 81.12 | 2857.4524 | 0 | 0 | MARKETING
Growth | MARKETING | 28 | 2029-02-01 | 38.2728 | 81.12 | 3104.6858 | 0 | 0 | MARKETING
Growth | MARKETING | 29 | 2029-03-01 | 41.29 | 81.12 | 3349.447 | 0 | 0 | MARKETING
Growth | MARKETING | 30 | 2029-04-01 | 44.2771 | 81.12 | 3591.7605 | 0 | 0 | MARKETING
Growth | MARKETING | 31 | 2029-05-01 | 47.2344 | 81.12 | 3831.6509 | 0 | 0 | MARKETING
Growth | MARKETING | 32 | 2029-06-01 | 50.162 | 81.12 | 4069.1424 | 0 | 0 | MARKETING
Growth | MARKETING | 33 | 2029-07-01 | 53.0604 | 81.12 | 4304.259 | 0 | 0 | MARKETING
Growth | MARKETING | 34 | 2029-08-01 | 55.9298 | 81.12 | 4537.0244 | 0 | 0 | MARKETING
Growth | MARKETING | 35 | 2029-09-01 | 58.7705 | 81.12 | 4767.4621 | 0 | 0 | MARKETING
Growth | MARKETING | 36 | 2029-10-01 | 63.9628 | 81.12 | 5188.6611 | 0 | 0 | MARKETING
Growth | MARKETING | 37 | 2029-11-01 | 69.1032 | 84.3648 | 5829.874 | 0 | 0 | MARKETING
Growth | MARKETING | 38 | 2029-12-01 | 74.1921 | 84.3648 | 6259.2038 | 0 | 0 | MARKETING
Growth | MARKETING | 39 | 2030-01-01 | 79.2302 | 84.3648 | 6684.2403 | 0 | 0 | MARKETING
Growth | MARKETING | 40 | 2030-02-01 | 84.2179 | 84.3648 | 7105.0265 | 0 | 0 | MARKETING
Growth | MARKETING | 41 | 2030-03-01 | 89.1557 | 84.3648 | 7521.6048 | 0 | 0 | MARKETING
Growth | MARKETING | 42 | 2030-04-01 | 94.0442 | 84.3648 | 7934.0172 | 0 | 0 | MARKETING
Growth | MARKETING | 43 | 2030-05-01 | 98.8837 | 84.3648 | 8342.3056 | 0 | 0 | MARKETING
Growth | MARKETING | 44 | 2030-06-01 | 103.6749 | 84.3648 | 8746.5111 | 0 | 0 | MARKETING
Growth | MARKETING | 45 | 2030-07-01 | 108.4181 | 84.3648 | 9146.6745 | 0 | 0 | MARKETING
Growth | MARKETING | 46 | 2030-08-01 | 113.114 | 84.3648 | 9542.8363 | 0 | 0 | MARKETING
Growth | MARKETING | 47 | 2030-09-01 | 117.7628 | 84.3648 | 9935.0365 | 0 | 0 | MARKETING
Growth | MARKETING | 48 | 2030-10-01 | 126.4112 | 84.3648 | 10664.6547 | 0 | 0 | MARKETING
Growth | MARKETING | 49 | 2030-11-01 | 134.9731 | 87.7394 | 11842.4557 | 0 | 0 | MARKETING
Growth | MARKETING | 50 | 2030-12-01 | 143.4493 | 87.7394 | 12586.1584 | 0 | 0 | MARKETING
Growth | MARKETING | 51 | 2031-01-01 | 151.8409 | 87.7394 | 13322.4241 | 0 | 0 | MARKETING
Growth | MARKETING | 52 | 2031-02-01 | 160.1484 | 87.7394 | 14051.3271 | 0 | 0 | MARKETING
Growth | MARKETING | 53 | 2031-03-01 | 168.373 | 87.7394 | 14772.9411 | 0 | 0 | MARKETING
Growth | MARKETING | 54 | 2031-04-01 | 176.5152 | 87.7394 | 15487.339 | 0 | 0 | MARKETING
Growth | MARKETING | 55 | 2031-05-01 | 184.5761 | 87.7394 | 16194.5929 | 0 | 0 | MARKETING
Growth | MARKETING | 56 | 2031-06-01 | 192.5563 | 87.7394 | 16894.7742 | 0 | 0 | MARKETING
Growth | MARKETING | 57 | 2031-07-01 | 200.4568 | 87.7394 | 17587.9537 | 0 | 0 | MARKETING
Growth | MARKETING | 58 | 2031-08-01 | 208.2782 | 87.7394 | 18274.2015 | 0 | 0 | MARKETING
Growth | MARKETING | 59 | 2031-09-01 | 216.0214 | 87.7394 | 18953.5867 | 0 | 0 | MARKETING
Growth | MARKETING | 60 | 2031-10-01 | 230.5654 | 87.7394 | 20229.6672 | 0 | 0 | MARKETING
Growth | ONBOARD | 1 | 2026-11-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 2 | 2026-12-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 3 | 2027-01-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 4 | 2027-02-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 5 | 2027-03-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 6 | 2027-04-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 7 | 2027-05-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 8 | 2027-06-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 9 | 2027-07-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 10 | 2027-08-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 11 | 2027-09-01 | 0 | 300 | 0 | 0 | 0 | ONBOARD
Growth | ONBOARD | 12 | 2027-10-01 | 2 | 300 | 600 | 0 | 0 | ONBOARD
Growth | ONBOARD | 13 | 2027-11-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 14 | 2027-12-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 15 | 2028-01-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 16 | 2028-02-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 17 | 2028-03-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 18 | 2028-04-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 19 | 2028-05-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 20 | 2028-06-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 21 | 2028-07-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 22 | 2028-08-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 23 | 2028-09-01 | 2 | 312 | 624 | 0 | 0 | ONBOARD
Growth | ONBOARD | 24 | 2028-10-01 | 3.4 | 312 | 1060.8 | 0 | 0 | ONBOARD
Growth | ONBOARD | 25 | 2028-11-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 26 | 2028-12-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 27 | 2029-01-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 28 | 2029-02-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 29 | 2029-03-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 30 | 2029-04-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 31 | 2029-05-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 32 | 2029-06-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 33 | 2029-07-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 34 | 2029-08-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 35 | 2029-09-01 | 3.4 | 324.48 | 1103.232 | 0 | 0 | ONBOARD
Growth | ONBOARD | 36 | 2029-10-01 | 5.78 | 324.48 | 1875.4944 | 0 | 0 | ONBOARD
Growth | ONBOARD | 37 | 2029-11-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 38 | 2029-12-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 39 | 2030-01-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 40 | 2030-02-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 41 | 2030-03-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 42 | 2030-04-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 43 | 2030-05-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 44 | 2030-06-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 45 | 2030-07-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 46 | 2030-08-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 47 | 2030-09-01 | 5.78 | 337.4592 | 1950.5142 | 0 | 0 | ONBOARD
Growth | ONBOARD | 48 | 2030-10-01 | 9.826 | 337.4592 | 3315.8741 | 0 | 0 | ONBOARD
Growth | ONBOARD | 49 | 2030-11-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 50 | 2030-12-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 51 | 2031-01-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 52 | 2031-02-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 53 | 2031-03-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 54 | 2031-04-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 55 | 2031-05-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 56 | 2031-06-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 57 | 2031-07-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 58 | 2031-08-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 59 | 2031-09-01 | 9.826 | 350.9576 | 3448.5091 | 0 | 0 | ONBOARD
Growth | ONBOARD | 60 | 2031-10-01 | 16.7042 | 350.9576 | 5862.4654 | 0 | 0 | ONBOARD
Growth | AI-IN | 1 | 2026-11-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 2 | 2026-12-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 3 | 2027-01-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 4 | 2027-02-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 5 | 2027-03-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 6 | 2027-04-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 7 | 2027-05-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 8 | 2027-06-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 9 | 2027-07-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 10 | 2027-08-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 11 | 2027-09-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 12 | 2027-10-01 | 0 | 0.4 | 0 | 0 | 0 | AI
Growth | AI-IN | 13 | 2027-11-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 14 | 2027-12-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 15 | 2028-01-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 16 | 2028-02-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 17 | 2028-03-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 18 | 2028-04-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 19 | 2028-05-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 20 | 2028-06-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 21 | 2028-07-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 22 | 2028-08-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 23 | 2028-09-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 24 | 2028-10-01 | 0 | 0.416 | 0 | 0 | 0 | AI
Growth | AI-IN | 25 | 2028-11-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 26 | 2028-12-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 27 | 2029-01-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 28 | 2029-02-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 29 | 2029-03-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 30 | 2029-04-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 31 | 2029-05-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 32 | 2029-06-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 33 | 2029-07-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 34 | 2029-08-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 35 | 2029-09-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 36 | 2029-10-01 | 0 | 0.43264 | 0 | 0 | 0 | AI
Growth | AI-IN | 37 | 2029-11-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 38 | 2029-12-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 39 | 2030-01-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 40 | 2030-02-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 41 | 2030-03-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 42 | 2030-04-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 43 | 2030-05-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 44 | 2030-06-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 45 | 2030-07-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 46 | 2030-08-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 47 | 2030-09-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 48 | 2030-10-01 | 0 | 0.44995 | 0 | 0 | 0 | AI
Growth | AI-IN | 49 | 2030-11-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 50 | 2030-12-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 51 | 2031-01-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 52 | 2031-02-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 53 | 2031-03-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 54 | 2031-04-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 55 | 2031-05-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 56 | 2031-06-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 57 | 2031-07-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 58 | 2031-08-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 59 | 2031-09-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-IN | 60 | 2031-10-01 | 0 | 0.46794 | 0 | 0 | 0 | AI
Growth | AI-OUT | 1 | 2026-11-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 2 | 2026-12-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 3 | 2027-01-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 4 | 2027-02-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 5 | 2027-03-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 6 | 2027-04-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 7 | 2027-05-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 8 | 2027-06-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 9 | 2027-07-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 10 | 2027-08-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 11 | 2027-09-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 12 | 2027-10-01 | 0 | 1.6 | 0 | 0 | 0 | AI
Growth | AI-OUT | 13 | 2027-11-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 14 | 2027-12-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 15 | 2028-01-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 16 | 2028-02-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 17 | 2028-03-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 18 | 2028-04-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 19 | 2028-05-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 20 | 2028-06-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 21 | 2028-07-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 22 | 2028-08-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 23 | 2028-09-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 24 | 2028-10-01 | 0 | 1.664 | 0 | 0 | 0 | AI
Growth | AI-OUT | 25 | 2028-11-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 26 | 2028-12-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 27 | 2029-01-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 28 | 2029-02-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 29 | 2029-03-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 30 | 2029-04-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 31 | 2029-05-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 32 | 2029-06-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 33 | 2029-07-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 34 | 2029-08-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 35 | 2029-09-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 36 | 2029-10-01 | 0 | 1.7306 | 0 | 0 | 0 | AI
Growth | AI-OUT | 37 | 2029-11-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 38 | 2029-12-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 39 | 2030-01-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 40 | 2030-02-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 41 | 2030-03-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 42 | 2030-04-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 43 | 2030-05-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 44 | 2030-06-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 45 | 2030-07-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 46 | 2030-08-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 47 | 2030-09-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 48 | 2030-10-01 | 0 | 1.7998 | 0 | 0 | 0 | AI
Growth | AI-OUT | 49 | 2030-11-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 50 | 2030-12-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 51 | 2031-01-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 52 | 2031-02-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 53 | 2031-03-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 54 | 2031-04-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 55 | 2031-05-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 56 | 2031-06-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 57 | 2031-07-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 58 | 2031-08-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 59 | 2031-09-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-OUT | 60 | 2031-10-01 | 0 | 1.8718 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 1 | 2026-11-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 2 | 2026-12-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 3 | 2027-01-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 4 | 2027-02-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 5 | 2027-03-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 6 | 2027-04-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 7 | 2027-05-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 8 | 2027-06-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 9 | 2027-07-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 10 | 2027-08-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 11 | 2027-09-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 12 | 2027-10-01 | 0 | 15000 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 13 | 2027-11-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 14 | 2027-12-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 15 | 2028-01-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 16 | 2028-02-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 17 | 2028-03-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 18 | 2028-04-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 19 | 2028-05-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 20 | 2028-06-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 21 | 2028-07-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 22 | 2028-08-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 23 | 2028-09-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 24 | 2028-10-01 | 0 | 15600 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 25 | 2028-11-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 26 | 2028-12-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 27 | 2029-01-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 28 | 2029-02-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 29 | 2029-03-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 30 | 2029-04-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 31 | 2029-05-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 32 | 2029-06-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 33 | 2029-07-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 34 | 2029-08-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 35 | 2029-09-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 36 | 2029-10-01 | 0 | 16224 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 37 | 2029-11-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 38 | 2029-12-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 39 | 2030-01-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 40 | 2030-02-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 41 | 2030-03-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 42 | 2030-04-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 43 | 2030-05-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 44 | 2030-06-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 45 | 2030-07-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 46 | 2030-08-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 47 | 2030-09-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 48 | 2030-10-01 | 0 | 16872.96 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 49 | 2030-11-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 50 | 2030-12-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 51 | 2031-01-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 52 | 2031-02-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 53 | 2031-03-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 54 | 2031-04-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 55 | 2031-05-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 56 | 2031-06-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 57 | 2031-07-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 58 | 2031-08-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 59 | 2031-09-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | AI-EVAL | 60 | 2031-10-01 | 0 | 17547.8784 | 0 | 0 | 0 | AI
Growth | CTMS-EXT | 1 | 2026-11-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 2 | 2026-12-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 3 | 2027-01-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 4 | 2027-02-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 5 | 2027-03-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 6 | 2027-04-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 7 | 2027-05-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 8 | 2027-06-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 9 | 2027-07-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 10 | 2027-08-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 11 | 2027-09-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 12 | 2027-10-01 | 0 | 40000 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 13 | 2027-11-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 14 | 2027-12-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 15 | 2028-01-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 16 | 2028-02-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 17 | 2028-03-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 18 | 2028-04-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 19 | 2028-05-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 20 | 2028-06-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 21 | 2028-07-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 22 | 2028-08-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 23 | 2028-09-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 24 | 2028-10-01 | 0 | 41600 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 25 | 2028-11-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 26 | 2028-12-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 27 | 2029-01-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 28 | 2029-02-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 29 | 2029-03-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 30 | 2029-04-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 31 | 2029-05-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 32 | 2029-06-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 33 | 2029-07-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 34 | 2029-08-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 35 | 2029-09-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 36 | 2029-10-01 | 0 | 43264 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 37 | 2029-11-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 38 | 2029-12-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 39 | 2030-01-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 40 | 2030-02-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 41 | 2030-03-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 42 | 2030-04-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 43 | 2030-05-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 44 | 2030-06-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 45 | 2030-07-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 46 | 2030-08-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 47 | 2030-09-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 48 | 2030-10-01 | 0 | 44994.56 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 49 | 2030-11-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 50 | 2030-12-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 51 | 2031-01-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 52 | 2031-02-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 53 | 2031-03-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 54 | 2031-04-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 55 | 2031-05-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 56 | 2031-06-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 57 | 2031-07-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 58 | 2031-08-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 59 | 2031-09-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Growth | CTMS-EXT | 60 | 2031-10-01 | 0 | 46794.3424 | 0 | 0 | 0 | CTMS
Formulas:
Date = EDATE('Start Here'!$B6,[Month]-1)

## Annual Summary
Annual reconciliation ¦ selected scenario
Year 1–5 = consecutive 12-month project years. Calendar summaries include partial first/last years; both sum to the same 60-month spend. Cash is closing balance, not sum of balances.
← Start Here
Basis | Year | Start date | End date | Spend | Revenue | Net burn | Financing | Closing cash | Peak FTE | Staff cash | Infra | Tools | Other vendor | One-time recruitment/equipment | Contingency | Payment fees
Project | 1 | 2026-11-01 | 2027-10-01 | 1027452.55 | 0 | 1027452.55 | 0 | -27452.55 | 6.25 | 750000 | 15000 | 3087 | 72600 | 52750 | 134015.55 | 0
Project | 2 | 2027-11-01 | 2028-10-01 | 1689379.9437 | 67689.207 | 1621690.7367 | 3000000 | 1350856.7133 | 8.75 | 1343680 | 16052.3023 | 5147.94 | 76879.9903 | 25500 | 220089.0349 | 2030.6762
Project | 3 | 2028-11-01 | 2029-10-01 | 2367018.1629 | 216547.6311 | 2150470.5318 | 0 | -799613.8185 | 12.75 | 1893611.2 | 17898.1584 | 6861.9012 | 94256.3352 | 40000 | 307894.1392 | 6496.4289
Project | 4 | 2029-11-01 | 2030-10-01 | 2830931.1213 | 426767.9573 | 2404163.164 | 0 | -3203776.9826 | 12.5 | 2302596.608 | 20419.572 | 8352.8052 | 119177.1736 | 0 | 367581.9238 | 12803.0387
Project | 5 | 2030-11-01 | 2031-10-01 | 2992468.332 | 730515.7807 | 2261952.5513 | 0 | -5465729.5339 | 12.5 | 2394700.4723 | 23985.5434 | 8603.3893 | 155800.0371 | 0 | 387463.4163 | 21915.4734
Calendar | 2026 | 2026-01-01 | 2026-12-31 | 100695.9167 | 0 | 100695.9167 | 0 | 899304.0833 |  | 47666.6667 | 2500 | 245 |  |  | 13134.25 | 0
Calendar | 2027 | 2027-01-01 | 2027-12-31 | 1144030.0075 | 2691 | 1141339.0075 | 3000000 | 2757965.0758 |  | 873240 | 15098.9447 | 3548.58 |  |  | 149210.7753 | 80.73
Calendar | 2028 | 2028-01-01 | 2028-12-31 | 1791908.1412 | 89179.6918 | 1702728.4494 | 0 | 1055236.6265 |  | 1429112.5333 | 16327.2309 | 5377.0738 |  |  | 233378.1848 | 2675.3908
Calendar | 2029 | 2029-01-01 | 2029-12-31 | 2519705.3143 | 246494.5832 | 2273210.731 | 0 | -1217974.1046 |  | 2021038.1013 | 18267.0723 | 7318.3216 |  |  | 327692.6709 | 7394.8375
Calendar | 2030 | 2030-01-01 | 2030-12-31 | 2856736.7551 | 469659.6499 | 2387077.1052 | 0 | -3605051.2098 |  | 2317947.2521 | 20933.8977 | 8394.5692 |  |  | 370780.039 | 14089.7895
Calendar | 2031 | 2031-01-01 | 2031-12-31 | 2494173.9752 | 633495.6511 | 1860678.3241 | 0 | -5465729.5339 |  | 1995583.7269 | 20228.4305 | 7169.4911 |  |  | 322848.1442 | 19004.8695
Reconciliation difference (should be 0) |  |  |  | 0
0
Formulas:
Start date = DATE([Year],1,1)
End date = DATE([Year],12,31)

## Scenario Comparison
Scenario comparison ¦ identical options, different operating assumptions
All three scenarios are live formulas, same global scope/stack switches. Comparison is spend, not valuation. Revenue is unproven; cost-only funding gap is separately visible.
← Start Here
Scenario | 5-year spend | Year 1 spend | Peak FTE | Cash low | Funding gap | Cost-only gap | Unresolved vendor cash | Unpaid founder | Year 5 exit ARR
Lean | 6008393.9276 | 678048.8 | 6.95 | -4247799.8833 | 4247799.8833 | 4508393.9276 | 428483.5562 | 597277.7786 | 145256.2914
Base | 10907250.1099 | 1027452.55 | 12.75 | -5465729.5339 | 5465729.5339 | 6907250.1099 | 428483.5562 | 974938.0608 | 888906.5968
Growth | 20697579.113 | 1515575.5 | 23 | -7025274.2542 | 7025274.2542 | 12697579.113 | 436972.7468 | 1105126.25 | 3873498.5626

## Charts
Formula-linked planning charts
Charts link to financial cells; no screenshots or static chart values. Expand monthly category columns to audit.
← Start Here